LEG/SGO-CAN-35017679-2009

Ms. Lynette P. Holder

Chief Executive Officer

The Barbados Small Business Association

#1 Pelican Industrial Park

St Michael BB11144

Barbados

Fax: 246-228-0613

Ref:	Barbados. Nonreimbursable Technical Cooperation No. ATN/ME-12041-BA. Development of Tourism Micro-Projects in Barbados.

Dear Ms. Holder:

This letter of agreement (the “Agreement”) between the Barbados Small Business Association and the Inter-American Development Bank acting in its capacity as Administrator of the Multilateral Investment Fund, (the “Bank”), which we are submitting for your consideration, is to formalize the terms of a grant of a nonreimbursable technical cooperation (the “Contribution”) to the Beneficiary, up to the amount of one hundred fifty thousand dollars of the United States of America (US$150,000), or its equivalent in other convertible currencies, which shall be chargeable to the resources of the Multilateral Investment Fund to finance the contracting of consulting services and procurement of goods necessary for the execution of a technical cooperation project for the development of tourism micro-projects in Barbados, the “Program”, which is set forth in the Annex of this Agreement. Unless otherwise stated in this Agreement, the term “dollars” shall hereinafter refer to the currency of legal tender in the United States of America.

This Agreement is entered into pursuant to the Agreement Establishing the Multilateral Investment Fund II, hereinafter the “MIF”, and the Agreement for the Administration of the MIF II, dated April 9, 2005.

The Bank and the Beneficiary agree upon the following:

First. Components of the Agreement.  This Agreement consists of this part one, referred to as the “Special Conditions”; part two, referred to as the “General Conditions”, and the Annex, which are attached hereto.  The prevalence between the above-mentioned Sections and Annex is established in Article 1 of the General Conditions.

Second.  Executing Agency.  The Executing Agency of this Program shall be the Barbados Small Business Association, hereinafter referred to as the “Executing Agency” or the “Beneficiary”. The Executing Agency certifies its legal and financial capacity to function as such, and undertakes to fulfill all the obligations that result from this Agreement.

Third.  Conditions Prior to First Disbursement.  The first disbursement of the Contribution shall be equivalent to 40% of the total Contribution and is subject to the fulfillment, to the satisfaction of the Bank, of the conditions set forth in Article 2 of the General Conditions, as well as the following requirements:

- Establishment of the Steering Committee nominated by the Executing Agency and approved by the Bank, including a representative from Ministry of Tourism and the IDB team leader;

- Approval of the ToR and guidelines for the Steering Committee;

- Approval of detailed ToR for the Project Coordinator; and

- Agreement on a detailed work program for the first 12 months, indicating what activities will be done, in what sequence, by whom, when, and indicating how they will be financed.

Fourth.  Reimbursement of Expenditures Chargeable to the Contribution.  With the consent of the Bank, resources of the Contribution may be used to reimburse expenditures incurred or to finance those that may be incurred in the Program on or after November 2, 2009, and up to the date of this Agreement, provided that requirements substantially similar to those set forth in this Agreement have been fulfilled.

Fifth.  Disbursements.  (a) In addition to the conditions set forth in Clause Third, the second and subsequent disbursements of the Contribution shall be subject to the Executing Agency's submission, to the satisfaction of the Bank, of evidence of compliance with the indicators described in paragraph Fifth (b), in accordance with the Annual Operations Plan and the Operational Regulations of this Program. Meeting those targets will not exempt the Executing Agency from achieving the project goals established in the logical framework.

(b) The second disbursement of the Contribution shall be equivalent to 20% of the total Contribution and is subject to the fulfillment, to the satisfaction of the Bank, structured training programs for agro-processing and arts & crafts clusters; (ii) The third disbursement of the Contribution shall be equivalent to 30% of the total Contribution and is subject to the fulfillment, to the satisfaction of the Bank, of the completion and approval of all diagnostic work for three clusters; The fourth disbursement of the Contribution shall be equivalent to 10% of the total Contribution and is subject to the fulfillment, to the satisfaction of the Bank, of the presentation of the approved contract for Impact Evaluation Report. The IDB Project Team Leader must formally accept any amendment of these milestones and corresponding disbursement values.

Sixth.  Deadlines.  (a) The period for execution of the Program shall be twenty (20) months, from the effective date of this Agreement.

(b)	The period for the last disbursement of the resources of the Contribution shall be twenty-six (26) months from the effective date of this Agreement, which shall include the period required for the payment of independent auditors referred to in Article 11 of the General Conditions. Any part of the Contribution which has not been utilized within this period shall be canceled.

(c)	The aforementioned deadlines and any others that may be stipulated in this Agreement may be extended, when duly justified, with the written consent of the Bank.

Seventh.  Total Cost of the Program and Additional Resources.  (a) The Beneficiary undertakes to make timely provision of the resources required, in addition to the Contribution, for the complete and uninterrupted execution of the Program, the “Counterpart Resources.”  The total Counterpart Resources required is estimated to be the equivalent of ninety thousand, five hundred dollars (US$90,500), to make up a sum equivalent to two hundred forty thousand, five hundred dollars (US$240,500), which is estimated to be the total cost of the Program.  These estimates do not reduce the obligation of the Beneficiary to provide any additional resources required to complete the Program.

(b)	The Counterpart Resources provided by the Beneficiary shall be used to finance the cost categories which are chargeable to it, as established in the Program’s budget set forth in the attached Annex. The Total Counterpart Resources of US$90,500 will be provided fifty percent (50%) in cash and fifty percent (50%) in kind contributions.

Eighth.  Recognition of Expenses Chargeable to the Counterpart Resources.  The Bank may recognize, as part of the local contribution, expenditures incurred or which may be incurred in the Program on or after November 2, 2009, and up to the date of this Agreement, provided that requirements substantially similar to those set forth in this Agreement have been fulfilled.

Ninth.  Currencies for Disbursements. The Bank shall disburse the Contribution in dollars or its equivalent in other convertible currencies. The Bank may convert these convertible currencies into other currencies, including the local currency by applying the exchange rate indicated in Article 7 of the General Conditions.

Tenth. Use of Contribution. The resources of the Contribution shall only be used for the payment of consulting services, including per diem and transportation expenses for the purposes of this Program, and goods originating from member countries of the Bank.

Eleventh. Acquisition of goods and services and Selection and contracting of consulting services. The acquisition of goods and related services and the selection and contracting of consulting services will be carried out by the Executing Agency in accordance with the provisions set forth in: (i) Document GN-2349-7 (“Policies For The Procurement Of Works And Goods Financed By The Inter-American Development Bank”); (ii) Document GN-2350-7 ( “Policies for the Selection and Contracting of Consultants Financed by the Inter-American Development Bank”) dated July 2006; and (iii) the Procurement Plan referred to in paragraph Twelfth of these Special Conditions.

Twelfth.	Procurement Plan. Before starting any competitive bidding process or any request for proposals for the acquisition of goods and services (different from consulting services) and for the contracting of consulting services, the Executing Agency shall prepare and furnish to the Bank for its approval, a Procurement Plan acceptable to the Bank setting forth the particular contracts for consulting services required to carry out the Program, including the estimated cost of each contract, and the proposed methods for acquisition of goods and selection of consultants’ services, in accordance with paragraphs 1 of Appendixes 1 of Documents GN-2349-7 and GN-2350-7. This Procurement Plan shall be reviewed by the parties every six (6) months during the execution of the Program, and each updated version shall be submitted to the Bank for approval. The Executing Agency shall implement the Procurement Plan in the manner in which it has been approved by the Bank.

Thirteenth.	Review by the Bank. Unless the Bank agrees otherwise in writing, each contract for the acquisition of goods and consulting services shall be subject to an ex post review. The review will be scheduled every year. The Executing Agency shall co- operate with its review and shall maintain the records and supporting documentation so that it is able to identify every transaction, service and procurement provider, acquired goods and services’ origin, corresponding procurement plan in accordance with Parragraph 4, Appendix 1 of the Procurement Policies..

Fourteenth.	Progress reports and evaluation. During the Execution of the Program, the Executing Agency undertakes to submit to the Bank, within 30 days after the end of each six-month period, project status reports (PSR) during the execution of the Program. These reports will follow a format previously agreed on with the MIF and will report on the status of project execution, the achievement of milestones and the completion of the project’s objectives, as stated in the logical framework and other operational planning tools. The reports will also discuss project issues encountered during execution and possible solutions. Within 90 days after the end of execution, the Executing Agency will submit a final PSR to the Bank detailing the outcomes achieved, a sustainability plan, and lessons learned.

Fifteenth. 	Financial statements. The Executing Agency undertakes to present to the Bank’s satisfaction, the financial statements of the Program duly certified by a firm of independent accountants selected and hired pursuant to Bank’s policies and procedures in accordance with the provision set forth in Article 11(b) of the General Conditions.

Sixteenth .	Information Disclosure. The Beneficiary undertakes to notify the Bank, in writing, within a maximum period of ten (10) working days from the date of signature of this Agreement, whether it considers any part of the Agreement to be confidential or sensitive, or information that may adversely affect relations between the member countries and the Bank or between private sector clients and the Bank, in which case the Beneficiary undertakes to identify those provisions considered as such. In accordance with the Bank’s Disclosure of Information Policy, the Bank will make the text of this Agreement available to the public once it has been signed and has entered into effect, with the sole exception of that information which the Beneficiary has specifically identified as confidential, sensitive or adverse to relations with the Bank in the manner indicated in this paragraph.

Seventeenth.	Notice. Any notice, request, or communication from one party to another by virtue of this Agreement shall be made in writing and shall be considered to have been made when the relevant documents are delivered to the addressee, unless the parties otherwise agree in writing.  If to the Beneficiary, such notice shall be addressed to the same address indicated above.  If to the Bank, such notice shall be addressed to:

Inter-American Development Bank

1300 New York Avenue, N.W.

Washington, D.C. 20577

U.S.A.

Facsimile: (202) 623-3096

Please confirm your acceptance of the terms and conditions of this Agreement, in representation of the Beneficiary, by signing and returning one of the originals to the Bank’s Country Office in Barbados.

This Agreement shall be signed in two (2) originals of equal tenor by duly authorized representatives, and will enter into force on the date of its signature by the Beneficiary.

Yours Faithfully, /s/ Anneke Jessen _______________________ Anneke Jessen Representative of the Bank

AGREED:

/s/ Lynette P. Holder

_____________________________

Ms. Lynette P. Holder

Title: Chief Executive Officer

Date: September 30, 2010