LEGIII/BA-680551-06

ANNEX

THE PROJECT

Institutional Strengthening of the Savings and Loan Cooperatives Sector of Barbados

I.	Objective

1.01	The goal of the Project is to enhance access to financial services through strengthening the credit union sector of Barbados.  The purpose of the Project is to strengthen the capacity and sustainability of the credit unions, and the ability of the regulatory entity for credit unions to implement risk-based supervision.

II.	Description

2.01	In order to achieve the above aforementioned objectives, the Project will finance the following components:

- Component I:  Institutional Strengthening of Credit Unions and Barbados Cooperative Credit Unions League Ltd. (“BCCULL”)

  - This component will consist of three (3) sub-components described below:

- (a)	Design and implementation of risk management tools

  - In order to improve the credit unions’ capacity to manage a more diverse set of risks and a growing membership base, this subcomponent will focus on designing adequate tools to manage financial and pricing risks, operational risks, and credit risks. Policies and procedures will be designed and implemented to assist the cooperatives in better analyzing and measuring their liquidity gaps, the pricing of their products, setting of interest rates, decisions on investments, and use of technology.

  - The first major undertaking under this subcomponent would be the selection of at least twenty (20) credit unions wishing to receive training and technical assistance under the Project. The basic requirement for participation will be the willingness to pay for a percentage of the services and commit resources to the participation. This same procedure will apply for participation in all of the Project’s subcomponents.

  - The following activities will be implemented under this subcomponent: (i) finalizing of the framework and requirement setting for the participation in the Project by the different cooperatives; (ii) Assessing diagnostic and needs of the participating cooperatives to evaluate their current risk management technologies and instruments; (iii) designing, development and upgrading of tools for risk management and control; (iv) providing on-site technical assistance in the individual cooperatives for the deployment of these risk management and control tools; and (v) developing and delivering training courses in risk management and control.

  - The results of this subcomponent will be that at least twenty (20) credit unions receive training and at least fifteen (15) of them receive direct technical assistance in the areas of risk management, allowing them to implement policies and procedures that reduce their levels of arrears, strengthen their level of capitalization and increase their profitability. It is expected that the cooperatives have more frequent and adequate portfolio reports, enhanced repayment schedules and policies, tighter arrears controls, improved pricing controls, adequate provisioning and write off policies, staff capable of performing more rigorous credit risk analysis and more prudent client selection mechanisms.

- (b)	New product development and marketing

  - This subcomponent is aimed to assist the cooperatives in their process of developing financial products more adequate to their membership demands in reference to standards in service and quality.

  - The following activities will be implemented under this subcomponent: (i) a diagnostic analysis of the existing financial services offered by the cooperatives, with specific recommendations as to how these can be enhanced or improved on; (ii) a market analysis of other potential products such as remittances, differentiated savings, small and micro enterprise loans, cooperative ATMs, and others; (iii) development and implementation of at least two (2) new products within the cooperatives along with its corresponding manuals, policies and procedures, and software and hardware adjustments; (iv) development of a marketing strategy to promote cooperative products and services, specially among the smaller members of the BCCULL; and (v) training to the cooperative leadership and staff on the management and marketing of the new products.

  - The result of this sub-component will be a more competitive cooperative sector with credit unions offering a more diverse set of products. In particular, the results will be: (i) at least ten (10) cooperatives will incorporate at least one (1) differentiated savings products; (ii) at least ten (10) cooperatives will implement small and micro enterprise loans as part of their credit offering; and (iii) at least one (1) ten (10) of the smaller range of cooperative will implement a new product.

- (c)	Strengthening of the BCCULL

  - The key activities of this subcomponent will be: (i) establishing the BCCULL’s Training and Education Department as the Project’s Executing Unit;  (ii) developing and implementing, in coordination with the Registrar of Cooperatives (“Registrar”), a strategic plan for the execution of the Project; (iii) organizing a formal Project launching conference to include all potentially interested credit unions and relevant participants from the private sector and the government; (iv) finalizing the terms of reference for the Project’s consulting services and carry out the procurement; (v) implementing an environmental policy and procedure to guide its members in reducing the environmental risks of investments and to ensure that the credit unions apply environmental management procedures; and (vi) designing and developing a plan to transfer the knowledge, methodologies, tools and procedures acquired from the Project, over to the BCCULL.

  - The results of this subcomponent will be: (i) a sustainable Training Education Department housed within the BCCULL; (ii) timely and adequate execution of all activities of the Project; (iii) adequate supervision of the training and consulting services provided by the specialized firm; and (iv) an environmental policy to be included by the BCCULL as part of its official training curricula.

- Component II: Improving the Capacity of the Regulatory Entity

  - This Component of the Project will provide resources to contract specialized training and technical assistance for the Registrar (the office of the Registrar supervises Barbados credit unions). The Registrar, as well as members and leaders from the individual credit unions will participate in this training, so that both entities understand and agree on the basic parameters for risk-based supervision and what it implies for the sector as a whole.

  - The key activities of this Component include: (i) managing the contracting of a specialized consulting firm to provide technical assistance to the Registrar; (ii) developing a set of tools and procedures that will allow the Registrar to implement risk-based supervision; (iii) training and providing key technical assistance to Registrar staff in the areas of risk-based supervision; (iv) financing the exchange visits of key staff to other regional agencies which currently supervise the sector using this approach; and (v) providing specific recommendations on the proposed changes in the Cooperative Law and in the placement of the Registrar within the government’s regulatory structure.

  - The results of this component will be: (i) alignment of the Registrar to the worldwide movement within the financial services industry to risk based supervision; (ii) a more rigorous policy and procedures for credit union inspections; (iii) in-house capacity to assess technological aspects related to credit and financial risks; and (iv) a more rigorous inspection procedure for investments and other liquid cash management.

III.	Total Cost of the Project

3.01	The estimated cost of the Project is the equivalent of one million and three hundred dollars (US$1.300.000), in accordance with the following Budget:

Budget

(in US$)

| # Activities | Bank | Local Contribution | Total |
| --- | --- | --- | --- |
| Component 1. Institutional strengthening of CU and the League | 526,200 | 459,200 | 985,400 |
| Financial and Risk Management Capacity | 216,500 | 71,000 | 287,500 |
| New Product Development | 202,500 | 80,000 | 282,500 |
| Strengthening of BCCULL | 46,000 | 19,000 | 65,000 |
| Executing Unit | 61,200 | 289,200 | 350,400 |
| Component 2. Improving the capacity of the regulatory entity | 270,000 | 0 | 270,000 |
| Evaluation & Audit | 43,800 | 800 | 44,600 |
| TOTAL | 840,000 | 460,000 | 1,300,000 |
|  | 65% | 35% | 100% |

IV.	Execution

  - The Project’s two (2) components will be executed in a closely coordinated manner. For the Component I, BCCULL and specifically its Training and Education Department, will be the Executing Unit, and will contract, through international competitive bidding, a consulting firm recognized for its expertise in finance and cooperative financial management. The Training Officer, responsible for the Education Department of the BCCULL, will act as the Project Coordinator who, along with the General Manager, will supervise and coordinate with the selected firm, Component I implementation.

  - For the Component II, the Bank, acting on behalf of, and in consultation with the Registrar, will procure the services of an international consulting firm to implement the required training and technical assistance. Specifically, the Bank’s Country Office in Barbados will be responsible for the selection of an international consulting firm with best practice capabilities in risk-based supervision, as well as for subsequent monitoring of the firm’s performance.

  - To ensure proper coordination between the two (2) components of the Project: (i) the BCCULL and the Registrar will sign an Agreement outlining the responsibilities and obligations for each one, as well as their commitments to the results of the Project; (ii) the BCCULL and the Bank will coordinate activities and progress in the Project through a Project Committee, conformed by a representative from each; and (iii) the Project Coordinator will ensure activities in both components are being executed as planned, reporting on this aspect in the semester monitoring reports.

- V.	Monitoring and Evaluation

  - Monitoring. Within sixty (60) days of the completion of each six-month period, BCCULL will submit reports to the Country Office in Barbados, which will include:  (i) information on progress toward Project objectives; (ii) a description on the various levels of coordination between the BCCULL and the Registrar; (iii) a description of technical assistance and training received and its quality and outcomes; (iv) a summary of budget execution and counterpart contributions; (v) statistical and financial information on performance, indicating the situation and trends and on whether the annual targets set for the Project indicators have been met; and (vi) information on BCCULL’s financial situation.

  - The Project will also track through the reporting mechanism, advances made towards the implementation of environmental policies and procedures at the BCCULL and individual cooperative level, tracking the number of cooperatives that have integrated these policies into their lending operations. The policies designed by the environmental consultancy will be delivered no later than in the second semiannual progress report.

  - BCCULL will also track a set of the PEARLS indicators (Credit Union Financial Monitoring System - Protection, Effective Financial Structure, Asset Quality, Rates of Return and Costs, Liquidity and Signs of Growth.) that the Registrar already uses to monitor the safety and soundness of credit unions. The Project will track indicators that measure institutional capacity, delinquency levels, profitability and growth.

  - Evaluations. A mid term evaluation will be conducted after fifty per cent  (50%) of the Project budget has been disbursed. With funds provided for in the Project budget, the Bank, through its Country Office in Barbados, will select and hire an external consultant specialized in financial cooperatives to carry out the evaluation.  The evaluation will look at the progress achieved in meeting Project objectives, results and performance targets by credit unions, and will use the Project’s logical framework.

  - This evaluation will consider the following: (i) appropriate use of the Bank’s funds; (ii) selection process for beneficiary credit unions; (iii) performance with respect to the indicators specified in the logical framework; (iv) progress with the execution of each component, based on indicators in the Project’s logical framework as well as the qualitative and quantitative indicators established under this Project; (v) a decision on the Insurance Company, based on the external study; (vi) degree of sustainability of the activities as measured by the amount of revenues generated by the BCCULL from training and participation fees; (vii) effectiveness of the BCCULL in delivering its services, as measured by repeat users and course evaluation forms; (viii) effectiveness of the coordination between the BCCULL and the Registrar, as measured by Project execution milestones and Project monitoring reports; and (ix) adherence  to environmental policies. The mid term evaluation will provide the necessary input for the Bank to take corrective actions or suspend further disbursements, in case Project execution is not resulting in effective and positive impact.

  - A final evaluation will also be performed, when at least ninety five per cent (95%) of the Bank’s funds have been disbursed, and the contents of which must include: (i) measurement of the impact of the Project on the individual cooperative’s financial performance; (ii) measurement of the impact of the Project on the BCCULL and the Registrar; (iii) measurement of the impact of the Project on the quality and quantity of service delivery by the cooperatives to its members; and (iv) identification of best practice and lessons learned from the Project.

  - The Country Office in Barbados will have the basic responsibility for the supervision of the operation and ensure that both components are coordinating activities and agreeing on key issues regarding training, supervision and quality of service delivery. In addition, the Country Office in Barbados will coordinate the terms of reference for the specialized consulting firm that will provide training and technical assistance to the Registrar.  Semiannually, BCCULL and the Country Office in Barbados will conduct Project-monitoring meetings to discuss the six-month report, the progress achieved in reaching performance indicators, and the work plan. Results from the meetings and reports should determine future disbursements for the Project.