Annex a

Document of the Inter-American Development Bank

- Not for Public Use

Barbados

Housing and Neighbourhood Upgrading Programme Propef Individual Operation

(BA-L1011)

# Memorandum of Assistance for Project Preparation and Execution (MAPPE)

This document was prepared by Sharon Miller (COB/CBA); in collaboration with Mauricio Silva (RE3/SC3), Team Leader; Robert Daughters, (SDS/SGC); and Ana Lucía Saettone (RE3/SC3).

Content

Executive Summary

I.	Justification	1

II.	Objectives, and relationship with the profile concept document action plan	2

III.	Description of the beneficiary	3

A.	The benificiary	3

B.	Scope of Services and Action Plan for Project Preparation	3

C.	Procurement and contracting of consulting services	4

IV.	Action plan and terms of reference	4

V.	Cost of the project	5

VI.	Environmental and Social Review	6

A.	PTI/SEQ classification	6

B.	Environmental and social impacts	6

Annexes

| Annex I | Copy of Official Request for use of PROPEF |
| --- | --- |
| Annex II | Lists of Proposed Consultancies |
| Annex III | Terms of Reference |
| Annex IV | Draft Letter of Agreement |
| Annex V | Procurement Plan |

Abbreviations

| CRG | Regional Management Committee |
| --- | --- |
| GOBA | Government of Barbados |
| HNUP | Housing and Neighbourhood Upgrading Programme |
| MAPPE | Memorandum of Assistance for Project Preparation and Execution |
| MHL | Ministry of Housing and Lands |
| MPWT | Ministry of Public Works and Transport |
| NHC | National Housing Corporation |
| PCD | Project Concept Document |
| PCMU | Project Coordinating and Monitoring Unit |
| PROPEF | Project Preparation and Execution Facility |
| TPD | Town Planning Department |

Memorandum of Assistance for Project Preparation and Execution

(MAPPE)

(BA-L1011)

Executive Summary

| Borrower: | Government of Barbados (GOBA) |  |  |
| --- | --- | --- | --- |
| Guarantor: | Government of Barbados (GOBA) |  |  |
| Project Name: | Housing and Neighbourhood Upgrading Programme - PROPEF Individual Operation. |  |  |
| Project Number: | BA-L1011 |  |  |
| Project Team: | Mauricio Silva, Team Leader, and Ana Lucía Saettone (RE3/SC3); Robert Daughters (SDS/SGC); and Sharon Miller (COF/CBA). |  |  |
| Beneficiary: | Ministry of Housing and Lands (MHL) |  |  |
| Executing agency: | Ministry of Housing and Lands (MHL) |  |  |
| Amount and source: | IDB (19/LC-BA): GOBA: Total: | US$688,000 US$137,600 US$825,600 |  |
| Objectives: | The overall objective of this Individual Operation under the PROPEF line of credit is to assist Government to further the preparation of the Housing and Neighbourhood Upgrading Programme (HNUP) through the financing of consultancies to complete technical inputs and detailed designs for four pilot low-income communities. |  |  |
| Description: | Resources under this individual facility will mostly go to support preparation activities under Component 1 Neighbourhood Upgrade of the HNUP Loan. Specifically, the financing will go towards the completion of detailed architectural and engineering designs for the four sites including two special sites located in the capital city, Bridgetown, for revitalization. In addition, the Executing Unit will coordinate surveys to supply baseline data and update the socio demographic profile of the four target communities. Proposals for formulating the institutional strengthening elements of the Ministry of Housing and Lands (MHL) and the National Housing Corporation (NHC) will also be carried out. To ensure the involvement of prospective households and to keep them informed, the PCMU will develop a communications and social marketing strategy. |  |  |
| Procurement: | Procurement will be carried out in accordance with the Bank’s standard procedures. Specific procurement events will be the responsibility of the Project Coordinating and Monitoring Unit (PCMU). However, the Beneficiary has requested the Bank to act on its behalf and engage the services of the consultants, especially those to be hired through international competitive bidding (see ¶III.5 - III.7). |  |  |

- Justification

  - For some time now, the Bank has been collaborating with the Government of Barbados in the preparation and financing of the multiphase Housing and Neighbourhood Upgrading Programme. This Operation is being designed to improve housing conditions of low and lower-middle income families; revitalize and urbanize depressed communities; and expand Government’s support systems and reach for affordable housing. To achieve these objectives, the Programme proposes implementation of three main components: (i) Neighbourhood Upgrading (US$20 million) to finance the national upgrading of low income neighbourhoods including the revitalization of two inner city communities; (ii) Support for Affordable Housing (US$12 million) through the provision of financing for land acquisition and infrastructural development as well as for the introduction of a pilot housing subsidy initiative; and (iii) Sector and Institutional Strengthening (US$8 million) which will include strengthening of the Ministry’s land planning and management approaches, modernization of the NHC, the main housing organization in the country, the improvement of a beneficiary selection system, and project financial costs.

  - Project preparation for this first phase has progressed well despite setbacks in the time it took Government to finalize policy decisions and more recently, in light of the lags associated with Ministerial and management changes within the Executing Unit.  So far, the CRG has approved the Project Concept Document, in October 2005 and the Borrower has now established a Project Executing Unit within the Ministry of Housing and Lands (MHL) with most of the key staff in place.

  - The Bank’s Project Team has utilized resources from the Canadian Technical Assistance Programme to support the preparation of the Loan. Outputs so far under the Neighbourhood Upgrading Component include conceptual designs for upgrading for the two urban sites (Cats Castle and Greenfield) and the two prototypes (Garden Land and Allen View). Other key outputs include the draft operating manual for the program, a proposal for the Affordable Housing aspects, a community involvement strategy and diagnosis reports for the institutional strengthening of the National Housing Cooperation (NHC) and the Ministry of Housing and Lands  (MHL).

  - Additional financial resources are required to advance project preparation to the next level and to obtain more detailed technical inputs for the Project Report. Accordingly, GOBA and the Bank have agreed on a list of vital consultancies (See Annex II) for providing these results. In anticipation of these activities, at the time of the formal request for PROPEF, the Government had also requested financing of up to US$750,000.00 to support the preparation process for HNUP. An amount of US$688,000 is required from PROPEF funds for these consultants while the Government will finance from counterpart resources, start up costs of the Project Executing Unit and administrative support for these consultancies.

- Objectives, and relationship with the profile concept document action plan

  - The main objectives of this individual operation under the PROPEF are to:

      - Assist the Government in advancing preparation of the Housing and Neighbourhood Upgrading Programme through the financing of consultancies to provide technical inputs and detailed designs for four select communities, Cats Castle, Greenfield, Allen View and Garden Land; and

      - Assist the Government in advancing preparation of the Housing and Neighbourhood Upgrading Programme through the financing of consultancies to provide technical inputs and detailed designs for four select communities, Cats Castle, Greenfield, Allen View and Garden Land; and

  - Whilst the first objective will be provided more directly as outputs of the consultants working in collaboration with both the GOBA’s and the Bank’s teams, the second objective will be achieved through the integrated way in which the consultants will be engaged with the Executing Unit.  The transfer of knowledge to those Ministry staff involved has been an important aspect so far in the preparation of this Loan.

  - The objectives for this individual operation are consistent with those outlined for the Housing and Neighbourhood Upgrading Programme as stated in the PCD dated September 23, 2005.  Financing from the PROPEF will support all the components of the proposed Loan and in particular the activities outlined under Component 1, Neighbourhood Upgrading where a consulting firm will provide detailed architectural and engineering designs for the four sites as well as the accompanying bidding documents. There is also provision for individual consultants to assist with the economic analysis of the Project and the preparation of baseline data for inputs to the Programme’s Logical Framework.

  - Board approval, originally scheduled for June 2006, as reflected in the PCD, has been revised for the first quarter of 2007.  Delays were due to the loss of momentum in project preparation caused mainly by ministerial changes, which prolonged the staffing of the executing unit responsible for preparation activities and for serving as suitable counterparts to work alongside the Bank’s team.

- Description of the beneficiary

- A.	The benificiary

  - The PROPEF Line of Credit, 19/LC-BA was signed on April 5, 2006 between the Borrower, the Government of Barbados and the Bank.  With the initiation of the PROPEF on September 5, 2006, the Borrower can now access resources for individual operations.  The Ministry of Economic Affairs and Development is the National Agency responsible for executing this PROPEF and has the authority for financing activities planned by beneficiary agencies that involve the use of this line of credit. The Ministry of Housing and Lands (MHL) is the beneficiary and will be the Executing Agency for this individual operation.

  - The Ministry of Housing and (MHL) has already established a Project Coordinating and Monitoring Unit (PCMU), which will be responsible for programme coordination, monitoring, evaluation and financial administration of the Loan as outlined in the PCD. This Unit will perform similar duties for this PROPEF individual operation.  The PCMU will operate under the guidance of the Permanent Secretary, the accounting officer of the Ministry, but will work in full collaboration with other agencies in implementing the activities contemplated in this operation. In particular, the PCMU will have to call on the cooperation and expertise of the National Housing Corporation, (NHC), Ministry of Social Transformation, (MST) the Ministry of Public Works and Transport (MPWT) and the Town Planning Department (TPD) amongst other public sector agencies, in order to have consultants fulfill their assignments.  The PCMU will also have to work closely with the utilities companies especially within the four sites for neighbourhood upgrading. At the community level, the PCMU will adopt guidelines of the Community Involvement Strategy to formulate and execute community entry and engagement during project preparation and beyond.

- B.	Scope of Services and Action Plan for Project Preparation

  - Resources of the PROPEF will finance an international consulting firm to prepare the detailed architectural and engineering designs for four communities selected as pilot under the HNUP.  Two of the sites, Cats Castle and Greenfield have been selected for urban revitalization in downtown Bridgetown, the capital city.  The other two sites, Allen View and Garden Land represent prototypes for low-income communities already identified in a national inventory for upgrading.  When the designs and attendant bidding documents are finalized, these will be used for the procurement of contractors to carry out the works under the HNUP.  Economic analysis, socio demographic surveys and environment and social impact analyses including a disaster risk management plan will also be conducted for the Programme. Proposals for the institutional aspects of both the Ministry and the National Housing Cooperation will be done.  Among them, preparation of terms of reference for a fixed assets management information system for the Ministry, a procurement system for the NHC and an institutional strategic plan for the Housing Planning Unit within the Ministry. Other activities will include the collection of baseline data for the Logical Framework and the production of a communications and social marketing strategy for the Neighborhood Upgrading and Affordable Housing Component of the Loan.

  - Loan approval date has been adjusted to March 2007 with the Analysis Mission scheduled to take place in January 2007.

- C.	Procurement and contracting of consulting services

  - Procurement of the consulting services to be financed from resources of this Facility will be carried out in accordance with the Bank’s standard procedures.  Specific procurement events will be the responsibility of the PCMU.  However, given the lengthy procurement and contracting processes within the public sector, due mostly to an overly centralized and bureaucratic system, the Beneficiary has requested the Bank to act on its behalf and engage the services of the consultants, especially those to be hired through international competitive bidding.  In Section 4.28 of Annex B, the Operating Regulations of the Line of Credit, 19/LC-BA, there is provision for the Bank, under exceptional cases, to engage consulting services on behalf of the Executing Agency.

  - Taking into consideration the experiences in contracting under existing Loan operations, the Project Team recommends approval of this request in accordance with these provisions. Procurement under this individual operation is considered an exceptional case because of the wide disparity between the inordinate length of time it normally takes the Beneficiary to procure services and the timelines established for Project preparation, approval and start up. If the Bank does not accede to this request, whilst the investment Loan will be approved, there is the risk that the current timelines for start up and implementation will be derailed leading to further delays in overall execution. Also, the Bank’s assistance in contracting will help preserve the swift and timely nature and intent of the PROPEF.

  - Under this arrangement, the PCMU, in close collaboration with the Bank, will complete terms of reference, prepare tender notices, short list and select consultants, and conduct all negotiations. The Bank will review and grant its non-objection in the usual manner and upon the satisfactory assessment of the procurement processes ex ante and sign the contracts with the consultants on behalf of the Executing Agency.

- Action plan and terms of reference

  - A number of consultants will be hired to carry out the activities identified in the scope of services.  Among them will be the consulting firm to prepare technical specifications and final designs for engineering works for the four selected sites.  This team of consultants will include an architect, urban planner, quantity surveyor, civil engineer, social worker and an environmental expert.  To provide these services a consulting firm will be hired through international competitive bidding for a six-month period.  A local consulting firm will be hired separately for two months to prepare, test and conduct the surveys for updating the socio demographic information and formulating the baseline for the four pilot sites.  Both local and international individual consultants will be hired on short-term basis to assist in the other aspects of the preparatory work. Annex II lists the proposed consultants.

  - Draft Terms of Reference have already been prepared for these consultants and are attached as Annex III to this Memorandum of Assistance. During implementation, the PCMU will finalize these Terms of Reference and before their use, present them for the Bank’s non-objection.

- Cost of the project

  - The total cost of this individual operation is estimated to be the equivalent of US$856,800 in accordance with the following investment categories and sources of financing:

| Cost and Financing Table (US$) |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | # BANK | # GOBA | TOTAL | % |
| 1.0 Project Administration | # 0 | # 100,000 | 100,000 | 12.0 |
| - Project Coordination and Monitoring Unit - Technical Assistance |  | 80,000 20,000 | 80,000 20,000 |  |
| 2.0 Direct Costs | 688,000 | 0 | 688,000 | 80.0 |
| 2.1 Consulting Firms 2.2 Individual Consultants | 620,000 68,000 | 0 0 | 620,000 68,000 |  |
| 3.0 Financial Costs | 0 | 54,800 | 54,800 | 6.4 |
| 3.1 Interest 3.2 Commitment Fee 3.3 Audit |  | 48,160 6,640 | 48,160 6.640 |  |
| 4.0 Contingency | 0 | 14,000 | 14,000 | 1.6 |
| TOTAL | 688,000 | 168,800 | 856,800 | 100.00 |
| Percentage | 80.00 | 20.00 | 100 | 100.00 |

  - Credit fees for this individual operation will be the same as for regular Bank loans. Interest will accrue from the date of each disbursement.  All finance charges will be repaid out of the proceeds of the first disbursement of the Bank’s investment Loan for Housing and Neighbourhood Upgrading Programme and at the time of the disbursement.

  - Disbursement of the resources for this PROPEF individual operation will be done utilizing the same procedures as for all Bank loan operations. The first disbursement will require certification by the Bank’s Representative (with the concurrence of the Legal Department for any legal opinion that is required as a condition precedent), that the conditions specified in the Letter of Agreement have been fulfilled and the operations eligible for disbursement. The Executing Agency will prepare and present the disbursement requests in accordance with the guidelines established in the Operating Regulations, Annex B of the Line of Credit 19/LC-BA. Where the Bank, pursuant to the provisions of the PROPEF, has engaged a consultant, disbursements will be made according to the contract without the need for the executing agency to submit a disbursement request.

  - The period of execution will be eighteen (18) months from the effective date of the Letter of Agreement between the Bank and the Borrower and the period for disbursement of the financing shall be twenty-four (24) months. The Executing Agency shall present the last disbursement request one month prior to the established deadline.

- Environmental and Social Review

- A.	PTI/SEQ classification

  - Since it is part of the overall Housing and Neighbourhood Upgrading Programme, this PROPEF individual operation qualifies as a social equity-enhancing project, as described in the indicative targets mandated by the Bank's Eighth Replenishment (document AB-1704). Furthermore, this individual operation, like the proposed Loan, qualifies as poverty targeted investment (PTI) as most of the activities are under the neighborhood improvement component, which is geographically targeted to the poor.

- B.	Environmental and social impacts

  - The Housing and Neighbourhood upgrading Programme is expected to have a positive impact in the environment mainly because of the provision of basic services to the squatter settlements that are now underserved. Many of the home improvement loans will also be used for the provision of basic services, reduce overcrowding or the construction of toilet facilities. Improvement in the two special neighborhood cases will also reduce fire hazard and overcrowding.

  - Several laws and regulations exist within the country to protect the environment. Among them are the National and Bridgetown Development Plans, the Coastal Zone Management Plan (produced with Bank support) and the regulations of the water and sewerage agency. This PROPEF individual operation has provision for the preparation of an environmental and social impact analysis.

  - Key issues to be analyzed are: capacity of executing agencies to comply with existing regulations, criteria for site selection, health and safety construction regulations, waste treatment capacity, potential resettlement, disaster risk management and social exclusion. The analysis will propose a strategy to address those issues and recommendations as well as the preparation of a disaster risk management plan to ensure compliance with all those laws and regulations. The strategy will give special consideration to ensure coordination with all agencies responsible for the provision of urban basic services, land use planning and effective community participation.