LEGIII/BA-530458-05

ANNEX

THE PROJECT

Strengthening of Business Facilitation Services

I.	Objective

1.01	The general objective of the Project is to strengthen the capacity of Barbados’s Corporate Affairs and Intellectual Property Office (CAIPO) to offer efficient and timely business facilitation services to companies operating, or seeking to operate, in or out of Barbados. The specific objectives are to help CAIPO (i) modernize its information and communication technologies; (ii) increase the efficiency of its internal work processes and staff; (iii) enhance its capacity to monitor the nature of services offered by companies doing business in and out of Barbados; (iv) expand its revenue streams through the introduction of new internet services; and (v) enable it to offer greater flexibility in services supplied.

1.02	The expected outcomes, assuming no change in external conditions, are (i) a decrease in the current turnaround time for company incorporation from 7 to 1-3 days; (ii) a 30 percent increase in revenue as a result of the introduction of on-line services within one year of Project completion; and (iii) a 50 percent increase in registrations within one year of Project completion.

II.	Description

- 2.01	To achieve the objectives outlined above, the Project will comprise the implementation of: (i) an intranet for use by CAIPO officials, and (ii) the provision of on-line services by CAIPO.

- Intranet

- 2.02	Implementation of an intranet and attendant staff training will be carried out over a two-month period and will entail the following sub-components:

    - Equipment: Purchase of a server with 2 Central Processing Units;

    - Software: Purchase of the software needed to operate the intranet;

    - Implementation and Customization of Software: The Project will finance the contracting of one consultant (systems administrator) for five days who will have responsibility for preparing the servers and workstations for installation of the application, for establishing network file systems and ensuring that files placed on the system are routinely backed up. The consultant systems administrator would also create the user accounts with appropriate privileges for the developers.

    - Creation of Intranet Content and Building Links to Existing Data: This sub-component foresees the hiring of (i) one consultant database administrator for five days who will plan, design and develop new databases or make necessary changes to an existing database. This person will also ensure that the databases are indexed appropriately to facilitate searches; and (ii) one consultant webmaster/developer for 15 days who will develop standards for deployment of content on the intranet.

    - Training (Train the trainer process): one consultant trainer for 10 days who would train a core team of three persons on use of the intranet. This core team will then train the entire CAIPO office over the course of 9-12 days.

- Provision of On-line services

- 2.03	Provision of on-line services by CAIPO will be implemented over a period of two months and will entail the following sub-components to be financed by the Project:

    - Creation of requirements documentation. One consultant will be hired for five days to design and define the requirements necessary to provide the on-line services in collaboration with the Registrar and the Registrar’s core team’s recommendations in relation to the content, definition of internet options and documents to be posted.

    - Implementation and Customization of Software. Under this sub-component, the Project will finance: (i) one consultant (systems administrator) for five days to prepare the servers and workstations for installation of the application, establish network file systems and ensure that files placed on the system are routinely backed up.  This person would also create the user accounts with appropriate privileges for the developers; (ii) one consultant for 20 days to develop the server pages and related tasks; create content (for testing purposes); and be responsible for the creation of community and business rules, enhancement of software data scheme files and development of code and/or connection to third party business systems; and (iii) one consultant database administrator for five days who will plan, design and develop new databases or make any major changes necessary to existing database. This person will also ensure that the databases are indexed appropriately to facilitate searches via the internet, create links to legacy databases and create other links to other web sites where necessary.

    - Training (Train the trainer process). One consultant trainer will be hired for 5 days to train a core team of three persons on use of the software. This core team will then train all CAIPO staff over the course of 9-12 days.

- 2.04	The Ministry of Industry and International Business, through CAIPO, will provide a counterpart contribution in-kind, from existing resources, as per the following:

    - Intranet: one staff member for 5 days to assist with the implementation and customization of software; three staff members for 20 days to assist with the creation of content on the intranet and build links to existing data; three staff members for 10 days to be trained as trainers for the rest of staff on the intranet system; and twenty staff members to be trained over the course of 9 days on the content and use of the intranet system.

    - Provision of On-line Services: five staff members for 3 days to plan and determine what internet options are needed and what documents to post on-line; one staff member for 5 days to assist with preparing requirements documentation; one staff member for 20 days and two other staff members for 15 days to assist with the implementation and customization of software; three staff members for 10 days to be trained as trainers for other staff on the system and the on-line services to be provided; and 20 staff members to be trained for 9 days on the content and use of the on-line system.

III.	Total Cost of the Project

3.01	The estimated cost of the Project is the equivalent of CAD$195,000, in accordance with the following Budget:

Budget

(in CAD$)

| Activity | Bank | Local Counterpart* | Total |
| --- | --- | --- | --- |
| ## 1. Intranet Equipment (Server) Software Implementation/customization of software 1 systems administrator (5 days x $1270) 1 staff (IT person) x 5 days Internet Content & Links to Existing Data 1 database administrator (5 days x $1270) 1 webmaster/developer (15 days x $1270) 1 staff (IT person) x 20 days 2 staff x 20 days ### Train the Trainer Process 1 consultant trainer (10 days x $1270) 1 staff (IT person) x 10 days 2 staff x 10 days #### Staff Training 20 staff x 9 days 3 in-house trainers x 9 days Sub-total | 6,350 31,500 6,350 0 6,350 19,050 0 0 12,700 0 0 0 0 82,300 | 0 0 0 360 0 0 1,440 2,880 0 720 1,440 12,960 1,944 21,744 | 6,350 31,500 6,350 360 6,350 19,050 1,440 2,880 12,700 720 1,440 12,960 1,944 104,044 |
| ## 2. Provision Of Online Services ### Definition of Requirements 1 consultant (5 days x $1270) Registrar and 4 staff x 3 days 1 staff (IT person) x 5 days ### Implementation/customization of software 1 systems administrator (5 days x $1270) 1 consultant developer (20 days x $1270) 1 database administrator (5 days x $1270) 1 staff (IT person) x 20 days 2 staff x 15 days ### Train the Trainer Process 1 consultant trainer (5 days x $1270) 1 staff (IT person) x 10 days 2 staff x 10 days ### Staff Training 20 staff x 9 days 3 in-house trainers x 11 days Sub-total | 6,350 0 0 6,350 25,400 6,350 0 0 6,350 0 0 0 0 50,800 | 0 1,080 360 0 0 0 1,440 2,160 0 720 1,440 12,960 2,376 22,536 | 6,350 1,080 360 6,350 25,400 6,350 1,440 2,160 6,350 720 1,440 12,960 2,376 73,336 |
| 3. Program Coordinator (8 days x $1270) | 10,160 | 0 | 10,160 |
| ## 4. Audit | 5,000 | 0 | 5,000 |
| ## 5. Contingencies | 1,740 | 720 | 2,460 |
| ##### TOTAL | 150,000 | 45,000 | 195,000 |

IV.	Execution

- 4.01	The Ministry of Industry and International Business, through its Corporate Affairs and Intellectual Property Office (CAIPO), will serve as executing agency for the Project. In this capacity, the Ministry will appoint a contact person responsible for overseeing the implementation of the Project and ensuring the fulfillment of the Ministry’s responsibilities in this regard.

- 4.02	The Executing Agency will select the consultants in consultation with the Bank, and hire the consultants and purchase the equipment according to the applicable Bank rules and procedures.

- 4.03	To assist with Project implementation, the Ministry will hire a consultant for 8 days in the early phases of Project implementation to serve as a program coordinator. The consultant will be hired by the Ministry in consultation with the IDB according to applicable Bank rules and procedures.

- 4.04	The consultants will work with the counterpart staff in order to effect a transfer of technology and knowledge and allow the staff to be better able to undertake the relevant functions after Project completion.

- 4.05	The Executing Agency, through CAIPO, will submit a written report to the IDB Representative in Barbados within 3 months of the date of signature on the status of the Project, the degree of completion of the aforementioned activities and the progress made in fulfilling the stated objectives. The report will include a disaggregated accounting of expenses. The Executing Agency will submit a subsequent report to the IDB Representative within each 3-month period thereafter. The Ministry will submit a final report, in accordance with the general Bank guidelines regarding the structure and content of those reports, to the IDB Representative at the end of the disbursement period. In this report, the Ministry will explain how it is monitoring the effectiveness of the new system and what value-added it may have already contributed.

- 4.06	Upon completion of the Project, an accounting firm will be hired to undertake an audit of the project, as per Bank rules on Technical Cooperation projects. The accounting firm that undertakes the audit will be selected according to Bank procedures.

- 4.07	The Bank’s Country Office in Barbados (COF/CBA) will be responsible for program administration and general supervision. COF/CBA will consult closely with the Bank’s Integration, Trade and Hemispheric Issues Division (INT/ITD) on all technical matters, including the hiring of consultants for the project, and will forward all project reports to INT/ITD.