# Modernization of Agricultural Public Services Program– (SU-L1033)

# Results Matrix

| Project Goal | The general objective of the PBP will be to contribute to the growth of the agricultural sector through the increase of agricultural productivity. The specific objectives will be to develop institutional and policy reforms to enhance farmers’ access to improved public agricultural services. |
| --- | --- |
| Expected Impacts Indicators; Base Line; Total End of Program; Comments and Verification. Sector Annual Growth; 1990-2011: 1.6% annual growth; 2012-2015: > 1.6% annual growth; Source: FAOSTAT 2011 Means of verification: Compare evolution of performance over time.. |
| Aggregate Intermediate Result; Base Line 2012; Year 2013; Year 2014; End of the Program 2015; Comments/Verification. Indicator: Increase in Total Factor Productivity of Agricultural Sector Number of farmers receiving services.; 2001-2007: 1% annual growth 2018; 2060; 2800; 2012-2015: > 1% annual growth 5500; Source: Ludeña, Carlos. Agricultural Productivity Growth, Efficiency Change and Technical Progress on Latin America and the Caribbean, IDB Working Paper Series, No 186, May 2010 Means of verification: Compare evolution of performance over time. Services include extension, veterinary, irrigation training and rehabilitated irrigation polders. Department of Agricultural Statistics – LVV. However, as a results of the reforms and given, the public nature of the services, it is expected that all producer benefit. Baseline: 10,188 farmers (2009). Source: Department of Agricultural Statistics.. Aggregate Intermediate Result; Base Line 2012; Year 2013; Year 2014; End of the Program 2015; Comments/Verification. Ratio of current Catch per unit of effort CPUE (kg/das) on historical CPUE max for the following specific species - Seabob (X. kroyeri) kg/das - Penaeid shrimp species (ton/trawler/year) - Groundfish species caught (multi-species CPUE) kg/das - Lane snapper (Lutjanus synagris) caught by bottom trawlers kg/das - Kandatriki (Cynoscion virescens) caught by bottom trawlers6) Black snapper (Lutjanus griseus) kg/das - Red snapper (Lutjanus purpureus) caucht by the Venezuelan fleet. kg/das; CPUEt 1.84 22 1750 103 350 150; CPUEt ≥ 1.60 ≥ 22 ≥ 1750 ≥ 150 ≈ (300,350] ≥ 175; CPUEt ≥ 1.60 ≥ 22 ≥ 1750 ≥ 150 ≈ (300,350] ≥ 175; CPUEt ≥ 1.60 ≥ 22 ≥ 1750 ≥ 150 ≈ (300,350] ≥ 175; LVV Fisheries information system. Component 2 Modernization of the Agricultural Statistics; Base Line 2012; Year 2013; Year 2014; End of the Program 2015; Comments/Verification. Result 1: To improve the performance of the data collection and analysis Indicator: Number of publications from data generated using probabilistic method.; 0; 1; 2; 3; Means of Verification : LVV Agricultural Statistics. Will only take into account LVV’s publications.. Outputs: 2.1 Agricultural Census 2008-09 published 2.2 Agricultural Data Collection Plan approved by LVV 2.3 Manual of Operation of Agricultural Information System approved by LVV 2.4 Agricultural Information System set up and functioning; 0 0 0 0; 1; 1 1; 1; Reports of Monitoring System Functioning means that the AIS is gathering, processing and analyzing information.. Component 3: Modernization of the Agricultural Health and Food Safety Services; Base Line 2012; Year 2013; Year 2014; End of the Program 2015; Comments/Verification. Result 1: To improve the performance of the agricultural health and food safety services Indicador 1: Number of Alert Notification for Food (fish, fruits and vegetables) generated by the EU. Indicador 2: Performance Index of the plant system as measured by IICA-PVS tool Indicador 3: Performance Index of the animal system as measured by OIE-PVS methodology Indicador 4: Number of major animal diseases for which Suriname obtains OIE free status certification Indicador 5: Number of major plant pests for which Suriname obtains IPPC-ISPM free status certification.; 15 (2008-11) 30% 42% 0 0; 15; 10; 7 45% 60% 1 1; Means of Verification : E.U.'s Rapid Alert System for Food and Feed (RASFF). IICA- National Plant Protection Organizations Performance, Vision, Strategy tool. OIE-Performance Veterinary Service tool OIE IPPC-ISPM. Outputs 3.1 Inter-Ministerial Working Group for Food Safety (IMWGFS) established by respectives Ministeries 3.2 Food Safety Strategy approved by IMWGFS 3.3 Food Safety Regulations for food production, post-harvesting and processing plans approved by IMWGFS 3.4 Food Safety protocols operational 3.5 Regulation of Animal Health Acts approved by LVV 3.6 Animal Health Human Resources and Infrastructure and Equipment Plan being implemented by LVV 3.7 National Animal Disease Surveillance and Monitoring Plan being implemented by LVV 3.8 Protocols and rules procedures for animal border control and quarantine being implemented by LVV 3.9 Strategy for declaring the country free of major animal diseases approved by LVV 3.10 Regulation of Plant Health Acts approved by LVV 3.11 Plant Health Human Resources and Infrastructure and Equipment Plan being implemented by LVV 3.12 National Plant Disease Surveillance and Monitoring Plan being implemented by LVV 3.13 Protocols and rules procedures for plant border control and quarantine being implemented by LVV 3.14 Strategy for determining the country status of major plant pests approved by LVV; 0 0 0 0 0 0 0 0 0 0 0 0 0 0; 1 1 1 1; 1 1 1 1 1 1 1 1 1 1; Reports of Monitoring System Operational means that the Protocols were approved and the Ministers members of the IMWGFS are ready to use them. Being implemented means that LVV is hiring and/or contracting technical experts and acquiring infrastructure and/or equipment according to plan. Being implemented means that LVV is conducting surveillance surveys according to plan. Being implemented means that LVV is training and allocating inspectors at the border controls according to plan. Component 4: Agricultural Innovation; Base Line 2012; Year 2013; Year 2014; End of the Program 2015; Comments/Verification. Result 1: To improve the performance of the agricultural innovation services. Indicator 1: % Innovation projects that are being implemented according to scheduled time Indicator 2: % of LVV’s recurrent resources allocated agricultural innovation projects. Result 2: To increase Capacity in Agricultural Research Indicator 1: Number of professionals operating in agricultural innovation projects - New - Trained Result 3: Increase in the collaborations with national and international institutions Indicator 1: number of collaborations with external partners national/international research institutions formulated; 0 0 0 0 2; 0 0 0 0 2; 0 0% 0 15 2; 80% 7% 4 30 3; Means of Verification : LVV Report of Agricultural Innovation Projects Monitoring and Evaluation System. Innovation projects being implemented means conducting research tests and extension activities. LVV Report of Agricultural Innovation Projects Monitoring and Evaluation System LVV Report of Agricultural Innovation Projects Monitoring and Evaluation System LVV Report of Agricultural Innovation Projects Monitoring and Evaluation System. Outputs 4.1 Agricultural Innovation Strategy published by LVV 4.2 The National Agricultural Innovation Board installed by LVV 4.3 Human Resource Plan for agricultural innovation approved by LVV 4.4 A project management system for agricultural innovation activities developed and being implemented by LVV 4.5 Strategic guidelines for linkages to partners outside of the country approved by LVV; 0 0 0 0 0; 1; 1 1 1 1; 1; Monitoring System Being implemented means training staff, establishing a project management unit.. Component 5: Modernization of the Drainage and Irrigation Services; Base Line 2012; Year 2013; Year 2014; End of the Program 2015; Comments/Verification. Outcome 1: To improve the effectiveness and sustainability of D&I systems Indicator1: Number of hectares irrigated with improved water applications and drainage; 2972; 4007; 4007; 6007; Means of Verification : LVV report on Irrigation and Drainage rehabilitation projects. Improved means that the drainage and irrigation systems have been rehabilitated.. Intermediate Outcome: To improve the governance and institutions of the D&I systems Indicator 1: Number of WBs with approved and implemented maintenance plans; 0; 0; 0; 6; LVV report on Irrigation and Drainage rehabilitation projects.. Outputs 5.1 Inter-Ministerial Irrigation and Drainage Coordination Working Group ( IMIDCWG) established by respective Ministries 5.2 Suriname Irrigation and Drainage Vision formulated by IMIDCWG 5.3 Manual of Operations to establish Water Boards endorsed by IMIDCWG 5.4 Six by-laws of Water Boards approved by RO 5.5 Operation and Maintenance work-plans of six Water Boards endorsed by RO and LVV 5.6 Suriname Irrigation and Drainage Vision approved by Council of Ministers 5.7 Implementation of the operation and maintenance plans certified by LVV and RO; 0 0 0 0 0 0 0; 1; 1 1 1 1; 1 1; Reports of Monitoring System. Component 6: Policy Support for Sustainable Fisheries Management; Base Line 2012; Year 2013; Year 2014; End of the Program 2015; Comments/Verification. Result: To improve the LVV’s capacity for sustainable fisheries management Indicator 1: Number of fishing licenses issued by LVV Marine Inland; Coastal 512 Inland 400; Coastal 512 Inland 400; <10%; Success: declining number of licenses LVV Fisheries information system. Outputs 6.1 Fisheries Monitoring, Control and Survelliance system (FMS) approved by Council of Ministers 6.2 Fisheries Management Plan (FMP) published by LVV 6.3 Ministerial Ordinance prepared by LVV Department of Fisheries according to FMP 6.4 Harvest Control Rules for shrimp and ground fisheries developed LVV Department of Fisheries; 0 0 0 0; 1 1; 1; 1; Reports of Monitoring System. |

Baseline : 1104 extension service, 389 veterinary services, 525 irrigation. 2013:add 42 irrigation. 2014 add 740 irrigation training. 2015 add 2000 extension and veterinary services and 700 irrigation. Farmers are receiving only one service. In coastal area 17% women.  Source: Department of Agricultural Statistics.

The IICA/PVS tool is a standardized methodology, internationally recognized, performed by independent experts. The proxy indicator (score from 0 to 100%) synthetizes 33 criteria, including human resources capabilities, financial sustainability, technical capacities (diagnosis, risk analysis, quarantine, epidemio-vigilance, pests and diseases control), collaboration with the private sector, access to markets, and conformity with international legislation and commitments.

The OIE/PVS tool is a standardized methodology, internationally recognized, performed by independent experts. The proxy indicator  synthetizes 46 criteria, including human resources capabilities, financial sustainability, technical capacities (diagnosis, risk analysis, quarantine, epidemio-vigilance, pests and diseases control, food safety, traceability), collaboration with the private sector, access to markets, and conformity with international legislation and commitments.