MIF PROJECT PERFORMANCE COMPLETION REPORT (MPCR)

“STRENGTHENING SYSTEMS FOR PROPERTY RIGHTS”

[TC ATN/MT – 6671-GY]

August 2006

| I. Basic Project Data |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Country: GUYANA Project Title: STRENGTHENING SYSTEM FOR PROPERTY RIGHTS TC Number (s): TC 9507155 MIF/AT: 289 ATN Number (s): ATN/MT-6671-GY Executing Agency (ies): MINISTRY OF LEGAL AFFAIRS CO Specialist responsible: JAMES CAMPBELL HQ Specialist responsible: Date of Report: 17 JULY 2006 Date of approval by Representative: Date of CRG: Date of final approval: |  |  |  |  |  |  |  |  |  |  | Date of Donor Approval (Month/day/year): 09/22/1999 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Date of Contract Signature: 24 January 2000 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Date of Contract Validity: 24 January 2000 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Date of First Eligibility for First Disbursement: 13 September 2000 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Date of Total Eligibility for First Disbursement: 13 September 2000 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Date of First Disbursement: 21 November 2000 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Original Date for Final Disbursement: 24 July 2002 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Actual Date of Final Disbursement: 24 May 2006 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Original Date for Final Execution: 24 January 2002 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Actual Date of Final Execution: 24 January 2004 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Extensions granted for final execution (months): 24 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Extensions granted for final disbursement (months): 46 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Extension granted as percentage of original execution period: _100__ % |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Extension granted as percentage of original disbursement period: __153_ % |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| II. Project Financing Data. |  |
| 1. MIF Financing: - Original amount: $940,000.00 - Actual amount: $785,698.88 - Total amount cancelled: $154,301.12 |  |  |  |  | 2. Counterpart contribution from EA: - Original amount: $415,000.00 - Actual amount: $$1,880,001.00 3. Counterpart contribution from other sources: - Original amount: NIL - Actual amount: NIL 4. Total Counterpart contribution (2 + 3): - Original amount: $415,000.00 - Actual amount: $$1,880,001.00 |  |  |  |  |  |  |  | - Project Total Cost (1 + 4): - Original amount: $1,355,000.00 - Actual amount: $1,020,944.25 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Actual Disbursements of MIF funds: - Amount: $785,698.88 - Percent of original funds (%): 83.5 |  |  |  |  |  |  |  | Actual Disbursements of Counterpart funds: - Amount: $$785,782.38 - Percent of original funds (%): 56.6 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| III. Project Performance Data. |  |
| # No Yes Were objectives and indicators been agreed to with beneficiary/executing agencies? [ ] [ ] Were original development objective(s) and/or indicators been officially reformulated? [ ] [ ] Were components and/or indicators been officially restructured? [ ] [ ] Were indicators reviewed during execution? [ ] [ ] Did the beneficiary/executing agency maintain performance indicator data? [ ] [ ] Was there a defined data gathering system in place with baseline information? [ ] [] Has the beneficiary/executing agency rated the performance of the project? [] [ ] If yes, what were the IP and DO classifications IP [ ] DO […] Did the beneficiary/executing agency ratings differ from the Bank’s? [ ] [ ] If yes, provide a brief explanation of the difference: What is the Executing Agency rating of Bank’s Performance VS [ ] S [ ] U [ ] VU [ ] What was the date of final evaluation: _ MARCH 2006_ |  |  |  |  |  |  | Historical MPPMR Ratings: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | June | Dec. | June |  | Dec. | June |  | Dec. |  | June |  | Dec. |  | Final |  |  |  |
|  |  |  |  |  |  |  | (year) |  |  | 2002 | 2002 | 2003 |  | 2003 | 2004 |  | 2004 |  | 2005 |  | 2005 |  |  | 2006 |  |  |
|  |  |  |  |  |  |  | IP |  |  | [ S ] | [S ] | [U ] |  | [U ] | [ U ] |  | [ U ] |  | [U] |  | [U] |  | [U] |  |  |  |
|  |  |  |  |  |  |  | DO |  |  | [L ] | [H ] | [H ] |  | [H ] | [H ] |  | [ H ] |  | [L ] |  | [L ] |  | [L ] |  |  |  |
|  |  |  |  |  |  |  | AS |  |  | [LP] | [P] | [ P ] |  | [P ] | [P ] |  | [LP] |  | [LP] |  | [LP] |  | [LP] |  |  |  |
|  |  |  |  |  |  |  | Summarize project’s major outcomes and likely impact, indicating if it met original expectations and if sustainability after completion is probable. The project did not achieve its major expected outcomes of improving the legal, institutional and organizational framework as measured by (i) a reduction in the cost and time required for registering titles and for creating security interests in movable and immovable property; and (ii) enhancing increased legal and physical security of titles. Original expectations were not met even though project execution languished for 46 months more than the scheduled 24 months. The prime mover of the project was Component II that sought to reform and modernize all the internal systems, including records management, computerization, work-flow procedures, human resource management and compensation and physical layout. To the extent that most of these interventions remain unimplemented in full in most instances, the original expectations could not be realized. The one signal success is the improvement of the physical layout of the Georgetown Registry. This however did not extend to the sub-Registry in New Amsterdam. Very importantly, the legal framework has not been fully created to set up a semi-autonomous agency with a scale of fees that reflect a significant improvement in performance that users are prepared to pay. For the changes to be sustained, it would require a core of qualified, trained, experienced, committed and highly motivated staff. This cannot be achieved unless the Human Resource recommendations, including a new compensation package are implemented. Enough training for staff was not done during implementation Briefly comment if (external) Assumptions were favorable or unfavorable for project outcomes and explain the reasons why. Although the GoG authorities did embark on an aggressive land titling and regularization process, this did not significantly impact on the achievement of the Development Objectives as the GoG took a decision in 2002 to separate the Land Registry from the Deeds Registry and make it into a semi-autonomous body. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| # IV. Project Results Data |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| # IV. A Project Outcomes (Purpose) And Impact |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Outcomes (DO or Purpose in the Logical Framework) |  |  |  |  |  | # Key Delivery Performance Indicators of Outcomes: |  |  |  |  |  |  |  |  |  | # Rating of Outcomes (DO) |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | VE |  | E |  | ME |  |  | I |  |
| Improve the legal, institutional and organizational framework for secured transaction in movable and immovable property. |  |  |  |  |  | 1. Reduction in the costs by at least 15% and in time by at least 25% for registering titles and for creating security interests in movable and immovable property by end of project |  |  |  |  |  |  |  |  |  | 1 |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | 2 |  |  |  |  |  |  |  |  |  | 2 |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | 3 |  |  |  |  |  |  |  |  |  | 3 |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | Etc. |  |  |  |  |  |  |  |  |  | etc. |  |  |  |  |  |  |  |  |  |  |
| Summary Effectiveness Ratings in terms of project outcomes (DO): VE [ ], E [ ], ME [], I [ ] |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Criteria for classification of Outcomes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Very Effective (VE) |  |  | The project: a) achieved all the expected outcomes (indicators); b) is likely to sustain the flow of benefits initiated by the project for the target population; c) has very high probability of achieving future outcomes and impacts. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Effective (E) |  |  | The project: a) achieved most of the expected outcomes (indicators); b) is likely to sustain most of the benefits initiated by the project for the target population; c) has high probability of achieving future outcomes and impacts. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Marginally Effective (ME) |  |  | The project: a) has achieved some of the expected outcomes (indicators); b) is not likely to sustain the flow of benefits initiated by the project for the target population; c) has low probability of achieving future project outcomes and impacts. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Ineffective (I) |  |  | The project: a) did not achieve the expected outcomes (indicators); b) is not sustainable, c) is unlikely to achieve future outcomes and impacts. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Description of project results in relation with its development objectives (DO or purpose in the project Logical Framework): - Based on DO classification above, describe the achieved outcomes (effects) of the project and compare with the expected outcomes in terms of its specific development objective. Provide a brief explanation for any major differences. The overall project implementation received a DO Classification of “ME” largely because most of the recommendations in the various Consultants’ report are yet to be fully operationalised while an important aspect such as computerization was not completed at the end of the project. The Government has committed to providing the additional computers and related equipment during the current fiscal year. - Comment on the likelihood of achieving the desirable impact (Goal in the Logical Framework) in the short and medium term (next 2/3 years) upon project’s beneficiaries, taking into consideration the expected sustainability of actions initiated by the project. Compare with the expected goals (as defined in the Logical Framework) and provide a brief explanation of differences. In the short to medium term it seems very unlikely that the project goal of “increasing financial intermediation” can be achieved. A concerted effort will have to be made to enact the draft laws and to complete the computerization of current and historical records. The issues of autonomy for the Deeds Registry and staff remuneration will also have to be addressed frontally. c) Indicate other outcomes not originally foreseen. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| # IV. B Project Outputs (Products). |
| Outputs (Components in the Logical Framework) 1. Improvement of the Legal Framework. |  |  |  |  |  | # Key Delivery Performance Indicators of Outputs: |  |  |  |  |  |  |  |  |  | # Rating of Outputs (IP) |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | VS |  | S |  | U |  |  | VU |  |
|  |  |  |  |  |  | 1.1 Deeds Registry Act and its Rules and Regulations amended by end of project. |  |  |  |  |  |  |  |  |  | 1.1 |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | - Movable Property Security Act approved in Parliament and assented to by end of project. |  |  |  |  |  |  |  |  |  | 1.2 |  |  |  |  |  |  |  |  |  |  |
| 2. Strengthening of the Deeds Registry |  |  |  |  |  | 2.1 Fully rehabilitated and computerized Deeds Registry with trained personnel being used by the general public, commercial lenders, lawyers and others by end of project. |  |  |  |  |  |  |  |  |  | 2.1 |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | 2.2 Reduction in the costs and time for registering titles and for creating security interests in movable and immovable property by end of project. |  |  |  |  |  |  |  |  |  | 2.2 |  |  |  |  |  |  |  |  |  |  |
| 3. Project Management |  |  |  |  |  | 3.1 Baseline survey of Deeds Registry users carried out by December 31, 2001. |  |  |  |  |  |  |  |  |  | 3.1 |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | 3.2 End of project survey carried out by end of project. |  |  |  |  |  |  |  |  |  | 3.2 |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | 3.3 Deeds Registry computer systems meet technical and security standards by end of project. |  |  |  |  |  |  |  |  |  | 3.3 |  |  |  |  |  |  |  |  |  |  |
| Summary Effectiveness Ratings in terms of project Outputs (IP): VS [ ], S [ ], U [ ], VU [ ] |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Criteria for classification of Outputs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Very Satisfactory (VS) |  | The project achieved all or exceeded the expected outputs in accordance with their respective indicators within the expected quality, reasonable timeframe, and reasonable costs. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Satisfactory (S) |  | The project achieved most (say, > 65%, < 100%) of the expected outputs in accordance with their respective indicators within the expected quality, reasonable timeframe, and reasonable costs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Unsatisfactory (U) |  | The project achieved some (say, > 50%, < 65%)of the expected outputs in accordance with their respective indicators within the expected quality, reasonable timeframe, and reasonable costs. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Very Unsatisfactory (VU) |  | The project achieve only a limited number of the expected outputs (say, <50%) in accordance with their respective indicators within the expected quality, reasonable timeframe, and reasonable costs. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Based on IP classification above, describe the achievement of each outputs (products) of the project and compare them with the expected outputs in terms of its implementation progress in the Logical Framework. Provide a brief explanation for any major differences. This description should be specific and referred to each indicator included in the original or modified Logical Framework. Indicate other outputs not originally foreseen. The following were delivered in Component 1 – - An initial report with a revised work-plan dated 15th August 2001. This report with Action Plan - The conduct of consultations and a report dated the 1st December 2001. - The preparation of a Training Plan dated 26th April 2002. - The preparation of a training Report dated 30th May 2002. - A final report with a draft Movable Property Security Act that took into account all other associated Acts The preparation of a stakeholder response report dated the 19th June 2002. There is no indication that this was unacceptable to the Client. However this Act has not been operationalised through an Act of Parliament and the clients. The following were delivered under Component 2 – - An initial report with proposed re-engineered processes submitted on August 5th 2002. However, payment and contractual difficulties with the Consultant led to this firm’s contract ending prematurely. The decision was taken to hire an individual consultant to deliver the modernisation and computerisation part of the original contract. The scope of work was modified because bureaucratic delays in the procurement of computers and other hardware resulted in a significantly lesser amount of equipment being procured. Consequently, some of the proposed processes were not introduced and the IT applications are based on automating the current manual processes ignoring the reengineered processes. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - A report with a new Chart of Accounts for an autonomous agency was submitted on October 14th 2002. However, this cannot be implemented until the agency is made autonomous or semi-autonomous. The time gap between the implementation of this and the time they were submitted may render them virtually useless unless the financial and economic environments remain unchanged. - The Deeds Registry building in Georgetown was refurbished, repainted, air-conditioned to meet many of the design specifications. The Vaults are in an unsatisfactory state and the controls envisaged to add greater effectiveness, preservation, and security to the records in the Vaults are ignored completely. - The Consultant engaged as Architect was given limited Terms of Reference so was not involved in all of the associated activities to protect the integrity of this aspect so valuable time was lost due to the inexperience of the in-house staff. Further protracted difficulties with the beneficiary agency’s main contact led to the Contract being suspended and the unavailability of the Consultant to supervise important aspects of the rehabilitation work leading to the poor performance of the Contractor on this contract. - An Archivist was contracted and did some excellent work with the records but was unable to take this to a final conclusion due to time delays and payment difficulties similar to those that affected all the Consultants on this project. For Component 3, the Baseline study was done and Final Evaluation were carried out. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| # V. External Factors That Affected Project Performance (Assumptions). |
| Project Outcomes Describe the major external factors that have either enhanced or negatively affected the achievement of project outcomes. Indicate if these factors were originally contemplated as Assumptions in the Logical Framework. The major external factors that negatively affected the achievements of this project include: 1. Failure of the GOG to implement the requisite legislation 2. Failure to adopt the new salary structure to improve the quality of skills attracted to the Registry Given the apparent enthusiasm with which project negotiations took place these inhibiters were unanticipated |  |  |  |  |  |  |  |  | Project Outputs Describe the major external factors that have either enhanced or negatively affected the achievement of project outputs. Indicate if these factors were originally contemplated as Assumptions in the Logical Framework. The key factors negatively influencing project outputs include: 1. Time delays in decision making as it relate to external parties 2. Ambiguity about the contract and difference in the modes of operations expected of contractors 3. Shortages in the Allocation of adequate counterpart funding 4. Poor performance of building Contractor |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| # VI. Efficiency in Project Implementation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicate the implementation Efficiency Rating in accordance with the criteria below: HE [ ], E [ ], I [ ], VI [ ] |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Highly Efficient (HE): |  |  |  | The project was implemented within the original schedule and budget |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Efficient (E): |  |  |  | a) Most of the components of the project were implemented within the original or revised schedule and budget, and b) the overall implementation time delay is less than 15% of the original or revised schedule and budget |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Inefficient (I): |  |  |  | a) Significant components of the project were implemented with delays in accordance with the original or revised schedule and budget, and b) the overall implementation time delays is more than 15% and less than 50% of the original schedule and budget |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Very Inefficient (VI): |  |  |  | The project was implemented with delays representing more than 50% of the original schedule and budget |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicate the major reasons that affected the efficiency in project implementation in accordance with the following criteria, and provide a brief explanation below: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| [ ] Delays in 1egislative approvals; [ ] Poor supplier/contractor performance; [ ] Qualified external audit. [ ] Lack of borrower/executing agency commitment and/or ownership; [ ] Inadequate project/component design; [ ] National Policy changes. [] Counterpart funding shortfall; [ ] Contract condition compliance delays; [ ] Executing agency Policy changes. [ ] Weak executing agency institutional capacity; [ ] Bank efficiency (response delays); [ ] Bank Policy changes. [ ] Community/political opposition; [ ] Procurement difficulties; [ ] Other (please specify). [ ] Inadequate consultant performance; [ ] Inadequate cost estimates. [ ] Difficulties in inter-agency coordination; [ ] Cost overrun. |
| Provide brief explanation of the major factors affecting (positively or negatively) implementation efficiency: No effort has been made to enact draft laws or to issue the Ministerial Order to give effect to the Deeds Registry Act. While there is symbolic commitment to project, the absence of counterpart funding, the failure to take actions that were possible, and the continuing power struggles between the Ministry and the Deeds Registry all point to the absence of real commitment. After some initial delays, the project commenced reasonable well with a Project Coordinating Group. That approach was abandoned with a change in personnel at the Ministry and the Coordinating Group was frustrated and ceased operating. Eventually, two Project Coordinators whose performances were short-lived, ineffectual and plagued with managerial conflicts were contracted. The continued conflicts affected the performance of all but 1 of the 5 Consultants on the project. The contract of the Consulting firm, Chemonics International, Inc was aborted and four individual consultants contracted to complete the activities. One of these Consultants contract was suspended at a critical point of the Contract delivery, while another Consultant left in frustration and one Consultant had his contract extended by 8 months due to performance problems with the building contractor. A three-month delay was caused due to poor coordination between the Ministry of Legal Affairs and the Lands and Surveys Commission. This occurred when the Executing Agency expressed its desire to construct a new building instead of the original plan of refurbishing a building at the Lands and Surveys Commission. This however was not in accordance with the rules for the use of MIF resources and ultimately had to be shelved. This delayed the removal of records etc and affected the refurbishment schedule. Additionally, the Building Contractor had underbid due to the exclusion of some of the technical specifications from the bid documents. This pressure of underbidding exacerbated the poor quality of work when the supervising Consultant suspended his contract. The Contractor used this absence of supervision to use materials below the specification and do shoddy work some of which had to be corrected. Procurement difficulties resulted in delays that negatively affected the acquisition of the computers. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| # VII. Sustainability Analysis |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Comment on the project sustainability after completion taking into consideration the strengthening of the a) institutional, b) technical and c) financial capacities resulting from project activities. Compare expected levels of sustainability at the time of project approval with that likely to be achieved at the end of the project. If the project contemplated cost recuperation mechanisms, indicate levels achieved in comparison with the projected levels, making specific reference to shortfalls and related reasons. Include the conclusion and recommendation of the sustainability workshop and specify the measures that have been agreed with the EA to ensure the continuity of project activities after completion, and comment if these agreed measures are being taken by the EA and if they likely to continue in the future. Indicate if in your view there are major internal or external factors that may affect the sustainability of the project in the future. Institutional Sustainability is considered to have been achieved when prevailing structures and processes have the capacity to continue to perform their functions over the long term. In terms of institutional strengthening of the Deeds Registry, the project envisaged inter alia reform of the legal framework for secured transactions, the establishment of some form of organizational autonomy, considerable human resources development and increased stakeholder involvement. While many reports were written, not enough was done by way of concrete implementation and this does not auger well for institutional sustainability. Institutional sustainability is driven by highly motivated human capital and this was precisely one the areas in which little implementation took place. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Technical Sustainability has to do with whether the prevailing technology and associated procedures are currently up-to-date and can be readily upgraded in the future and whether the available human resources are fully trained and capable to operate such. Although the Deeds Registry processes were completely re-engineered on paper during project execution, not much was implemented. As a result, the computerization proceeded on the basis of existing procedures. Full computerization, encompassing activities to bring all historical records online and connecting the sub-Registries of New Amsterdam and Suddie to Georgetown, was not achieved under this project. It therefore follows that technical sustainability at the end of the project is somewhat impaired. Notwithstanding, funds have been allocated in the new Support for Competitiveness Loan to support the improvement of the computerized business registration system at the Registry, and will finance technical assistance for: (i) the digitalization of historical records and the creation of a database for business names and companies; (ii) the establishment of linkages between all the registries offices. Financial viability of the Registry was predicated on the ability of the agency to provide efficient services that could then attract a scale of fees that adequately cover operational costs. The willingness of users to pay more for a better service was never in doubt. The project anticipated the development of a chart of accounts and new fee structure consistent with the establishment of an autonomous agency. Also, it contemplated higher levels of remuneration to attract and retain better staff. The second survey revealed that users have seen very little improvement in most aspects of the service over the last five years. The flexibility of the agency to charge additional fees on the basis of improved services is therefore quite constricted. This limits the financial sustainability of the project. A key external limitation on sustainability is the seeming lack of commitment to effect the necessary changes for the creation of an autonomous Deeds Registry. The signing of the Ministerial Order to bring the Deeds Registry Act into force has been included as a first tranche conditionality under the recently approved “Support for Competitiveness Loan”. the resources of the Loan Program will finance technical assistance for a consultancy that will put together a four-year action plan for the Registry based on previous work of consultants and will include at least: (i) a financial plan with a new schedule of fees and services, forecasts of fee revenues and the proportion of revenue to be used by the new agency; and (ii) the definition of a new organizational structure for the Registry, new salary scales and a human resource plan for the new status of the Registry. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Considering the previous analysis, rate the probability for the sustainability of this project during the next three (3) years |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  Very Probable (VP)  Probable (P)  Low Probability (LP)  Improbable (I) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Very Probable (VP) | Most of the factors influencing project sustainability were included in the project design; during project execution there was significant progress in its institutionalization; at the project completion future actions required to ensure sustainability and a strong commitment is observed from the national authorities to maintain an ongoing flow of project outputs. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Probable (P) | Some factors influencing project sustainability were included in the project design; during project execution some efforts were made towards its institutionalization; at the project completion future actions required have been foreseen in order to ensure sustainability of the project. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Low Probability (LP) | Some factors influencing project sustainability were included in the project design; during project execution few efforts were made towards its institutionalization; at the project completion the future actions to be taken in order to ensure project sustainability, are not clear. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Improbable (I) | There are no foundations to expect project sustainability. The factors influencing project sustainability were not considered, neither during project design nor execution. No progress is observed towards the project institutionalization and no future actions required have been established to ensure project sustainability |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| VIII. Lessons Learned |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ### Provide a detailed account of lessons learned from the implementation of the project, considering critical factors that affected the design,, approval, negotiation, execution, monitoring and completion of the project.. In this analysis, consider a) technical, b) institutional and c) operational factors related to the project, as well as external factors that affected project performance. In addition, make recommendations for the improvement of future project design and execution, specifying measures and actions to improve project performance and results, as well as those for strengthening project supervision and monitoring. - The major weakness in the implementation of this project was the lack of a dedicated full-time coordinator and a properly functioning project executing unit. Neither the Donors Memorandum nor the Annex A of the Agreement established a viable mechanism for project coordination or supervision. It is of critical importance that a project execution unit is established and staffed with qualified individuals, on a timely basis, if projects are to be efficiently implemented. - The delays in the contracting of the consultants were due mainly to the need to prepare and agree on the Terms of Reference for the consultancies. The project design should include all the necessary terms of reference as part of the technical proposal before it is approved by the CRG. - To provide for a transfer of technology and thus contribute to the sustainability of the project achievements, the beneficiary should, as far as possible, identify suitable counterparts to work with the international consultants. - In operations where there is a mix of reform activities and investment activities, there is sometimes a tendency to advance the investments while paying little regard to the reform activities. It is highly recommended that in such operations, the pace of the investment activities is linked to the implementation of the reforms. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Provide a summary of the Final Report of the Executing Agency, emphasizing results obtained and lessons learned and action to be taken to ensure project sustainability, as well as its own evaluation of the Bank’s performance. Include said report as an Annex IX. Completion Report of the Executing Agency. The Final Report of the Executing Agency has not been received. |
| X. Other Annexes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Include any other document that may contribute to a better understanding of the development results of the project. - Financial Information and Financial Statements - Aide Memoire – Sustainability Workshop |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |