Legiii/su-507146-su

APPENDIX

PLAN OF OPERATIONS

SURINAME

FEBRUARY 2, 2005

- Executive Summary

| Project name: | Institutional Strengthening of Suriname’s Social Safety Net (SSN) |  |  |  |
| --- | --- | --- | --- | --- |
| Project number: | SU-T1008 |  |  |  |
| Team members: | Mario Sánchez, Project Team Leader (RE3/SO3); Antonio Giuffrida (RE3/SO3); Jennelle Thompson (RE3/SO3); Ian Mac Arthur (SDS/SOC); Kevin McTigue (LEG); Marcelo Pérez Alfaro (COF/CSU); and Ethel Muhlstein (RE3/SO3) |  |  |  |
| Beneficiary: | Suriname |  |  |  |
| Executing agency: | Ministry of Social Affairs and Housing (SoZa) |  |  |  |
| Target Beneficiaries: | Beneficiaries of Suriname’s SSN |  |  |  |
| Financing: | IDB (FSO): Local: Total: |  |  | US$149,500 US$ 15,000 US$164,500 |
| Objectives: | The goal of this program is to set up the basis for improving the institutional and organizational arrangement for a reformed SSN. Its purpose is twofold. First, it intends to assess the current institutional and organizational setting of Suriname’s SSN in order to develop a capacity building plan. Second, it aims at establishing a SSN Reform Strategy through a process of stakeholders’ consultation. |  |  |  |
| Execution timetable: | Execution Period: |  |  | 8 months |
|  | Disbursement Period: |  |  | 12 months |
| Special contractual conditions: | As a condition prior to eligibility of this TC, SoZa will designate a coordinator with Bank’s no objection, as described in Paragraph 5.3. |  |  |  |
| Exceptions to Bank policies and procedures: | There are no proposed exceptions to Bank policies or procedures. |  |  |  |
| Environmental and social review: | There are no foreseeable environmental or negative social impacts occurring from the implementation of this TC. |  |  |  |
| Coordination with other official development finance institutions: | - The major international donor in Suriname is the Netherlands, through the so-called Independence Treaty Funds. Dutch assistance was re-established after a period of low activity. The Netherlands and Suriname agreed to channel the last trench of these funds through a sector wide approach. Although the Social Safety Net Sector was not chosen as such, some of the activities involved in the Sector Plan for Health are related to the Health System for the poor. There is no other major development institution assisting the Social Safety Net Sector. |  |  |  |

- BACKGROUND AND JUSTIFICATION

- A.	Main issues

  - A social safety net (SSN) is defined as the array of social programs that guarantee a minimum level of well being to individuals and households affected by chronic poverty or transitory negative shocks. The Government of Suriname has placed assessing and strengthening its SSN system as a priority within its social development agenda. The rationale for such prioritization is straightforward under a scenario characterized by fiscal prudence on the one hand, and high poverty incidence (46% of households and 67% of individuals) and social vulnerability (due to high economic volatility) on the other. It is crucial for Suriname to deliver SSN services effectively, with adequate coverage, and in an efficient manner, in order to protect its chronically poor and vulnerable populations, and in order to promote development oriented investments by these populations.

  - It is widely recognized that institutional settings are key determinants of the quality of policymaking and of the efficiency of social services delivery. Therefore, it is crucial to rely on an adequate institutional and organizational capacity while reforming the delivery of SSN services. During 2004, the Bank financed Suriname’s Poverty and Social Safety Net Assessment (SSNA) in order to help define specific actions of sector reform and Bank support. One of the recommendations of the Assessment was to strengthen the Ministry of Social Affairs (SoZa) technical capacities for policy-making, monitoring and evaluation, as the Ministry in charge of designing the welfare policy of the country, providing welfare services for the poor, and overseeing the policies for the elderly, the youth and the disabled. This Technical Cooperation represents a follow up of that recommendation by the Government of Suriname and by the Bank.

- B.	Program rationale and consistency with Bank strategies

  - This Technical Cooperation is consistent with the Bank’s country strategy in Suriname (GN-2080-1), the core of which is to support policy and institutional reforms in order to improve institutional and incentive frameworks. One of the five principal areas of strategic focus is human resource development and social inclusion.  Within that strategic area, the Bank’s strategy is to promote social inclusion by strengthening the SSN. The proposed program fits with this strategic goal as SSN programs are an essential element of human resource development and social inclusion. The proposed technical cooperation was included explicitly in the operational program updated in the last Programming Mission (November 2004).

- C.	Other initiatives complementary to this program

  - The Bank is supporting a wide array of actions that complement this operation. One of the main activities funded by the Support for the Implementation of the Health Sector Reform Program (1537/OC-SU) is the implementation of a beneficiary administration system, known as Beneficiary Information and Payment System (BIPS). The system will be introduced to allow for a continuously updated and automated list of persons eligible to receive free health care and as a management tool for other social benefits administered by SoZa, and eventually other ministries. BIPS will fundamentally change the way in which SoZa manages programs and will bring to surface valuable information for planning and evaluation purposes. BIPS implementation is scheduled to begin in March 2005. Another complementary activity of that Program is supporting the improvement of SoZa targeting mechanisms. That subcomponent seeks to expand the free health cards program of SoZa to all poor households, while simultaneously reducing the inclusion of non-poor households. Scorecards with clear criteria for eligibility will be introduced to improve the transparency of the health card awarding system. Additionally, a CT Intra ATN/SF-8951-SU was recently approved, to explore successful social protection systems in the region. The CT Intra will finance four SoZa high officials to look at experiences related to beneficiary administration systems in both Jamaica and Colombia.

  - Finally, the Bank will process a Technical Cooperation that will support the preparation of a pension reform program in Suriname. The pension system has a strong link to the SSN programs through the Old Age Pension System (AOV), which gives a flat allowance to every Surinamese over 60 years.

- D.	Value added of this program

  - As it has been discussed previously, it is well known that for any program, institutional and organizational factors cause service delivery failure and project implementation problems. This is particularly true for SSN interventions, given their multi-dimensional and multi-sectoral nature. The value added of this program is twofold. First and as an immediate result, it will produce a picture of the institutional and organizational factors that currently hinder or facilitate SSN services delivery in a cost-effective manner. Second, the outputs of this TC will provide the basis and guidance for preparation of a program, including an indication of its appropriate size, which will aim at reforming the delivery of SSN services, in order to improve coverage, efficiency and effectiveness in the provision of SSN services in Suriname.

- PROGRAM DESCRIPTION

- A.	Program goal and purpose

  - The goal of this program is to set up the basis for  improving the institutional and organizational arrangement for a reformed SSN. Its purpose is twofold. First, it intends to assess the current institutional and organizational setting of Suriname’s SSN in order to develop a capacity building plan. Second, it aims at establishing a SSN Reform Strategy throughout a process of stakeholders’ consultation (both within and outside the government.)

- Components

  - The Program is constituted by two components. The first component’s products will be the Institutional and Organizational Assessment (IOA) and the Capacity Strengthening Plan (CSP). The second component will finance the development of the SSN Reform Strategy (RS).  The sequencing of the products will be the following. Once the IOA is completed, the RS will be developed, and after that, having determined the scope of the reform, the consultancy that prepared the IOA will be in charge of resuming its work to finalize the CSP.

  - Component 1. Institutional and organizational assessment (US$63,000)

  - During the first phase of this component, the IOA will be produced as a policy-dialogue document, which will include a background section where the general ethno-socio-political setting will be discussed, together with a description of the public and private sector administrative culture, general perceptions of social assistance programs, and a discussion of the current normative and administrative framework under which SSN programs operate. It will also discuss SoZa’s institutional (rules of behavior, procedures, regulations, accountability, incentives, cooperation and coordination with other relevant actors) and organizational (human, financial and technical resources and leadership) capacity. The consultancy will also deliver baseline information on current costs of delivering SSN services, in terms of financial resources and time-consumed. It will discuss, as well, the extent of informal and privately provided SSN services, the current and potential state of community-based interventions, and the degree of overlapping with current publicly provided SSN services. Finally, it will include general recommendations on capacity strengthening activities necessary to foster SoZa’s role as a coordinator of Suriname’s SSN, which will be discussed with SoZa’s officers through a dissemination seminar.

  - As discussed in ¶3.2, the second phase of this component will be triggered by the completion of the RS. With a clear idea of the scope of the reform, the recommendations of the IOA will be complemented and/or adjusted, and the CSP will be formulated. The CSP will be presented to SoZa during a workshop.

  - Component 2 – Development of a SSN Reform Strategy  (US$61,500)

  - A key instrument to institutional capacity building is the development of medium and long term goals to orient policy-making, which embody a “vision” shared by key stakeholders. To that end, this component will finance a process of consultation and consensus building among government officials and other relevant stakeholders on the purpose and process of SSN reform, taking the conclusions and recommendations in SSNA and IOA as building blocks to produce the RS. Specifically, this component will finance a workshop with government officials and other key stakeholders, and a facilitator, who previously to the workshop will interview key participants, in order to understand the political economy of the consensus-building process. Annex 2 contains Terms of Reference for the workshop facilitator. The component will finance as well basic training to selected government officials in order to enhance their technical capacity as leaders in the development of the RS. Terms of reference for the technical training sub-component will be prepared by the project team in light of the findings and recommendations of the consultancy discussed in the previous section. It is expected that some of the topics for capacity strengthening will include: (i) poverty and vulnerability measurement and analysis, (ii) monitoring and evaluation of programs and services performance; (iii) strategic analysis; and (iv) Logical Framework methodology. This consultancy will also support the Government of Suriname while developing the RS, after the consultation process has been implemented.

- COST AND FINANCING

- A.	Summary cost table

  - Table 4.1 presents the program’s summary cost table.

| Concept | IDB | GOS | Total |
| --- | --- | --- | --- |
| Component 1: Inst. And Org. Assessment | 63,000 |  | 63,000 |
| Consultancy Fees | 35,000 |  | 35,000 |
| Travel | 3,000 |  | 3,000 |
| Per diem | 5,000 |  | 5,000 |
| Dissemination | 20,000 |  | 20,000 |
| Component 2: SSN Reform Strategy | 61,500 |  | 61,500 |
| Consultancy Fees | 20,000 |  | 20,000 |
| Per diem | 1,500 |  | 1,500 |
| Dissemination | 20,000 |  | 20,000 |
| Training | 20,000 |  | 20,000 |
| Counterpart Team (in kind) |  | 15,000 | 15,000 |
| Contingencies | 25,000 |  | 25,000 |
| G R A N D T O T A L | 149,500 | 15,000 | 164,500 |

- B.	Description and composition of financing

  - The total cost of the program is US$164,500. The Bank would finance up to US$149,500 of the costs of the project on a non-reimbursable basis from the net income of the Fund for Special Operations (FSO). The local counterpart of US$15,000 represents in kind contributions related to the local costs for personnel and office facilities for project implementation.

- C.	Sustainability

  - This TC will complement to actions that SoZa is undertaking with Bank’s support. BIPS implementation will begin in May 2005, and the activities related to this TC will reinforce those done in that context.  It is worth to stress that both activities will involve SoZa permanent staff, which has participated along the entire project cycle.

  - The capacity of a program to modify relevant institutions and organizations in order to provide adequate incentives for service providers and beneficiaries is a critical element of sustainability. Building up such capacity is one of the purposes of this TC.

  - One of the main events that could affect sustainability is the national elections of May 2005, and the installation of a new administration by August/September 2005. However, during the preparation of SSNA it was perceived that reforming the SSN will continue being one of the top priorities in the social development agenda a new administration. Furthermore, the experiences of the Health and Education programs, in which the studies and the TC supporting the program definition began under one administration while the program was approved under a different one, show continuity of programs along different administrations.

- EXECUTING AGENCY AND MECHANISM

- .	Executing agency

  - The executing agency will be the SoZa, as the ministry that is actually managing the vast majority of social programs throughout the country.

- .	Executing mechanism

  - Because of SoZa’s weak institutional and organizational capacity, the Government has requested the Bank to execute this program on its behalf to facilitate the smooth implementation and execution of this TC (as per communication #D1578/04 of December 8, 2004 to COF/CSU). Following this request, COF/CSU will have basic responsibility and RE3/SO3 technical responsibility for the Program’s execution.

  - For the Program’s execution the Government  will designate a Task Force as a counterpart for the consultancy services.  The task force will be lead by a coordinator, who will be selected by the Government based on education level, knowledge of SoZa’s programs, and technical capacity for program evaluation. The  coordinator will be responsible for: (i) acting as counterpart of all TC activities; (ii) supporting the activities of consultants; (iii) ensuring the coordination and collaboration of SoZa departments with the consultants; (iv) reviewing the studies and consultancy reports; (iv) assessing project implementation together with COF/CSU; and (v) making decisions concerning the log-frame seminar and the team-building workshop.  The coordinator’s appointment should have the Bank’s no objection, as a condition prior to eligibility of this TC.

- .	Program implementation readiness

  - Given the execution mechanism proposed in the previous section, this TC will be ready to begin its implementation in financing the consultancies as described in ¶3.2 and ¶3.3, as soon as SoZa has designated a  coordinator.

- .	Execution period and disbursement schedule

  - The execution period for this TC will be of 8 months, with a disbursement period of 12 months.

- .	Procurement

  - As requested by the Government, the Bank will conduct the process of selection, hiring and payment of the consulting firms.

- MONITORING AND EVALUATION

- A.	Monitoring

  - The implementation of the three consultancies to be financed by this TC has been designed in a logical sequence that will facilitate quality control. Moreover, Bank’s approval of the technical quality of initial proposals and intermediate drafts will be included as conditions for disbursements for the consultancies.

- B.	Progress and final reports

  - The consultancy financed by the first component will produce a methodological proposal for the IOA and a preliminary draft of the IOA, a final draft of the IOA, and the CSP.  The second consultancy will produce a Final Report containing the agreements reached during the workshop for approval by the Government of Suriname. Taking as inputs the SSNA, the preliminary draft of the IOA, and the Final Report on The Consultation Process, the Task Force will be responsible for the development of the RS, supported by the capacity-strengthening consultancy, which will deliver a preliminary report on the expected results of the capacity-strengthening activities, and a final report describing the process of development of the RS. These reports will be reviewed  by the  Bank and the Task Force and approved by the Bank. The Task Force will have a maximum of thirty days to produce comments and suggestions on a report, period after which, the Bank  can consider a report as delivered.

- C.	Describe the evaluations proponed

  - During the workshops and seminars where the products of this TC will be presented to SoZa and other key stakeholders, participants’ evaluations on the pertinence and quality of the products will be implemented. The IOA will produce both quantitative and qualitative baseline information, against which it will be possible to judge the impact of an institutional and organizational capacity strengthening.

- D.	Other auditing, financial management and reporting procedures

  - Standard Bank procedures for auditing, financial management of the resources and reporting will be followed.

- PROGRAM BENEFITS AND RISKS

- .	Program benefits and developmental impact

  - This TC aims at providing and optimal institutional and organizational arrangement for a reformed SSN. Such arrangement is a sine qua non requirement to guarantee that Suriname operates a SSN that focalizes its interventions on the relatively poorer and more vulnerable, with adequate coverage, with minimal transaction costs, and which ultimately provides not only a safety net, but also a “spring-board” towards social development for its beneficiaries.

- .	Target beneficiaries

  - SoZa, as the Ministry in charge of designing and monitoring the welfare policy of the country will be the targeted beneficiary institution of this TC.

- .	Risks

  - The program’s risks are related to the coming elections in the sense of the continuity of the program. That risk is mitigated by the perceived—during the implementation of Suriname’s Poverty and SSN Assessment—consensus among main stakeholders on the need of streamlining the SSN, which this TC is designed to strengthen, and because of the implementation of the activities mentioned in Section II-C, which are also financed by the Bank and provide a solid base for the TC.

- RECOMMENDATION

  - Mario Sánchez, as team leader of this project, recommends its approval and the use of resources from the Fund for Special Operations (FSO), for a total of US$149,500, to finance this project.

- APPROVAL

Vo. Bo. ______/s/ Juan M. Fariña _________	Date: FEB-4-2005 __

Juan M. Fariña, SO3/CHF

Vo. Bo. _____/s.f./ Dora Currea __________	Date: FEB-4-2005___

Dora Currea, OD6/CHF

Vo. Bo. _____/s/ Camille Gaskin-Reyes ____	Date: FEB-11-2005___

Camille Gaskin-Reyes, RE3/DEP

Approved by: ___/s/ Ciro De Falco________	Date: FEB-11-2005___

Ciro De Falco,  RE3/MGR

Suriname Poverty and Social Safety Net Assessment (Pérez-Calle & Saavedra; IADB 2004, final draft).