LEGIIII/SU-550289-05

ANNEX

THE PROJECT

Consolidation of Democracy in Suriname through

Strengthening of Electoral Processes

I.	Objective

  - The objective of the project is to strengthen, on a sustainable basis, key processes and structures that ensure that electoral processes in Suriname are free, fair, transparent and accessible to all voters in Suriname.

  - The main expected specific results of this project are: (i) improved quality, effectiveness and efficiency of the organization of the elections by the electoral authorities, with specific focus on sustainable improvement of the electoral register and professionalizing the independent supervision of the administration of the elections; (ii) increased awareness and involvement of the electorate in the elections and related governance areas; (iii) enhanced capacity of NGOs to successfully implement civic education programs; (iv) increased credibility for the electoral process and related democracy outcomes through sustainable, national improvements in transparency, supervision and observation; and (v) improved electoral system, through electoral legal reform and improving the role of District and Resort Councils in decentralizing public participation.

II.	Description

  - This objective will be achieved through the implementation of four core project components.

- Component I: Technical assistance to electoral authorities

  - Under this first component, financing of technical assistance to the electoral authorities: the Independent Electoral Bureau (OKB), the Central Civil Registry Bureau (CBB), and the Central Voting Office (CHS); will enhance the capacity of the national electoral bodies to conduct fair and technically sound elections. Assistance will be financed to improve management of the elections, and to obtain an accurate voter register including, in particular, youth and people living in the interior.

  - A Chief Technical Adviser (CTA), to be financed under the program, has been attached to the OKB, and is also working with other electoral authorities, the CBB and the CHS. Assistance to strengthen the management and processes for the elections shall be financed. This plan includes indicators to monitor progress in the implementation.

  - Under this first component, equipment and specialized software for the automation of electoral processes, including training packages, will be financed, in particular for the establishment and maintenance of databases on the voters´ list, political parties, number of votes obtained, number of seats in parliament obtained and various other applications related to the results of the elections, all presentable in graphic formats. The results of the election will be transferred through online Internet connection between the several Central Polling Stations in the various districts and the central database at CHS. Data will be centrally stored and processed.

  - Financial assistance will also be provided for the ‘Interior Project’ in order to reach the difficultly accessible interior, inhabited by indigenous and maroon people. Materials will be financed for the production and issuance of ID cards (film and laminate materials); for cleaning up and updating of the voters’ registry; production and dissemination of voters cards (cardboard and paper, print cartridges, preformatted forms for printing of voters cards); and for the related missions to the interior (fuel for generators and outboard engines, hammocks, provisions and first aid kits).

- Component II: Civic and voter education through civil society

  - A second component is a program for civic and voter education designed and implemented by Surinamese non-governmental organizations (NGOs). This is aimed at enhancing the level and quality of participation of the Surinamese population in the democratic and electoral processes.

  - A civic education sub-unit has been established within the Technical Project Implementation Unit, headed by an international technical adviser and national staff. The unit has called for proposals for the implementation of civic and voter education activities by the NGOs. The civic education unit is evaluating proposals, and is providing guidance or training for implementation, management of funds and financial and narrative reporting to the selected NGOs, where necessary.

- Component III: Domestic supervision of the elections and media monitoring

  - The third component is domestic supervision of the elections, which emphasizes the importance of sustainable, comprehensive, national supervision and professional and neutral reporting by the media of the electoral processes. Under this component, the current supervision system coordinated by OKB is being professionalized through standardization of the recruitment procedures for electoral supervisors, training of domestic supervisors according to internationally accepted standards and standardization of reporting and complaint procedures.

  - Under this component, broad discussions (among others in the form of workshops) will also be financed on the need to establish a system of national supervisors, therewith also reducing the need for international observation of the elections and increasing and consolidating the level of trust in national democratic institutions and mechanisms. Such national supervision mechanisms would function in accordance with international standards, would have participation of civil society groups without party affiliation and would be external to the existing electoral structures to guarantee independent observation. A domestic supervision sub-unit, headed by an international adviser, will be financed within the Technical Project Implementation Unit to implement these activities.

  - A media monitoring sub-unit will also be financed within the Technical Project Implementation Unit, consisting of an international adviser, a national professional and support staff, for providing a specific training program for the media that focus on a professional and neutral reporting on the electoral process, and more generally, on democracy issues in-between elections. The sub-unit also monitors (by taking samples of) the reporting by media on electoral matters, paying particular attention to freedom of the press and freedom of expression. The results will be used for lessons learned in future elections. The media monitoring sub-unit functions in close cooperation with the domestic supervision sub-unit sharing the same secretariat.

  - The project includes financial provisions for international travel, in particular international travel of the technical specialists/advisers (CTA, Technical Adviser in Civic Education, Technical Adviser in Domestic Observation, Technical Adviser in Media Monitoring) and of six regional observers from the Caribbean Community (CARICOM), from country of origin to Paramaribo and return.

- Component IV: Post-electoral governance activities

  - The fourth component comprises post-electoral governance activities, covering assistance for a thorough review of electoral laws based on the lessons learned from the successive elections and the 2005 elections and a study on the District and Resort Councils.

  - Together with the electoral authorities, in particular with the OKB as the permanent and independent body, an electoral law review process should engage the new legislature to implement electoral law reform and necessary constitutional amendments, in conformity with international standards. The District and Resort Councils should be empowered to fulfill their role in the democratic system of Suriname. A pilot study will analyze roles and responsibilities of the local councils that were established at the last Constitutional revision in 1987, but turned out in practice not to be fully functional and thus resulting in an underutilization of existing democratic structures. Upon presentation of this study, follow up activities shall be planned. Close co-operation will exist with the IDB-funded decentralization project (Loan 1343/OC-SU), which seeks to create a resource base for District and Resort Councils. The post-electoral follow up activities complement those carried out under UNDP's broader governance program and will be coordinated with that program.

## Total Cost of the Project

3.01	The estimated total cost of the Project is the equivalent of US$ 2,357,770 approximately; of which US$544,100 is going to be financed by the Bank on a non-reimbursable basis from the net income of the Fund for Special Operations (FSO). The equivalent of US$648,700 is going to be financed by the European Community (EC), the equivalent of US$260,370 by the UNDP and the equivalent of US$904,600 by the GOS, in accordance with the following Budget:

# Budget

(Approximate Equivalent in US$)

| Project/Activity | IDB | EC | UNDP | GOS | TOTAL |
| --- | --- | --- | --- | --- | --- |
| i. Project management | 27,200 | 208,650 | 103,889 | 161,654 | 501,393 |
| ii. Technical assistance to electoral authorities (OKB, CBB, CHS) | 172,700 | 65,000 | 61,639 | 618,598 | 917,937 |
| iii. Civic and voter education | 111,800 | 42,900 | 38,770 | 0 | 193,470 |
| iv. Domestic supervision of elections and media monitoring | 139,100 | 332,150 | 56,072 | 124,348 | 651,670 |
| v. Post-electoral activities | 68,000 | 0 | 0 | 0 | 68,000 |
| vi. Audit | 10,000 |  |  |  | 10,000 |
| vii. Contingencies | 15,300 |  |  |  | 15,300 |
| TOTAL | 544,100 | 648,700 | 260,370 | 904,600 | 2,357,770 |

IV.	Execution

  - The project is being directly executed and coordinated by the United Nations Development Program on behalf of the other contributing partners. Implementation of the activities funded by the Bank will be governed by the existing cooperation agreement between the Bank and the UNDP, namely the Agreement for the Cooperation and Coordination of Activities between the UNDP and the IDB (June 2003).

  - A Technical Project Implementation Unit has been established and equipped, guided by a Chief Technical Adviser (CTA), housed by the UNDP. The UNDP selects, contracts and supervises the international and local staff that comprises the three technical sub-units (civic education, domestic supervision and media monitoring).

  - A monitoring system is being established by the CTA to spot-check the implementation of activities by the implementing partners. Project evaluation and auditing will be conducted in conformity with the cooperation agreement between IDB and the UNDP.

  - The Technical Project Implementation Unit will assist, if necessary, in the establishment of a core unit for international election observers, once international election observation is secured.

  - The program is in an advanced stage of readiness given the proximity of the elections. The TOR for all the consultants have been prepared and in fact three technical assistants have been contracted and started working. Many of the project activities have begun and/or will be expedited in the coming weeks. As a result, the Bank has agreed to recommend the recognition of expenses (up to US$376,000) and retroactive financing (up to US$348,000) provided that advance procurement has been carried out according to Bank procedures and policies.

- V.	Monitoring and Evaluation.

  - Work plans are being elaborated by the Technical Project Implementation Unit to demonstrate the indicators and achievement of the results at the different levels and will be monitored at review meetings and reports of the relevant sub-units.

  - The implementation of the project will be monitored through bi -monthly meetings prior to the elections and at least once a quarter during the remainder of the execution period between the Ministry of Planning, Ministry of Home Affairs, the UNDP, EC, and IDB. During these meetings the UNDP will be responsible for providing progress reports that, inter alia, monitor expenditure and cost estimates against the project budget. In addition, written progress reports, including project budget and disbursement status, will be submitted to the Bank by UNDP every six months, which will be used by the Bank to track the progress of the project.

  - Six months after the election results, a joint report will be prepared by the UNDP in collaboration with the Ministry of Home Affairs, the EU and the IDB containing the achieved results and lessons learned from the implementation of this project. This report on the results will be submitted for consultation to the relevant counterparts and the authorities and/or funding institutions as well as stakeholders, thus providing a preliminary measure of the success of the project/electoral process. At the end of the execution period a final independent evaluation, focusing on the post electoral project activities will be similarly prepared and submitted to the relevant counterparts.

Eligibility and selection criteria for small grants to NGOs/CSOs in civic education and voters education include the following: (a) applicants should be non-political/non-partisan, civil society non-profit organization, e.g. professional society, association, non-governmental organization (NGO), community-based organization (CBO), umbrella/network organization; (b) relevance of proposed project activities to organization’s mandate and experience; (c) capacity of organization to manage proposed project; (d) project activities must address raising awareness and motivation of the target group/electorate to participate in the electoral process. Eligible activities include drafting, production, distribution and propagation of civic education material and awareness activities; and (e) target group priority: women, youth, people of the interior, new voters.

Calculated with an exchange rate of US$1.30 per Euro.