LEGIII/SU-503106-05

APPENDIX

SURINAME

PLAN OF OPERATIONS

February 11, 2005

- Executive Summary

| Project name: | Strengthening the legal and institutional foundation for private investment in Suriname. |  |  |
| --- | --- | --- | --- |
| Project number: | SU-T1013 |  |  |
| Team members: | Kim B. Staking, Project Team Leader (RE3/FI3); Carlos Elias (RE3/OD6); Kevin McTigue (LEG), Marcelo Pérez Alfaro (COF/CSU); Xiaolun Sun and Benjamin Herzberg (FIAS). |  |  |
| Beneficiary: | Suriname |  |  |
| Executing agency: | Inter-American Development Bank |  |  |
| Target Beneficiaries: | Private sector firms and associations. |  |  |
| Financing: | IDB (FSO): FIAS co-financing (non-reimbursable ) Local: Total: |  | US$99,960 US$25,000 US$15,000 US$139,960 |
| Objectives: | The goal of this program is to facilitate private investment in Suriname. Its purpose is to: (i) prepare an amendment to the Investment Law and related legislation to eliminate unfair or inequitable treatment and reduce current levels of bureaucratic uncertainty; and, (ii) to develop an Action Plan to improve the institutional environment which supports private investment. |  |  |
| Execution timetable: | Execution Period: |  | 8 months |
|  | Disbursement Period: |  | 12 months |
| Special contractual conditions: | As a condition prior to eligibility of this TC, MOF will designate, with Bank’s no objection, a Project Promoter as described in ¶5.3 and ¶5.4. |  |  |
| Exceptions to Bank policies and procedures: | There are no proposed exceptions to Bank policies or procedures. |  |  |
| Environmental and social review: | There are no foreseeable environmental or negative social impacts occurring from the implementation of this TC. |  |  |
| Coordination with other official development finance institutions: | - The Project will build upon recommendations provided in two reports of the Foreign Investment Advisory Service (FIAS) regarding to the Investment Environment in Suriname [Diagnostic (2003); Recommendations (2004)]. At the Government’s request these two reports were fully funded by the Bank. This Project supports implementation of the most critical recommendations of the FIAS reports. FIAS– jointly operated by the International Finance Corporation (IFC) and the World Bank- who will cofinance this TC has worked with the Project Team in the design of this TC and will continue providing advisory services to Government during the execution of this Project. |  |  |

- BACKGROUND AND JUSTIFICATION

- A.	Main issues

  - After a long period of political and economic turmoil, Suriname currently enjoys macroeconomic stability and a good relationship with the international donor community.  The current administration has had a respectable track record in economic management and introducing reforms, which are reflected in a substantial increase of total investment.  The IMF estimates that total investment almost tripled from 11.9% of GDP in 2000 to 33.4% of GDP in 2003. With the intention to make the country even more attractive to private sector investment, in 2001 the Government of Suriname passed the Investment Law and the InvestSur Law, which focus on fiscal incentives.

  - At the Government’s request in 2003, the Bank funded the Foreign Investment Advisory Service (FIAS) to evaluate the Investment Law and the investment environment in the country.  The 2003 report recommended the appropriate role for investment legislation within an internationally competitive framework.  This work was followed up in 2004 by a second FIAS report, also funded by the Bank.  This report provided recommendations on how to:

    - improve the taxation system (including a summary of the changes needed to bring the existing Investment Law closer to international best practice);

    - initiate the establishment an effective Investment Promotion Agency,

    - reform fiscal incentives to eliminate those that distort competitive outcomes;

    - modify the accounting treatment of depreciation to assure consistency; and

    - establishing a plan to develop other institutional structures needed to support private investment.

  - The Government of Suriname is determined to improve the investment climate and concurs with many of the recommendations of these reports.  Government however notes that in the current political situation, not all the recommendations can be adopted before the elections in May 2005, and that compromise may be needed with relevant stakeholders in order for the key recommendations to be adopted by the National Assembly before the end of May.  It is therefore proposed that the most critical legal changes be included in an amendment to the Investment Law (and other related legislation) on a fast track basis and a concrete action plan be developed to implement other important, institutional changes over time.  This will be accompanied by a communications strategy to inform and educate critical stakeholders and civil society regarding the importance of the changes.

- B.	Program rationale and consistency with Bank strategies

  - This Technical Cooperation is consistent with the Bank’s Country Strategy in Suriname (GN-2080-1), the core of which is to support policy and institutional reforms in order to improve institutional and incentive frameworks. In this context, one of the five principal areas of strategic focus is private sector development and export-led growth.

- C.	Other Bank initiatives complementary to this program

  - The Bank continues supporting a wide array of actions that complement this operation and supports private sector development. The Agriculture Trade Policy Loan, which resulted in abolishing the trade licensing system, quotas and import prohibitions lowered the costs of trade and increased transparency.  The Bank is also preparing a trade loan, which should be approved before the elections, with the objective of improving public management of Suriname’s foreign trade by strengthening the country’s capacity to formulate, negotiate and implement trade policy and related agreements.  To address poorly defined property rights in Suriname, the Bank’s pipeline includes an operation in land management.  Finally, Government requested support to improve its tax administration, and the Bank is at the preliminary stages of preparing a new program, including the participation of the IMF, to support the country in this important area.

  - PRI, MIF and IIC are actively seeking opportunities to invest in Suriname, but have been hampered by the lack of investment.  PRI is in discussion with a number of large international investors but is awaiting final decisions by the project sponsor regarding whether they will proceed with these investments.

  - MIF has two TCs in execution.  A $450,000 project for airport security (49% disbursed) and a $845,000 project of sustainable tourism (0% disbursed – approved in late 2004).  Suriname is also indirectly benefiting from a MIF US$2.5 million loan and non-reimbursable US$335,000 TC to Development Finance Ltd. (DFL).  The objective of this MIF operation is to improve the competitiveness of small and medium-sized enterprises.  DFL has established a subsidiary, DFL South America, based in Georgetown, Guyana, with a branch office in Suriname to provide financing and technical assistance to SMEs in Guyana and Suriname.  The IIC is also considering a US$200,000 equity participation in DFL South America to strengthen the capital base of the institution and allow it to provide financing to a larger number of SMEs in Guyana and Suriname.

- D.	Value added of this Program

  - The Bank supports the Government’s urgency in using the period before the elections to build consensus among stakeholders and attempt to fix the most glaring problems with the Investment Law.  Based on the available work, an environment conducive to private investment will be significantly improved if the Investment Law is amended by: (i) leveling the playing field for private sector investment by eliminating current tax incentives, which are based on non-transparent processes and result in unfair treatment of firms; and, (ii) defining the depreciation mechanism to be used by firms, which was left undefined in the law.  Moreover, Government is also considering lowering the corporate income tax rate that stands at 36%, one of the highest in the Caribbean region, as a further incentive for increased private investment.  Preparing an Action Plan to improve the business environment, which will be used for Bank’s dialogue with new authorities in 2005, will complement these amendments.  This TC is an important input in the process to prepare a new Country Strategy with Suriname and a Private Sector Development Strategy.

- PROGRAM DESCRIPTION

- A.	Program goal and purpose

  - The goal of this program is to facilitate private investment in Suriname.  Its purpose is to: (i) prepare an amendment to the Investment Law and related legislation to eliminate unfair and inequitable treatment of firms and reduce current levels of bureaucratic uncertainty while developing and implementing a communications strategy to inform and involve the relevant stakeholders in this process; and (ii) to develop an Action Plan to improve the institutional environment which supports private investment. The Government hopes to have the legislative changes ready before the elections in May 2005.  The preparation of an Action Plan will support the development of the institutional environment needed to promote private sector investment, building on the basis of the proposed legislative changes.  This Action Plan will provide clear priorities and sequencing of the supporting institutional reforms. These legislative and institutional changes, taking into consideration FIAS’ recommendations, will be a solid step in the direction of promoting private sector development in Suriname.

- Components

  - This TC has two components: (i) Preparation of the Amendment of the Investment Law and other related legislation (including the development an appropriate communications strategy); and, (ii) Development of an Action Plan to strengthen the institutional structure supporting private investment.  The Minister of Finance will assemble a Team of Experts (local and international lawyers, international economist, along with an office coordinator) to implement these two components led by a Project Promoter.  The description of the role of the Project Promoter and the composition of the Team of Experts is provided in ¶5.3.

  - Component 1. Amendment of the Investment Law and related legislation (US$61,660)

  - The Team of Experts will review and revise the existing Investment Law and related legislation affecting the investment environment.  In coordination with the Ministry of Finance, while taking into account the comments of the private sector and other relevant public institutions, the Team of Experts will implement the following work program.  The Project will finance the activities of the Project Promoter, members of the Team of Experts (consulting fees; travel); the hiring of a local public relations firm and general logistical support for the communications/consultations strategy.  FIAS will provide a communications specialist and an international lawyer.

  - Review of current legislation.  The review will compare existing legislation to international best practices.  Attention will be focused on the issues raised in the FIAS reports and other available secondary information.  The role played by the local in international lawyers at this stage is critical, and it is expected that they will provide a good assessment of current legislation.

  - Proposal to revise the current Investment Law and related laws.  The Team of Experts will prepare draft legislation to amend the Investment Law and related legislation, including the elimination of all the current loopholes that provide ad hoc tax incentives and tax holidays, therefore leveling the playing field for private sector investment.  The draft legislation will also include the elimination of unnecessary bureaucratic steps in setting up and registering new and ongoing investments, setting standards for the accounting treatment of a definition of depreciation methods to be used by private sector firms, and other legal norms that suppress desirable private investment.  The Team of Experts will prepare an estimate of the fiscal effects of implementing these actions, on a stand alone basis as well as in conjunction with a possible reduction in the corporate income tax rate.  The Team of Experts should provide solid analysis of additional legislative actions that they propose (that go beyond the Investment Law and related laws).   The Team of Experts should also propose a strategy to phase out current ad hoc tax incentives, exclusions and tax holidays to firms.

  - Communications Strategy.  Key to the success of this TC is the preparation of a communications strategy that is comprehensive enough to facilitate the consultation process.  FIAS will provide a communication expert who will design an overall communications strategy.  The TC will finance the contraction of a local or regional public relations firm which will implement this strategy with support from the FIAS communications expert.  Communication activities should be organized around three target audiences:

- The inner circle consisting of individuals and firms who have a direct stake in the Law, either for financial, economic or political reasons, and who are likely to either provide key support or who might be likely to block the legislative process.  Communication with this group should be done through meetings on an individual and private basis, involving the most senior personnel from both sides.

- The middle circle consisting of people and entities who are the likely users of the Law and which organizations may support it or not, depending of their perception of the issues. Communication with this group should be done on a group basis, through public meetings sponsored by third parties.

- The outer circle consisting of people who have a remote interest in the law but who may provide a general sense of support or discontent for the Government and the National Assembly’s policies on improving the investment climate.  A plan for communicating with the members of this outer circle will developed by the FIAS communications specialist and this plan will then be implemented by the public relations firm.

  - Communication strategies to these three target audiences would likely evolve as the process unfolds and as the date of submission to the National Assembly comes closer.

  - Consultation process.  The Team of Experts will closely coordinate the consultation process with the communications process.  The Team of Experts will identify key stakeholders during the reviewing and revising stages of the process to amend the Investment Law.  In this context, the Team of Experts may invite representatives from the relevant Ministries and administrations to sit in some of the fact-finding meetings. The Team of Experts should also conduct meetings with representatives of the private sector, the social actors, and parliamentarians. The aim of such meetings shall be both informative in terms of keeping stakeholders up-to-date with the Team of Experts’ work process, and to gather feedback on the draft of the Amendments.

  - Prior to the expected publication of the Amendments on the official gazette by the National Assembly, the following steps in the approval of the amendments must be accompanied with communications and consultation activities that will be defined in the process of implementing this TC.

- The Minister of Finance presents the Amendments for review and approval to the Council of Ministers.

- The President presents the Amendments to the Staatsraad for review and approval.

- The President sends the Amendments to the National Assembly for review and approval.

  - Component 2 – Preparation of an Action Plan (US$31,300)

  - The second major component is the preparation of an Action Plan to improve the institutional environment surrounding private investment. The Project will finance the activities of the Project Promoter, the Team of Experts (consulting fees; travel).  FIAS will provide general support and an independent review of the Action Plan.

  - The Action Plan will identify concrete steps that should be taken with respect to the legislative and institutional framework for private sector development, including: (i)  rationalization of the current legal framework; (ii) additional laws needed to provide a good legal framework for Suriname—in particular to look into the need for a law on intellectual property rights and another law to ensure market competition; (iii) the structure and activities of the Investment Promotion Agency; and (iv) institutional structures that are needed to implement a new legal framework—in particular with respect to ensuring that property rights are well defined (i.e. property registries, mortgages, and secured transactions).  The Action Plan will also provide concrete recommendations for eliminating bottlenecks to private sector development, including: (i) the tax system; (ii) the public sector and its public enterprises; (iii) rule of law; (iv) security; and (v) corruption.  The Action Plan will summarize the legal and institutional changes in a comprehensive format and will include sequencing and priorities.

- COST AND FINANCING

- Summary cost table

  - Table 4.1 presents the program’s summary cost table.

| Concept | IDB | FIAS[1] | GOS | Total |
| --- | --- | --- | --- | --- |
| Component 1: Amending Investment Law | 63,660 | 25,000 |  | 88,660 |
| Consultancy Fees | 37,700 | 16,000 |  |  |
| Travel | 1,000 | 4,000 |  |  |
| Per diem | 2,160 | 5,000 |  |  |
| Consultation & Communications | 22,800 |  |  |  |
| Component 2: Action Plan | 29,300 |  |  | 29,300 |
| Consultancy Fees | 26,500 |  |  |  |
| Travel | 1,000 |  |  |  |
| Per diem | 1,800 |  |  |  |
| Counterpart Team (largely in kind) |  |  | 15,000 | 15,000 |
| Evaluation | 3,000 |  |  | 3,000 |
| Contingencies | 4,000 |  |  | 4,000 |
| G R A N D T O T A L | 99,960 | 25,000 | 15,000 | 139,960 |

- (1)FIAS is financed by a Trust Fund. As such, FIAS budgets include staff time and travel expenses for all operations. The total amount of the FIAS budget for this operation, including hiring an international lawyer and WB and FIAS staff time and travel expenses exceeds US$90,000.

- B.	Description and composition of financing

  - The total cost of the program is US$139,960. The Bank would finance up to US$99,960 of the costs of the project on a non-reimbursable basis from the net income of the Fund for Special Operations (FSO). FIAS will finance up to US$25,000, and the local counterpart of US$15,000 represents in kind contributions related to the local costs for personnel and office facilities for project implementation.

- C.	Sustainability

  - This TC is one solid step in the long path to improve the business environment in Suriname.  As such, the approval of the amendments to the Investment Law and other laws will provide a leveled playing field for private sector investment.  The Bank will follow up with complementary activities, of which the development of a Private Sector Development Strategy and a Country Strategy with Suriname will be implemented during 2005.

- EXECUTING AGENCY AND MECHANISM

- .	Executing agency

  - The executing agency will be the Ministry of Finance.

- .	Executing mechanism

  - Because of the Government’s insufficient institutional and organizational capacity to implement this TC in the short period required, the Government has requested the Bank to execute this program on its behalf to facilitate the smooth and execution of this TC (as per communication No.684 of February 18th, 2005). In response to this request, COF/CSU will have basic responsibility and RE3/FI3 technical responsibility for the Program’s execution.

  - The Minister of Finance will form a Team of Experts led by the Project Promoter.  The Project Promoter should be a respected local business leader capable of positively reaching out to a variety of stakeholders.  The Team of Experts will also include two local lawyers, who are experts in legislation related to the Investment Law and an international economist with experience in tax systems and private sector development.  FIAS will provide a communications expert, and will finance an international lawyer.  Finally, an office coordinator will be hired to support the Team of Experts.

  - The Minister of Finance will formally announce the local members of the Team of Experts in a public letter stressing the importance of investment promotion for Suriname, and their objective of undertaking the drafting of amendments to the Investment Law and related legislation.  The letter should also stress that such drafting shall be done in a consultative manner, under the authority of the Project Promoter and that the Team of Experts will prepare a program of complementary actions, with emphasis on the legislative and institutional framework, to improve the investment environment.  The letter should also provide information about the schedule of work, with a delivery date of a final draft of both the Investment Law and the Action Plan.

  - The Bank and World Bank/FIAS staff will provide technical assistance through out the implementation process.   Inter-American Development Bank  and World Bank/FIAS experts would visit Suriname for two one-week missions.  The first one would take place as soon as the draft amendments are ready for discussion. The aim of this Mission will be to participate in the official presentation of the Team of Experts with relevant stakeholders, so as to give international backing to the Team of Experts’ findings.  The Mission would also assess reactions from a variety of stakeholders in order to tune up the communications strategy.

  - The second Inter-American Development Bank-World Bank/FIAS Mission would take place when the draft amendments have been submitted to the National Assembly. The Mission would meet parliamentarians and interest groups to support the proposal as appropriate, and reiterate the messages communicated during the information campaign, in view of facilitating the enactment of the amendments by the National Assembly.

- .	Program implementation readiness

  - The Minister of Finance will send a letter to the members of the Team of Experts inviting their participation by the end of February.  Candidates for local legal expertise have been identified by the Government and are being reviewed by the Project Team.  The TORs have been already prepared and the candidates will be contracted as soon as the TC is approved.

- .	Execution period and disbursement schedule

  - The execution period for this TC will be of 8 months, with a disbursement period of 12 months.

- .	Procurement

  - As requested by the Government, the Bank will conduct the process of hiring and payment of the consulting firms (see ¶5.2).

- MONITORING AND EVALUATION

- A.	Monitoring

  - The Bank will monitor the implementation of this TC through the Country Office, supported by Bank and FIAS staff.

- B.	Progress and final reports

  - The Team of Experts will prepare two final reports for each component.  The report of the first component will include a draft law, and exposition of motives for the law, and a review of the consultative process.  The second report will present and justify the proposed Action Plan.  Draft Reports will be submitted to the Government and the Bank and FIAS for comments prior to submission of the final report.

- C.	 Proposed Evaluations

  - The TC will fund an evaluation of the program.  This evaluation will be contracted to a local consultant.  The evaluation will describe the outputs of each component, and outcomes of proposed actions.

- D.	Other auditing, financial management and reporting procedures

  - Standard Bank procedures for auditing, financial management of the resources and reporting will be followed.

- PROGRAM BENEFITS AND RISKS

- .	Program benefits and developmental impact

  - This TC aims at improving the investment climate for local and foreign investors in Suriname.  A first step in that direction is the amendment of the current Investment Law and related laws, and the preparation of a supportive Action Plan.  However, the activities supported by this TC require complementary actions, which the Bank will support in the context of future programming exercises.

- .	Target beneficiaries

  - The results of this TC will be felt through out the economy, however, in the short term it will directly benefit private sector firms affected by unfair ad hoc practices allowed by the current law.

- .	Risks

  - The major risk of this TC is that the consultation process needed to build consensus around the amendments to the laws take longer than originally expected.  In that event, the country would have missed the window of opportunity that is open until the elections in May.  To ameliorate this risk, this TC allocates a significant amount of resources to the communications strategy, attempting to provide prompt and professional expertise to accelerate the consensus building process.  There is also the risk that the legislation passed by the parliament does not fully resolve the issues or the new administration following the election does not take the steps outlines in the Action Plan.  The Project, by having well prepared and justified outputs, which build on international best practices, and with ongoing IDB/FIAS involvement as independent and  neutral third parties, parties should help reduce this risk.

- RECOMMENDATION

  - Kim B. Staking, as Team Leader of this project, recommends its approval and the use of resources from the Fund for Special Operations (FSO), for a total of US$99,960, to finance this project.

- APPROVAL

Vo. Bo. __________Original signed__________			Date: ___3/2/2005___

Ana María Rodríguez-Ortiz, FI3/CHF

Vo. Bo. _________Original signed________			Date: ___3/2/2005___

Dora Currea, OD6/CHF

Vo. Bo. _______Original signed_________				Date: ___3/2/2005___

Camille Gaskin-Reyes, RE3/DEP

Approved by: _____Original signed_______			Date: ___3/2/2005___

Ciro De Falco,  RE3/MGR