LEGIII/SU-604956-05

ANNEX

THE PROGRAM

Establishment Suriname Gold Mining Association

I.	Objective

1.01	The general objective of the project is to organize the small-scale gold mining sector in Suriname within a private sector regime for the purpose of bringing order to the sector, promote self-regulation, facilitate the transfer and exchange of technology, and lobby for governmental, international donor, and civil society assistance in promoting the sound environmental, social, and financial management of the sector.  The specific objective of the project is to promote the overall competitiveness of the sector, its improved management, and the adoption and use of improved mining practices and technology by legally organizing and establishing the Suriname Gold Miners Association (SGMA) as an NGO and hold the initial election for its office holders.

II.	Description

The program will have the following three components:

Component 1.  Project coordination, legal development, codes, publicity, and materials.

2.01	The project will fund a project advisor to lead and coordinate all aspects of the project and expert consultants for the legal development of the SGMA and an industry wide code of mining practices.  The project advisor will lead the development of a five-year business plan for the SGMA.

Component 2: Workshop and training.

2.02	The project advisor will organize a series of consultations and awareness building workshops with the different stakeholder groups to discuss and review the SGMA bylaws, codes of practices, and other relevant documents and issues.  He/she will also develop training materials and organize workshops to gold concession holders, equipment owners and operators, and others participating in the small-scale gold mining sector.  The purpose of the workshops will be to introduce and explain the objective and purpose of the SGMA, solicit views on the establishment of the association, and foster ownership of the SGMA by the key stakeholders.  Workshops and consultations will be held in all of the important mining areas of the country, as well as in Paramaribo.

Component 3:  Organizing and holding of SGMA elections.

2.03	The project advisor will organize an assembly for the elections of the first officials and Board of Directors of the SGMA as called for in the by-laws of the association.  Workshops and consultations will be offered to concession holders, equipment owners and operators, and others to explain the election process.  The election will be undertaken and the results announced in a transparent manner and as proscribed by law in Suriname, and as stated in the legal establishment of SGMA.

III.	Total Cost of the Program

3.01	The estimated cost of the Program is the equivalent of US$149,500, in accordance with the following Budget:

Budget

(in thousands of US$)

|  | MIF | WWF-G | Total | (%) |
| --- | --- | --- | --- | --- |
|  | US$ | US$ | US$ |  |
| Component 1 | 66,000 | 16,000 | 82,000 | 55 |
| Component 2 | 10,000 | 9,000 | 19,000 | 13 |
| Component 3 | 17,000 | 5,000 | 22,000 | 15 |
| Auditing | 2,000 |  | 2,000 | 1 |
| WWG-G Admin. Exp. | 0 | 19,500 | 19,500 | 13 |
| Contingences | 5,000 |  | 5,000 | 3 |
| Total | 100,000 | 49,500 | 149,500 | 100 |