LEGIII/SU-677078-06

## ANNEX

THE PROJECT

## Support the National Strategic Plan for HIV/AIDS (NSP)

I.	Objective

  - The general objective of the Project is to contribute to the achievement of the Millennium Development Goal of halting HIV/AIDS epidemic and begin to reverse its spread by the year 2015.

  - The specific purpose of the Project is to reduce behaviors that are conducive to HIV/AIDS contagion, as well as stigma and discrimination for People Living with HIV/AIDS.

II.	Description

- 2.01	To achieve the above objectives, the Project finance the following components:

  - Component 1 – Strengthening National AIDS Coordination

- 2.02	This component will strengthen the National AIDS Program (NAP) and the upcoming multi-sectoral National AIDS Commission (NAC).

- 2.03	The component will finance: (a) long-term technical assistance to strengthen the NAP in HIV/AIDS prevention and monitoring and evaluation; (b) short-term technical assistance to support the establishment of the NAC; (c) the acquisition of office equipment and materials for the NAP and NAC; and (d) the implementation of the Protocol of Intentions between Brazil and Suriname in HIV/AIDS to facilitate the exchange of experiences, material and know-how.

  - Component 2 – Stigma and discrimination reduction

- 2.04	The goal of the component is to reduce stigma and discrimination for People Living with HIV/AIDS (PLWHA) through the enactment of a new rights-based legal framework on HIV/AIDS. The component will finance technical assistance provided by a legal firm to draft a new HIV/AIDS legislation for Suriname, as well as draft new legislation and regulations for safe blood bank. Special attention will be given to Moral Act, HIV/AIDS in the workplace and anti discrimination laws. The component will also finance workshops and consultations involving all key stakeholders to ensure a broad consensus on the new legal framework. Further, the component will finance a national information campaign aimed to inform the general public regarding the preparation of the new HIV/AIDS legal framework and reduce stigma and discrimination for PLWHA.

  - Component 3 - Scaling up prevention

- 2.05	The goal of the component is to reduce the risk of HIV infection among the Surinamese population. The component will finance the design, implementation and analysis of Behavior Surveillance surveys (BSS). BSS are a monitoring and evaluation methodology designed to track trends in HIV/AIDS knowledge, attitudes, risk behavior and exposure to interventions in selected segments of the population. The component will finance two rounds of BSS for each of the main at risk populations: youth, men-who-have-sex-with-men (MSM), commercial sex workers (CSW), health workers and prisoners. The second round will be administrated about two years after the first round, to identify and evaluate behavioral changes and estimate the impact of the various interventions, including the prevention projects financed by the component. The component will also support the dissemination of BSS survey’s findings in a way that is accessible to the general public. The dissemination will aim to raise awareness and ultimately to promote behavior change and reduce stigma and discrimination.

- 2.06	The Project will finance the implementation of HIV/AIDS prevention projects aimed at young persons (in particular girls), and other vulnerable populations, including CSW, MSM, health workers and prisoners. The HIV/AIDS prevention projects will be developed and implemented by governmental and non-governmental organizations (NGOs). The component will also provide seed money to finance innovative research on HIV/AIDS prevention produced by graduate students at the University of Suriname. Finally, the implementation of this component will be complemented by the development of a multi–lingual educational/prevention material targeted at different target groups with high-risk behavior, financed through the Global Fund to fight AIDS, Tuberculosis and Malaria.

  - Component 4 - Project administration

- 2.07	This component will finance the hiring of a Project Assistant and administrative support for the Project Execution Unit (PEU), as well as the final evaluation and the final financial audits of the Project.

III.	Total Cost of the Project

3.01	The estimated cost of the Project is the equivalent of US$940,000, in accordance with the following Budget:

Budget

(in US$)

| Activities | Bank Contribution |  |  | ### Local | Total | Total (%) |
| --- | --- | --- | --- | --- | --- | --- |
| 1. Component 1: Strengthening National AIDS Coordination | 137,000 |  |  | 20,000 | 157,000 | 17% |
| 2. Component 2:Stigma and discrimination reduction | 170,000 |  |  | 15,000 | 185,000 | 20% |
| 3. Component 3: Scaling up prevention | 383,000 |  |  | 70,000 | 453,000 | 48% |
| 4. Component 4: Administration | 58,500 |  |  | 85,000 | 143,500 | 15% |
| 5. Contingencies | 1,500 |  |  | 0 | 1,500 | 0% |
| TOTAL | 750,000 |  |  | 190,000 | 940,000 | 100% |
|  | 80% |  |  | 20% |  |  |

IV.	Execution

- 4.01	The Executing Agency, through the Project Execution Unit of Loan Contract 1537/OC-SU (Health Sector Facility) (PEU-HSF) will be responsible for the administration, procurement, and reporting to the Bank of Project activities.  The PEU-HSF will: (i) contract services and purchase goods identified in the Project; (ii) assist and monitor the execution of the Project; (iii) present periodic reports to the Ministry of Health (MOH) and the Bank on the progress of the execution; (iv) prepare and submit disbursement requests to the Bank and the corresponding justification of expenses; (v) prepare and submit to the Bank the final financial statements regarding Project’s expenses, and the semi-annual Revolving Fund Status Reports; and (vi) maintain an adequate documentation and filing system.

  - Existing staff of the PEU-HSF and the additional administrative support financed by the technical cooperation will perform the above-mentioned activities with the support of NAP staff and in collaboration with the Global Fund PEU. The Operational Regulations of Loan Contract 1537/OC-SU will govern the execution of this Project.

4.03	The PEU-HSF will operate under the direction of the Director for Health, the highest-ranking technical officer in the MOH. The Director of the NAP will be responsible for the overall technical coordination and oversight to the Project and day-to-day supervision of the consultants hired under the technical cooperation. The Steering Committee for HIV/AIDS, appointed to lead the implementation of the NSP, will be superseded by the NAC. The Steering Committee and the upcoming NAC will provide technical advice to the PEU-HSF and will ensure effective coordination between the activities financed under the technical cooperation and the other activities implemented as part of the NSP.

- V.	Monitoring and evaluation

- 5.01	The Logical Framework and the Project Performance Monitoring Report (PPMR) system for nonreimbursable technical cooperations will be used as tools for monitoring and evaluation of the pace of execution of this Project

- 5.02	Baseline data will be defined based on the information collected by the 1st module of the BSS. To permit the correct evaluation of the prevention projects financed under the technical cooperation project, the data collection of the first BSS module should take place before the implementation of the prevention projects related to the same at-risk population.

- 5.03	A technical mission will be conducted when the results of the first round of the BSS are available and/or at least five (5) proposals of prevention projects are submitted. The mission will define the baseline based on the results of the BSS models, refine the indicators for the Logical Framework, gauge progress in the execution of the Project, and will provide technical support as required.

5.04	A final evaluation will be conducted by an independent consultant hired specifically for this purpose and financed as part of the Project.