## PEP&POA
|  |  | October 2016 to September 2017 | [12 empty] | October 2017 to September 2018 | [12 empty] | October 2018 to September 2019 | [12 empty] | October 2019 to September 2020 | [12 empty] | October 2020 to September 2021 | [12 empty] | IDB COST (xUS$1000) | GoBH COST (xUS$1000)
ACTIVITY | IDB BUDGET (US$) | GoBH BUDGET (US$) | YEAR 1 | [12 empty] | YEAR 2 | [12 empty] | YEAR 3 | [12 empty] | YEAR 4 | [12 empty] | YEAR 5
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | Total | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | Total | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | Total | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | Total | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | Total
Contract Signing | bar: YEAR 1 1 to YEAR 1 3
Conditions Prior to First Disbursement | bar: YEAR 1 4 to YEAR 1 9
Hiring of PEU | bar: YEAR 1 1 to YEAR 1 3
PIU Contracts | 570000 |  |  |  |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 90 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 120 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 120 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 120 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 120 | 570
Procurement of Trainings | bar: YEAR 1 4 to YEAR 1 9
Execution of Trainings | 300000 |  | YEAR 1 10: 50; YEAR 1 11: 50; YEAR 1 12: 50 | 150 | [9 empty] | 50 | 50 | 50 | 150 | [39 empty] | 300
Procurement for Structuring of the management contract | bar: YEAR 1 4 to YEAR 1 9
Structuring of the management contract | 430000 |  | YEAR 1 10: 50; YEAR 1 11: 50; YEAR 1 12: 50 | 150 | 50 | [6 empty] | 50 | 50 | 50 | 50 | 30 | 280 | [39 empty] | 430
Civil Works Procurement
Execution of Works - IDB | 33000000 | [23 empty] | 2400 |  |  | 2400 | 850 | 850 | 850 | 850 | 850 | 850 | 850 | 850 | 850 | 850 | 850 | 850 | 10200 | 850 | 850 | 850 | 850 | 850 | 850 | 850 | 850 | 850 | 850 | 850 | 850 | 10200 | 850 | 850 | 850 | 850 | 850 | 850 | 850 | 850 | 850 | 850 | 850 | 850 | 10200 | 33000
Execution of Works - GoBH includes Project Management and engineering designs |  | 16700000 | [22 empty] | 550 | 425 | 425 | 1400 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 5100 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 5100 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 5100 |  | 16700
Procurement for Firefighting and Security Equipment | bar: YEAR 1 10 to YEAR 1 11
Suply for Firefighting and Security Equipment - GoBH |  | 2100000 | [16 empty] | 420 | [5 empty] | 1260 |  | 420 | 2100 | [40 empty] | 2100
ICAO Audit | 200000 | [61 empty] | 50 | 50 | 50 | 50 | 200 | 200
Procurement for Monitoring and Evaluation
Execution of Monitoring and Evaluation | 300000 | [34 empty] | 45 |  | 45 |  |  | 90 | [22 empty] | 75 | 60 | 75 | 210 | 300
Procurement of Financial Audit | bar: YEAR 1 10 to YEAR 1 12
Excecution of Financial Audit | 200000 | [21 empty] | 40 |  |  |  |  | 40 | [7 empty] | 40 |  |  |  |  | 40 | [7 empty] | 40 |  |  |  |  | 40 | [7 empty] | 40 |  |  |  | 40 | 80 | 200
TOTAL BUDGET | 35000000 | 18800000
Monthly Expense IDB | [5 empty] | 10 | 10 | 10 | 10 | 10 | 10 | 110 | 110 | 110 |  | 60 | 10 | 10 | 10 | 10 | 10 | 10 | 100 | 60 | 2510 | 110 | 90 |  | 860 | 860 | 860 | 860 | 860 | 860 | 860 | 945 | 860 | 905 | 860 | 860 |  | 860 | 860 | 860 | 860 | 860 | 860 | 860 | 900 | 860 | 860 | 860 | 860 |  | 860 | 860 | 860 | 860 | 860 | 860 | 860 | 900 | 910 | 985 | 970 | 1025 |  | 35000
Cumulative Expense IDB | [5 empty] | 10 | 20 | 30 | 40 | 50 | 60 | 170 | 280 | 390 |  | 450 | 460 | 470 | 480 | 490 | 500 | 510 | 610 | 670 | 3180 | 3290 | 3380 |  | 4240 | 5100 | 5960 | 6820 | 7680 | 8540 | 9400 | 10345 | 11205 | 12110 | 12970 | 13830 |  | 14690 | 15550 | 16410 | 17270 | 18130 | 18990 | 19850 | 20750 | 21610 | 22470 | 23330 | 24190 |  | 25050 | 25910 | 26770 | 27630 | 28490 | 29350 | 30210 | 31110 | 32020 | 33005 | 33975 | 35000
Annual Expense IDB |  |  | YEAR 1 12: 390 | [12 empty] | 2990 | [12 empty] | 10450 | [12 empty] | 10360 | [12 empty] | 10810 |  | 35000
Advance of Funds IDB |  |  | YEAR 1 10: 470 |  |  |  |  | 200 | [5 empty] | 5290 | [6 empty] | 5245 | [5 empty] | 5205 | [6 empty] | 5200 | [5 empty] | 5160 | [6 empty] | 5250 | [5 empty] | 2980 |  |  |  | 35000
Annual Disbursement Projection IDB |  |  | YEAR 1 12: 470 | [12 empty] | 5490 | [12 empty] | 10450 | [12 empty] | 10360 | [12 empty] | 8230 |  | 35000
Monthly Expense GoBH | [18 empty] | 420 | [5 empty] | 1810 | 425 | 845 |  | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 |  | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 |  | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 | 425 |  |  | 18800
Cumulative Expense GoBH | [25 empty] | 2655 | 3500 |  | 3925 | 4350 | 4775 | 5200 | 5625 | 6050 | 6475 | 6900 | 7325 | 7750 | 8175 | 8600 |  | 9025 | 9450 | 9875 | 10300 | 10725 | 11150 | 11575 | 12000 | 12425 | 12850 | 13275 | 13700 |  | 14125 | 14550 | 14975 | 15400 | 15825 | 16250 | 16675 | 17100 | 17525 | 17950 | 18375 | 18800
Annual Expense GoBH | [26 empty] | 3500 | [12 empty] | 5100 | [12 empty] | 5100 | [12 empty] | 5100 |  |  | 18800

## Products - Annual summary
|  | October 2016 to September 2017 (xUS$1000) | [12 empty] | October 2017 to September 2018 (xUS$1000) | [12 empty] | October 2018 to September 2019 (xUS$1000) | [12 empty] | October 2019 to September 2020 (xUS$1000) | [12 empty] | October 2020 to September 2021 (xUS$1000) | [12 empty] | COST (xUS$1000)
ACTIVITY | BUDGET (US$) | YEAR 1 | [12 empty] | YEAR 2 | [12 empty] | YEAR 3 | [12 empty] | YEAR 4 | [12 empty] | YEAR 5
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | Total | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | Total | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | Total | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | Total | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | Total
PRODUCT NORTH ELEUTHERA AIRPORT | 29000000 | [16 empty] | 210 | [5 empty] | 1790 | 200 | 390 | 2590 | 460 | 460 | 460 | 435 | 460 | 460 | 410 | 445 | 805 | 805 | 805 | 805 | 6810 | 637.5 | 637.5 | 637.5 | 637.5 | 637.5 | 637.5 | 637.5 | 637.5 | 637.5 | 637.5 | 637.5 | 637.5 | 7650 | 1005 | 995 | 995 | 995 | 995 | 995 | 995 | 995 | 995 | 995 | 995 | 995 | 11950 | 29000
PRODUCT EXUMA AIRPORT | 20400000 | [16 empty] | 210 | [5 empty] | 1790 | 200 | 390 | 2590 | 460 | 460 | 460 | 435 | 460 | 460 | 410 | 445 | 805 | 805 | 805 | 805 | 6810 | 637.5 | 637.5 | 637.5 | 637.5 | 637.5 | 637.5 | 637.5 | 637.5 | 637.5 | 637.5 | 637.5 | 637.5 | 7650 | 637.5 | 637.5 | 637.5 | 637.5 | 637.5 | 162 | [6 empty] | 3349.5 | 20399.5
0
PRODUCT MARSH HARBOUR AIRPORT | 200000 | [22 empty] | 50 |  |  | 50 |  |  |  | 50 |  |  | 100 | [5 empty] | 150 | [26 empty] | 200
PRODUCT TREASURE CAY AIRPORT | 2200000 | [22 empty] | 470 |  | 200 | 670 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 130 |  |  |  |  | 1530 | [26 empty] | 2200
PRODUCT CREATION OF THE PROGRAM IMPLEMENTATION UNIT Costs associated to the payments of the PIU | 570000 |  |  |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 90 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 120 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 120 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 120 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 120 | 570
PRODUCT NUMBER OF TRAININGS TO GoBH STAFF Costs associated to the execution of Trainings | 300000 | YEAR 1 10: 50; YEAR 1 11: 50; YEAR 1 12: 50 | 150 | [9 empty] | 50 | 50 | 50 | 150 | [39 empty] | 300
PRODUCT NUMBER OF MANAGEMENT CONTRACTS DRAFTED Costs associated to the structuring of the management contract The contract will be elaborated withint the implementation of the program and its delivery and signature will be undertaken by the end of the implementation of works | 430000 | YEAR 1 10: 50; YEAR 1 11: 50; YEAR 1 12: 50 | 150 | 50 | [6 empty] | 50 | 50 | 50 | 50 | 30 | 280 | [39 empty] | 430
PRODUCT ICAO Audit | 200000 | [60 empty] | 50 | 50 | 50 | 50 | 200 | 200
Execution of Monitoring and Evaluation | 300000 | [33 empty] | 45 |  | 45 |  |  | 90 | [22 empty] | 75 | 60 | 75 | 210 | 300
Excecution of Financial Audit | 200000 | [20 empty] | 40 |  |  |  |  | 40 | [7 empty] | 40 |  |  |  |  | 40 | [7 empty] | 40 |  |  |  |  | 40 | [7 empty] | 40 |  |  |  | 40 | 80 | 200
TOTAL BUDGET | 53800000 | [12 empty] | 390 | [12 empty] | 6490 | [12 empty] | 15550 | [12 empty] | 15460 | [12 empty] | 15909.5 | 53799.5