## Procurement Plan
PROCUREMENT PLAN INITIAL LOAD INFORMATION (ONGOING AND/OR LAST PRESENTED)
WORKS
Executing Agency: | Activity: | Additional Information: | Procurement Method (Select one of the options): | Lots Quantity: | Process Number: | Estimated Amount |  |  | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments - for UCS include selection method
[6 empty] | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount Counterpart %: |  |  | Specific Procurement notice | Contract Signature
GOODS
Executing Agency: | Activity: | Additional Information: | Procurement Method (Select one of the options): | Lots Quantity: | Process Number: | Estimated Amount |  |  | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments - for UCS include selection method
[6 empty] | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount Counterpart %: |  |  | Specific Procurement notice | Contract Signature
Office of the Cabinet | IT Equipment PMO Team (Laptops, Camera and Digital Accessories) |  | Shopping |  | 1.1.1.28b | 20000 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2017-10-01 | 2018-01-01
Office of the Cabinet | Furniture and Partitions for PMO Office |  | Shopping |  | 1.1.1.80 | 11000 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2017-07-01 | 2017-09-01
Office of the Cabinet | Flow Dedicated Internet for New Test Site and Project Team |  | Direct Contracting |  | 1.1.1.57 | 36000 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Ante | 2018-02-01 | 2018-02-01
Office of the Cabinet | Microsoft Licenses (OS -Datacenter, MSSql) - Production |  | Direct Contracting |  | 1.1.1.59b | 100000 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Ante | 2017-11-01 | 2017-12-01
Office of the Cabinet | Hardware and Software for Kiosks for 14 MDAs |  | Shopping |  | 1.1.1.2b | 95000 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2018-01-01 | 2018-03-01
Office of the Cabinet | ICT Norms, Polices and Standards - Management Software |  | Shopping |  | 2.1.3.1 | 14360 | 100 |  | Component 2 Information & Communication Technologies Management (ICTM), sub-component 2.1 Institutional strengthening of the new ICT governance framework | Ex-Post | 2018-01-01 | 2018-03-01
Office of the Cabinet | IT equipment |  | Shopping |  | 2.1.1.3 | 20000 | 100 |  | Component 2 Information & Communication Technologies Management (ICTM), sub-component 2.1 Institutional strengthening of the new ICT governance framework | Ex-Post | 2017-02-01 | 2017-04-01
Office of the Cabinet | Adobe Illustrator for Teams |  | Shopping |  | 2.3.1.6 | 396.43 | 100 |  | Component 2 Information & Communication Technologies Management (ICTM), sub-component 2.3 Establishment of a one-stop-shop for business registration | Ex-Post | 2017-11-01 | 2017-12-01
Office of the Cabinet | Resharper Subscription License |  | Direct Contracting |  | 2.3.1.5 | 1420.25 | 100 |  | Component 2 Information & Communication Technologies Management (ICTM), sub-component 2.3 Establishment of a one-stop-shop for business registration | Ex-Ante | 2017-11-01 | 2017-12-01
Office of the Cabinet | IT Equipment (MIND) |  | National Competitive Bidding |  | 3.3.2.2.1 | 105800 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.3 Procurement process efficiency improved | Ex-Post | 2017-12-01 | 2018-02-01
Office of the Cabinet | Communication (DVD, Online ) |  | National Competitive Bidding |  | 3.3.2.6 | 383283.2 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.3 Procurement process efficiency improved | Ex-Post | 2017-12-01 | 2018-02-01 | This activity will be broken down into smaller contracts neither of which will exceed $150,000.
Office of the Cabinet | Microsoft Software |  | Direct Contracting |  | 3.3.5.3.10 | 7000 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.3 Procurement process efficiency improved | Ex-Ante | 2017-11-01 | 2017-12-01
NON CONSULTING SERVICES
Executing Agency: | Activity: | Additional Information: | Procurement Method (Select one of the options): | Lots Quantity: | Process Number: | Estimated Amount |  |  | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments - for UCS include selection method
[6 empty] | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount Counterpart %: |  |  | Bidding Documents | Contract Signature
Office of the Cabinet | Hosting Service |  | National Competitive Bidding |  | 1.1.1.73 | 108000 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Ante | 2017-07-01 | 2017-10-01
Office of the Cabinet | Workshop - HCMES Training |  | Shopping |  | 1.1.1.74 | 30000 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2017-07-01 | 2017-08-01 | This activity will be broken down into a number of workshops.
Office of the Cabinet | Rental for DR Site |  | Direct Contracting |  | 1.1.1.75 | 18000 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Ante | 2017-09-01 | 2017-10-01
Office of the Cabinet | Workshop - Changement Lead |  | Shopping |  | 1.1.1.76 | 37116.22 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2017-09-01 | 2017-10-01
Office of the Cabinet | Workshop - PMO Team |  | Shopping |  | 1.1.1.74 | 5000 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2017-07-01 | 2017-08-01
Office of the Cabinet | Change Management Worshop - Facilitator |  | Direct Contracting |  | 1.1.1.69a | 50000 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Ante | 2017-11-01 | 2017-12-01
Office of the Cabinet | ICT Policy Management Workshop |  | Shopping |  | 2.1.2.2 | 21450 | 100 |  | Component 2 Information & Communication Technologies Management (ICTM), sub-component 2.1 Institutional strengthening of the new ICT governance framework | Ex-Post | 2017-12-01 | 2018-01-01
Office of the Cabinet | ICT Change Management Workshop - Facilitator |  | Direct Contracting |  | 2.1.1.1.4b | 625 | 100 |  | Component 2 Information & Communication Technologies Management (ICTM), sub-component 2.1 Institutional strengthening of the new ICT governance framework | Ex-Ante | 2017-11-01 | 2017-11-01
Office of the Cabinet | Study tour to observe successful implementation of SCS by other Governments |  | Direct Contracting |  | 2.4.1 | 25000 | 100 |  | Component 2 Information & Communication Technologies Management (ICTM), sub-component 2.4 Introduction of Shared Corporate Services | Ex-Ante | 2017-06-01 | 2017-07-01
Office of the Cabinet | Sensitisation Session - Procurement Law and Regulations |  | Shopping |  | 3.3.3.2 | 30000 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.3 Procurement Process Efficiency Improved | Ex-Post | 2017-12-01 | 2018-01-01
CONSULTING FIRMS
Executing Agency: | Activity: | Additional Information: | Procurement Method (Select one of the options): | Process Number: | Estimated Amount |  |  | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments - for UCS include selection method
[5 empty] | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount Counterpart %: |  |  | Specific Procurement notice | Contract Signature
Office of the Cabinet | HCMES Application Change Orders |  | Single Source Selection | 1.1.1.68 | 1200000 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Ante | 2017-09-01 | 2018-01-01
Office of the Cabinet | Change Management Consultancy |  | Quality and Cost Based Selection | 1.1.1.69 | 240000 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Ante | 2017-07-01 | 2017-10-01
Office of the Cabinet | Communications Consultancy |  | Quality and Cost Based Selection | 1.1.1.70 | 100000 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2017-07-01 | 2017-09-01
Office of the Cabinet | International Consultancy (Firm) - Standardisation of Processes and adopting to the software |  | Quality and Cost Based Selection | 1.1.1.71 | 300000 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Ante | 2017-04-01 | 2017-07-01
Office of the Cabinet | Trademark the Human Capital Enterprise System (HCMES) Name and Logo MyHR+ |  | Single Source Selection | 1.1.1.78 | 137.98 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Ante | 2017-03-01 | 2016-04-01
Office of the Cabinet | Training for SHRMD in HRM Units in Priority areas |  | Single Source Selection | 1.2.2 | 596700 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.2 Strengthening the Capacity of Strategic Human Resource Management Division (SHRMD) | Ex-Ante | 2017-05-01 | 2017-07-01 | This activity will be broken down into smaller contracts neither of which will exceed $500,000.
Office of the Cabinet | Trained support staff - ISO Training |  | Quality and Cost Based Selection | 2.1.1.4 | 272000 | 100 |  | Component 2 Information & Communication Technologies Management (ICTM), sub-component 2.1 Institutional strengthening of the new ICT governance framework | Ex-Ante | 2017-02-01 | 2017-06-01
Office of the Cabinet | Organization Assessment eGOVand MDAs |  | Quality and Cost Based Selection | 2.1.1.7 | 350000 | 100 |  | Component 2 Information & Communication Technologies Management (ICTM), sub-component 2.1 Institutional strengthening of the new ICT governance framework | Ex-Post | 2017-12-01 | 2018-03-01
Office of the Cabinet | To Assist Information and Communication Technologies (ICT) Jamaica with the Development of an Enterprise Architecture |  | Quality and Cost Based Selection | 2.1.1.8 | 150000 | 100 |  | Component 2 Information & Communication Technologies Management (ICTM), sub-component 2.1 Institutional strengthening of the new ICT governance framework | Ex-Post | 2017-12-01 | 2018-03-01
Office of the Cabinet | Design a Secure WAN Communication Backbone Infrastructure for the Government of Jamaica (GOVNET) |  | Quality and Cost Based Selection | 2.1.4 | 180000 | 100 |  | Component 2 Information & Communication Technologies Management (ICTM), sub-component 2.1 Institutional strengthening of the new ICT governance framework | Ex-Ante | 2016-07-01 | 2017-03-30
Office of the Cabinet | To Develop Schemes of Management Transformation of the Government Electrical Inspectorate into a Regulatory Entity |  | Quality and Cost Based Selection | 2.2.3 | 100000 | 100 |  | Component 2 Information & Communication Technologies Management (ICTM), sub-component 2.2 Streamlining the process of the GEI | Ex-Post | 2017-09-01 | 2017-12-01
Office of the Cabinet | Communications campaign |  | Quality and Cost Based Selection | 2.3.4 | 39000 | 100 |  | Component 2 Information & Communication Technologies Management (ICTM), sub-component 2.3 Establishment of a One-Stop-Shop for Business Registration | Ex-Post | 2017-03-01 | 2017-05-01
Office of the Cabinet | Developing and Implementing Shared Corporate Services |  | Quality and Cost Based Selection | 2.4.2. | 1443217.05 | 100 |  | Component 2 Information & Communication Technologies Management (ICTM), sub-component 2.4 Introduction of Shared Corporate Services | Ex-Ante | 2016-11-01 | 2017-04-01
Office of the Cabinet | Upgrade of the Government of Jamaica Internal Auditor's Community website |  | Quality and Cost Based Selection | 3.2.2.6 | 12000 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.2 Strengthening the Internal Audit System capacity | Ex-Post | 2017-12-01 | 2018-02-01
Office of the Cabinet | Evaluation Consultant |  | Quality and Cost Based Selection | 4.4 | 108000 | 100 |  | Component 4 Administration | Ex-Post | 2018-01-01 | 2018-03-01
INDIVIDUAL CONSULTANTS
Executing Agency: | Activity: | Additional Information: | Procurement Method (Select one of the options): | Process Number: | Estimated Amount |  |  | Estimated Number of Consultants: | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments - for UCS include selection method
[5 empty] | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount Counterpart %: |  |  |  | No Objection to TOR's | Contract Signature
Office of the Cabinet | Business Analyst (x2) |  | Comparison of Qualifications - National Individual Consultant | 1.1.1.82 | 116666.67 | 100 |  | 2 | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2017-12-01 | 2018-02-01
Office of the Cabinet | Change Management Officer (x2) |  | Comparison of Qualifications - National Individual Consultant | 1.1.1.83 | 116666.67 | 100 |  | 2 | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2017-12-01 | 2018-02-01
Office of the Cabinet | Systems Support Officer (x2) |  | Comparison of Qualifications - National Individual Consultant | 1.1.1.84 | 100000 | 100 |  | 2 | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2017-12-01 | 2018-02-01
Office of the Cabinet | Programmer (x2) |  | Comparison of Qualifications - National Individual Consultant | 1.1.1.85 | 100000 | 100 |  | 2 | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2017-12-01 | 2018-02-01
Office of the Cabinet | Communications Officer (x2) |  | Comparison of Qualifications - National Individual Consultant | 1.1.1.86 | 116666.67 | 100 |  | 2 | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2017-12-01 | 2018-02-01
Office of the Cabinet | Payroll Lead |  | Comparison of Qualifications - National Individual Consultant | 1.1.1.87 | 65000 | 100 |  | 1 | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2017-12-01 | 2018-02-01
| HR Lead |  | Comparison of Qualifications - National Individual Consultant | 1.1.1.88 | 65000 | 100 |  | 1 | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2017-12-01 | 2018-02-01
Office of the Cabinet | Change Management Lead |  | Comparison of Qualifications - National Individual Consultant | 1.1.1.63 | 78000 | 100 |  | 1 | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2016-07-01 | 2017-09-01
Office of the Cabinet | International Consultancy (organisational structure development of CIO's Office within MSTEM) |  | Comparison of Qualifications - International Individual Consultant | 2.1.1.2 | 157403.31 | 100 |  | 1 | Component 2 Information & Communication Technologies Management (ICTM), sub-component 2.1 Institutional strengthening of the new ICT governance framework | Ex-Ante | 2017-04-01 | 2017-12-01
Office of the Cabinet | Develop a Business Plan |  | Comparison of Qualifications - National Individual Consultant | 2.1.1.4 | 50000 | 100 |  | 1 | Component 2 Information & Communication Technologies Management (ICTM), sub-component 2.1 Institutional strengthening of the new ICT governance framework | Ex-Post | 2017-11-01 | 2018-01-01
Office of the Cabinet | To Assist Information and Communication Technologies (ICT) Jamaica with Technical Support for the Implementation of Open Data Initiative |  | Comparison of Qualifications - International Individual Consultant | 2.1.1.2 | 40000 | 100 |  | 1 | Component 2 Information & Communication Technologies Management (ICTM), sub-component 2.1 Institutional strengthening of the new ICT governance framework | Ex-Post | 2017-02-01 | 2017-06-01
Office of the Cabinet | Microsoft .Net Consultant |  | Single Source Selection | 2.3.1.2a | 90000 | 100 |  | 1 | Component 2 Information & Communication Technologies Management (ICTM), sub-component 2.3 Establishment of a One-Stop-Shop for Business Registration | Ex-Ante | 2017-05-01 | 2017-07-01
Office of the Cabinet | Facilitator - Business registration seminars and workshops |  | Comparison of Qualifications - National Individual Consultant | 2.3.3.1a | 10000 | 100 |  | 1 | Component 2 Information & Communication Technologies Management (ICTM), sub-component 2.3 Establishment of a One-Stop-Shop for Business Registration | Ex-Post | 2017-03-01 | 2017-08-01
Office of the Cabinet | Centralization of Legal Services - Project Management Executive |  | Comparison of Qualifications - National Individual Consultant | 2.4.6.1 | 41999.28 | 100 |  | 1 | Component 2 Information & Communication Technologies Management (ICTM), sub-component 2.4 Introduction of Shared Corporate Services | Ex-Post | June 1, 2017 | 2018-01-01
Office of the Cabinet | Centralization of Legal Services - Change Management Specialist |  | Comparison of Qualifications - National Individual Consultant | 2.4.6.2 | 31756.1 | 100 |  | 1 | Component 2 Information & Communication Technologies Management (ICTM), sub-component 2.4 Introduction of Shared Corporate Services | Ex-Post | June 6, 2017 | 2018-02-01
Office of the Cabinet | Centralization of Legal Services - Project Manager Legal |  | Comparison of Qualifications - National Individual Consultant | 2.4.6.3 | 31756.1 | 100 |  | 1 | Component 2 Information & Communication Technologies Management (ICTM), sub-component 2.4 Introduction of Shared Corporate Services | Ex-Post | June 1, 2017 | 2018-02-01
Office of the Cabinet | Centralization of Legal Services - Human Resource |  | Comparison of Qualifications - National Individual Consultant | 2.4.6.4 | 27731 | 100 |  | 1 | Component 2 Information & Communication Technologies Management (ICTM), sub-component 2.4 Introduction of Shared Corporate Services | Ex-Post | June 1, 2017 | 2018-02-01
Office of the Cabinet | Centralization of Legal Services - Administrative Assistant |  | Comparison of Qualifications - National Individual Consultant | 2.4.6.5 | 9191.7 | 100 |  | 1 | Component 2 Information & Communication Technologies Management (ICTM), sub-component 2.4 Introduction of Shared Corporate Services | Ex-Post | June 1, 2017 | 2018-02-01
Office of the Cabinet | Procurement Specialist - NPPC |  | Comparison of Qualifications - National Individual Consultant | 3.3.2.4 | 120000 | 100 |  | 1 | Component 3 Control Systems and Accountability, sub-component 3.3 Procurement process efficiency improved | Ex-Post | 2017-11-01 | 2018-01-01
Office of the Cabinet | Procurement Specialist - PAPU |  | Comparison of Qualifications - National Individual Consultant | 3.3.2.5 | 50000 | 100 |  | 1 | Component 3 Control Systems and Accountability, sub-component 3.3 Procurement process efficiency improved | Ex-Post | 2017-11-01 | 2018-01-01
Office of the Cabinet | Impact Evaluation Principal Investigator |  | Comparison of Qualifications - International Individual Consultant | 4.13 | 53600 | 100 |  | 1 | Component 4 Administration | Ex-Post |  | 2017-04-01
Office of the Cabinet | To support implementation of an integrated communication and engagement strategy in support of the Public Sector Transformation and Modernisation Programme - Communication Lead |  | Comparison of Qualifications - National Individual Consultant | 4.18 | 43000 | 100 |  | 1 | Component 4 Administration | Ex-Post | 2017-08-01 | 2018-01-01
Office of the Cabinet | Procurement Officer |  | Comparison of Qualifications - National Individual Consultant | 4.17 | 26923.08 | 100 |  | 1 | Component 4 Administration | Ex-Post | August 14, 2017 | 2018-03-01
TRAINING
Executing Agency: | Activity: | Additional Information: | Procurement Method (Select one of the options): | Process Number: | Estimated Amount |  |  | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments - for UCS include selection method
[5 empty] | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount Counterpart %: |  |  | Annual Training Plan (ATP) | End of Activity
TRANSFERS
Executing Agency: | Transfer Purpose: | Additional Information: | Process Number: | Estimated Amount |  |  | Associated Component: | Estimated Number of Transfers: | Dates |  | Comments - for UCS include selection method
|  |  |  | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount Counterpart %: |  |  | Contract Signature | Transfer Date
AWARDED CONTRACTS
GOODS
Executing Agency: | Activity: | Additional Information: | Procurement Method (Select one of the options): | Lots Quantity: | Process Number: | Estimated Amount |  |  | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments - for UCS include selection method
[6 empty] | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount Counterpart %: |  |  | Specific Procurement notice | Contract Signature
Office of the Cabinet | PMO Team (Project Expenses) - Computer |  | Shopping |  | 1.1.1.56 | 5000 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2017-02-01 | 2017-03-01 | awarded
Office of the Cabinet | Relocation of Production Server for Hosting Service |  | Shopping |  | 1.1.1.55b | 124.03 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2017-07-01 | 2017-08-01 | Awarded
Office of the Cabinet | Hardware and Software for Kiosks for 14 MDA's |  | National Competitive Bidding |  | 1.1.1.2a | 55313.98 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2017-07-01 | 2017-09-01 | Awarded
Office of the Cabinet | Hardware for Disaster Recovery |  | International Competitive Bidding |  | 1.1.1.60a | 53600.51 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Ante | 2017-04-01 | 2017-11-01 | Awarded
Office of the Cabinet | Load Balancer |  | National Competitive Bidding |  | 1.1.1.61 | 11051.81 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2017-07-01 | 2017-11-01 | Awarded
Office of the Cabinet | Expansion of Internet Connectivity - SSL Certificates |  | Direct Contracting |  | 1.1.1.62 | 4575 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Ante | 2017-09-01 | 2017-12-01 | Awarded
Office of the Cabinet | Expansion of Internet Connectivity - Dedicated Internet Access Service |  | Shopping |  | 1.1.1.62.2 | 49545.79 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Ante | 2017-07-01 | 2017-08-01 | Awarded
Office of the Cabinet | Port Cisco Switch, SR Fiber Transceivers, LC Fiber Cables, Fabric 10Gb Switch |  | Shopping |  | 1.1.1.62.3 | 30971.81 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2017-09-01 | 2017-12-01 | awarded
Office of the Cabinet | Expansion of Internet Connectivity - Unifi Switch, 16 Port, 10 Gigabit |  | Shopping |  | 1.1.1.62.4 | 1897.59 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2017-10-01 | 2017-11-01 | awarded
Office of the Cabinet | PMO Team (Test Site Installation - IT Equipment) |  | Shopping |  | 1.1.1.55a and c | 13785.13 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2017-07-01 | 2017-09-01 | awarded
Office of the Cabinet | Novelties/promotional literature (desk caddies, mouse pads, paperclip holders, posters etc.) |  | Shopping |  | 1.1.1.77a | 95000 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2017-02-01 | 2017-03-01 | Awarded
Office of the Cabinet | Procurement for Enterprise HCMES/Payroll Software Hardware |  | International Competitive Bidding |  | 1.1.1.10 | 4737625.52 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Ante | 2015-05-01 | December 30, 2015 | Awarded
Office of the Cabinet | IT Equipment for PMO Team (server, computer) |  | Shopping |  | 1.1.1.11 | 14389.91 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2015-12-01 | 2016-01-01 | Awarded
Office of the Cabinet | IT Equipment for PMO Team (laptop) |  | Shopping |  | 1.1.1.12 | 13675.93 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2015-12-01 | 2016-01-01 | Awarded
Office of the Cabinet | IT Equipment for PMO Team (printer) |  | Shopping |  | 1.1.1.13 | 12255.21 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2015-12-01 | 2016-01-01 | Awarded
Office of the Cabinet | Supply of Modular Furniture |  | Shopping |  | 1.1.1.14 | 38021.35 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2016-02-01 | March 24, 2016 | Awarded
Office of the Cabinet | Supply of Microsoft Software |  | Direct Contracting |  | 1.1.1.15 | 783.66 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Ante | 2016-02-01 | March 30, 2016 | Awarded
Office of the Cabinet | Renovation of PMO Office |  | Shopping |  | 1.1.1.16 | 10708.4 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2016-02-01 | April 7, 2016 | Awarded
Office of the Cabinet | Electrical Services |  | Shopping |  | 1.1.1.17 | 3222.86 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2016-02-01 | April 11, 2016 | Awarded
Office of the Cabinet | Cabling of Office Space (PMO) |  | Shopping |  | 1.1.1.18 | 4456.24 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2016-02-01 | May 18, 2016 | Awarded
Office of the Cabinet | Supply of ten (10) Lenovo Idea pad laptop - HCMES Training |  | Shopping |  | 1.1.1.19 | 3220.57 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2016-10-01 | 2016-10-01 | Awarded
Office of the Cabinet | Scanners (HCMES) |  | Shopping |  | 1.1.1.20 | 25507.53 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2016-06-01 | 2016-08-01 | Awarded
Office of the Cabinet | Relocation of Printer |  | Direct Contracting |  | 1.1.1.21 | 86.61 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Ante | 2016-07-01 | 2016-07-01 | Awarded
Office of the Cabinet | Supplying Stationery & Office Supplies |  | Shopping |  | 1.1.1.22 | 1262.46 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2016-07-01 | 2016-07-01 | Awarded
Office of the Cabinet | Supply of Modular Furniture |  | Direct Contracting |  | 1.1.1.23 | 664 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Ante | 2016-08-01 | 2016-08-01 | Awarded
Office of the Cabinet | Symc Endpoint Protection |  | Direct Contracting |  | 1.1.1.24 | 201 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Ante | 2016-08-01 | 2016-08-01 | Awarded
Office of the Cabinet | SSL Certificates |  | Direct Contracting |  | 1.1.1.25 | 1647 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Ante | 2016-07-01 | 2016-07-01 | Awarded
Office of the Cabinet | Supply of Desk Phones |  | National Competitive Bidding |  | 1.1.1.26 | 4784.3 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2016-08-01 | 2016-08-01 | Awarded
Office of the Cabinet | Supply of Firewall |  | National Competitive Bidding |  | 1.1.1.27 | 3033 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2016-08-01 | 2016-08-01 | Awarded
Office of the Cabinet | Supply of laptop, bag, cable and mouse |  | Shopping |  | 1.1.1.28a | 4041 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2016-10-01 | 2016-10-01 | Awarded
Office of the Cabinet | Microsoft Software |  | Direct Contracting |  | 1.1.1.29 | 16160.94 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Ante | 2016-05-01 | 2016-06-01 | Awarded
Office of the Cabinet | Microsoft Software |  | Direct Contracting |  | 1.1.1.30 | 41364.54 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Ante | 2016-10-01 | 2016-10-01 | Awarded
Office of the Cabinet | Network Equipment |  | National Competitive Bidding |  | 1.1.1.31 | 13565 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2016-08-01 | 2016-09-01 | Awarded
Office of the Cabinet | Office Supplies - Kettle, Refrigerator and Microwave |  | Shopping |  | 1.1.1.32 | 685 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2016-10-01 | 2016-10-01 | Awarded
Office of the Cabinet | PMO Team (AC acquisitionl) |  | Direct Contracting |  | 1.1.1.33 | 17272 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Ante | 2016-02-01 | 2016-09-01 | Awarded
Office of the Cabinet | Nvivo Software |  | Direct Contracting |  | 1.1.1.34 | 2622 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Ante | 2016-11-01 | 2016-11-01 | Awarded
Office of the Cabinet | Projector |  | Shopping |  | 1.1.1.35 | 3861 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2016-07-01 | 2016-11-01 | Awarded
Office of the Cabinet | Office Supplies for PMO |  | Shopping |  | 1.1.1.36 | 468 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2016-10-01 | 2016-10-01 | Awarded
Office of the Cabinet | Supplying Stationery & Office Supplies |  | Shopping |  | 1.1.1.37 | 1262.46 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2016-10-01 | 2016-10-01 | Awarded
Office of the Cabinet | Supply of monitors |  | National Competitive Bidding |  | 1.1.1.38 | 2363.32 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2016-10-01 | 2016-12-01 | Awarded
Office of the Cabinet | Supply of Docking Stations |  | National Competitive Bidding |  | 1.1.1.39 | 769.89 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2016-10-01 | 2016-12-01 | Awarded
Office of the Cabinet | Supply of Personal Computers |  | National Competitive Bidding |  | 1.1.1.40 | 16190.16 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2016-10-01 | 2016-12-01 | Awarded
Office of the Cabinet | Supply of Fitness Tracker for the HCMES Name and Logo Competition |  | Shopping |  | 1.1.1.53 | 71.57 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2017-01-01 | 2017-02-01 | Awarded
Office of the Cabinet | Supply of Tablet for the HCMES Name and Logo Competition |  | Shopping |  | 1.1.1.54 | 88.37 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2017-01-01 | 2017-02-01 | Awarded
Office of the Cabinet | Microsoft Licenses (OS -Datacenter, MSSql) - Production |  | Direct Contracting |  | 1.1.1.59a | 24000 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Ante | 2017-02-01 | 2017-08-01 | Awarded
Office of the Cabinet | Ventilation Grills for Securing Computer Equipment |  | Direct Contracting |  | 2.3.2.1f | 386.1 | 100 |  | Component 2 Information & Communication Technologies Management (ICTM), sub-component 2.3 Establishment of a one-stop-shop for business registration | Ex-Ante | 2017-08-01 | 2017-09-01 | Awarded
Office of the Cabinet | IT equipment (Kiosks ) |  | Shopping |  | 2.3.2.1e | 8615.5 | 100 |  | Component 2 Information & Communication Technologies Management (ICTM), sub-component 2.3 Establishment of a one-stop-shop for business registration | Ex-Post | 2017-02-01 | 2017-03-01 | awarded
Office of the Cabinet | ICT vendor (2 servers, server software, backup and recovery power systems) |  | National Competitive Bidding |  | 2.3.1.4 | 75000 | 100 |  | Component 2 Information & Communication Technologies Management (ICTM), sub-component 2.3 Establishment of a one-stop-shop for business registration | Ex-Ante | 2015-03-01 | 2015-05-01 | awarded
Office of the Cabinet | Supply of Computers |  | National Competitive Bidding |  | 2.3.2.1a | 15931.92 | 100 |  | Component 2 Information & Communication Technologies Management (ICTM), sub-component 2.3 Establishment of a one-stop-shop for business registration | Ex-Post | January 5, 2016 | February 29, 2016 | awarded
Office of the Cabinet | Supply of Signature Pads |  | National Competitive Bidding |  | 2.3.2.1b | 7213.14 | 100 |  | Component 2 Information & Communication Technologies Management (ICTM), sub-component 2.3 Establishment of a one-stop-shop for business registration | Ex-Post | April 11, 2016 | June 30, 2016 | awarded
Office of the Cabinet | Supply of Scanners |  | National Competitive Bidding |  | 2.3.2.1c | 14800 | 100 |  | Component 2 Information & Communication Technologies Management (ICTM), sub-component 2.3 Establishment of a one-stop-shop for business registration | Ex-Post | April 11, 2016 | 2016-06-01 | awarded
Office of the Cabinet | Supply of Signature Pads Stand |  | Direct Contracting |  | 2.3.2.1d | 3241.55 | 100 |  | Component 2 Information & Communication Technologies Management (ICTM), sub-component 2.3 Establishment of a one-stop-shop for business registration | Ex-Ante | 2016-08-01 | 2016-10-01 | awarded
Office of the Cabinet | Projectors and LED Smart Screen Televisions |  | National Competitive Bidding |  | 3.1..1.2b | 12054.66 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.1 Strengthening the AGD's capacity for Performance Audit and Information Technology Audit | Ex-Ante | 2014-10-01 | 2015-03-01 | Awarded
Office of the Cabinet | Purchase of Laptops for training Contractor: Management Control Systems |  | International Competitive Bidding |  | 3.1.1.2a | 38315.2 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.1 Strengthening the AGD's capacity for Performance Audit and Information Technology Audit | Ex-Ante | 2014-08-01 | 2015-01-01 | Awarded
Office of the Cabinet | Purchase of Laptops for training Contractor: Management Control Systems |  | International Competitive Bidding |  | 3.1.4.1a | 38315.2 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.1 Strengthening the AGD's capacity for Performance Audit and Information Technology Audit | Ex-Ante | 2014-08-01 | 2015-01-01 | Awarded
Office of the Cabinet | Caseware Software Contractor: Caseware International |  | Direct Contracting |  | 3.1.4.2 | 68905 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.1 Strengthening the AGD's capacity for Performance Audit and Information Technology Audit | Ex-Ante | 2016-11-01 | 2016-11-01 | Awarded
Office of the Cabinet | Supply of Scanners |  | National Competitive Bidding |  | 3.1.5.3 | 4024.84 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.1 Strengthening the AGD's capacity for Performance Audit and Information Technology Audit | Ex-Post | 2016-09-01 | 2016-11-01 | Awarded
Office of the Cabinet | Supply of Laptops Contractor: Lan Integrators |  | National Competitive Bidding |  | 3.1.5.3 | 19429.85 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.1 Strengthening the AGD's capacity for Performance Audit and Information Technology Audit | Ex-Post | 2016-09-01 | 2016-12-01 | Awarded
Office of the Cabinet | Supply of Computers |  | National Competitive Bidding |  | 3.1.5.3 | 4053.96 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.1 Strengthening the AGD's capacity for Performance Audit and Information Technology Audit | Ex-Post | 2016-09-01 | 2016-12-01 | Awarded
Office of the Cabinet | Sever and SAN upgrade |  | National Competitive Bidding |  | 3.1.5.4 | 7118 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.1 Strengthening the AGD's capacity for Performance Audit and Information Technology Audit | Ex-Post | 2016-11-01 | 2016-12-01 | Awarded
Office of the Cabinet | IT Equipment - Laptops Contractor: Appliance Traders Limited |  | International Competitive Bidding |  | 3.2.2.1 | 76472.28 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.2 Strengthening the Internal Audit System capacity | Ex-Ante | 2014-08-01 | 2015-01-01 | Awarded
Office of the Cabinet | Server Contractor: Royale Computers and Accessories Limited |  | National Competitive Bidding |  | 3.2.2.2a | 33414 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.2 Strengthening the Internal Audit System capacity | Ex-Ante | 2015-01-01 | 2015-04-01 | Awarded
Office of the Cabinet | Supply of HP upgrade License applied to SAN Switch at eGov Jamaica Limited in respect of Teammate (Royale Computers & Accessories) |  | Direct Contracting |  | 3.2.2.2f | 4135.96 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.2 Strengthening the Internal Audit System capacity | Ex-Ante | 2015-05-01 | 2015-05-01 | Awarded
Office of the Cabinet | Storage Area Network Contractor: Digicel (Jamaica) Limited |  | Direct Contracting |  | 3.2.2.2b | 69583.59 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.2 Strengthening the Internal Audit System capacity | Ex-Ante | 2015-01-01 | 2015-04-01 | Awarded
Office of the Cabinet | Microsoft Software Contractor: Ministry of Science, Environment and Technology |  | Direct Contracting |  | 3.2.2.2c | 15357.54 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.2 Strengthening the Internal Audit System capacity | Ex-Ante | 2015-05-01 | 2015-05-01 | Awarded
Office of the Cabinet | TeamMate Software Contractor: Wolters Kluwer, Boston |  | Direct Contracting |  | 3.2.2.2e | 296661 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.2 Strengthening the Internal Audit System capacity | Ex-Ante | 2014-09-01 | 2014-12-01 | Awarded
Office of the Cabinet | Supply of VPN Licenses for MOFPS Contractor: Fujitsu |  | National Competitive Bidding |  | 3.2.2.4 | 170.3 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.2 Strengthening the Internal Audit System capacity | Ex-Post | 2016-04-01 | 2016-07-01 | Awarded
Office of the Cabinet | Supply of Projector |  | National Competitive Bidding |  | 3.2.4.2 | 1070.94 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.2 Strengthening the Internal Audit System capacity | Ex-Post | 2016-09-01 | 2016-12-01 | Awarded
Office of the Cabinet | Supply of Laptops Contractor: MC Systems |  | National Competitive Bidding |  | 3.2.4.3 | 30931.24 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.2 Strengthening the Internal Audit System capacity | Ex-Post | 2016-09-01 | 2016-12-01 | Awarded
Office of the Cabinet | Symantec Endpoint Protection |  | National Competitive Bidding |  | 3.2.2.2 | 170.28 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.2 Strengthening the Internal Audit System capacity | Ex-Post | 2015-01-31 | 2015-05-05 | Awarded
Office of the Cabinet | Supply of server Contractor: Massy Technology |  | International Competitive Bidding |  | 3.3.5.3.1 | 203700.04 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.3 Procurement process efficiency improved | Ex-Ante | 2016-10-01 | 2016-12-01 | Awarded
Office of the Cabinet | supply of microsoft software products |  | Direct Contracting |  | 3.3.5.3.2 | 15441 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.3 Procurement process efficiency improved | Ex-Ante | 2016-11-01 | 2016-12-01 | Awarded
Office of the Cabinet | Adobe Software |  | Shopping |  | 3.3.5.3.3 | 1207.06 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.3 Procurement process efficiency improved | Ex-Post | 2016-11-01 | 2016-12-01 | Awarded
Office of the Cabinet | Supply of server Contractor: Massy Technology |  | National Competitive Bidding |  | 3.3.5.3.4 | 41853.82 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.3 Procurement process efficiency improved | Ex-Post | 2016-10-01 | 2016-12-01 | Awarded
Office of the Cabinet | Supply of Computers Contractor: Productive Business Solutions |  | National Competitive Bidding |  | 3.3.5.3.5 | 41395.77 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.3 Procurement process efficiency improved | Ex-Post | 2016-10-01 | 2016-12-01 | Awarded
Office of the Cabinet | Supply of Network Equipment Contractor: Massy Technology |  | National Competitive Bidding |  | 3.3.5.3.6 | 27604.39 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.3 Procurement process efficiency improved | Ex-Post | 2016-10-01 | 2016-12-01 | Awarded
Office of the Cabinet | Supply of Printer Contractor: Copiers and Consumables |  | National Competitive Bidding |  | 3.3.5.3.7 | 47990.62 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.3 Procurement process efficiency improved | Ex-Post | 2016-10-01 | 2016-12-01 | Awarded
Office of the Cabinet | Supply of Projector Contractor: Massy Technology |  | National Competitive Bidding |  | 3.3.5.3.8 | 15433.7 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.3 Procurement process efficiency improved | Ex-Post | 2016-10-01 | 2016-12-01 | Awarded
Office of the Cabinet | Supply of UPS Contractor: Modern Power & Cooling |  | National Competitive Bidding |  | 3.3.5.3.9 | 6623.59 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.3 Procurement process efficiency improved | Ex-Post | 2016-10-01 | 2016-12-01 | Awarded
Office of the Cabinet | e-tendering software functioning at MoF Contractor: European Dynamics |  | Direct Contracting |  | 3.3.5.2 | 1340000 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.3 Procurement process efficiency improved | Ex-Ante | 2016-03-01 | 2016-12-01 | Awarded
Office of the Cabinet | Conference Package |  | Shopping |  | 3.3.3.1 | 14772 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.3 Procurement process efficiency improved | Ex-Post | 2016-10-01 | 2016-12-01 | Awarded
Office of the Cabinet | Stenotype Machines |  | Direct Contracting |  | 3.4.2.4.2 | 45952 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.4 Enhancing Parliament´s oversight role | Ex-Ante | 2016-10-01 | 2016-10-01 | Awarded
Office of the Cabinet | STATA Software |  | Direct Contracting |  | 3.4.2.5 | 1900 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.4 Enhancing Parliament´s oversight role | Ex-Ante | 2016-11-01 | 2016-11-01 | Awarded
Office of the Cabinet | Supply of furniture Contractor: Corporate Interior |  | Shopping |  | 3.4.2.2.1 | 18367.15 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.4 Enhancing Parliament´s oversight role | Ex-Post | 2016-07-01 | 2016-12-01 | Awarded
Office of the Cabinet | Supply of furniture |  | Shopping |  | 3.4.2.2.1 | 2801.83 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.4 Enhancing Parliament´s oversight role | Ex-Post | 2016-07-01 | 2016-12-01 | Awarded
Office of the Cabinet | Microsoft Office Professional Plus |  | Direct Contracting |  | 3.4.2.2.7 | 2554.56 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.4 Enhancing Parliament´s oversight role | Ex-Ante | 2016-12-01 | 2016-12-01 | Awarded
Office of the Cabinet | Supply of Desktop |  | Shopping |  | 3.4.2.2.2 | 10508.35 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.4 Enhancing Parliament´s oversight role | Ex-Post | 2016-10-01 | 2016-12-01 | Awarded
Office of the Cabinet | Supply of Laptop |  | Shopping |  | 3.4.2.2.2 | 11090.45 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.4 Enhancing Parliament´s oversight role | Ex-Post | 2016-10-01 | 2016-12-01 | Awarded
Office of the Cabinet | Supply of Server |  | Shopping |  | 3.4.2.2.2 | 9650.05 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.4 Enhancing Parliament´s oversight role | Ex-Post | 2016-10-01 | 2016-12-01 | Awarded
Office of the Cabinet | Supply of LED TV |  | Shopping |  | 3.4.2.2.2 | 1878.41 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.4 Enhancing Parliament´s oversight role | Ex-Post | 2016-10-01 | 2016-12-01 | Awarded
Office of the Cabinet | Office Supplies (Refrigerator) |  | Shopping |  | 3.4.2.2.6 | 334.14 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.4 Enhancing Parliament´s oversight role | Ex-Post | 2016-12-01 | 2016-12-01 | Awarded
Office of the Cabinet | Office Supplies (Kettle) |  | Shopping |  | 3.4.2.2.6 | 138.08 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.4 Enhancing Parliament´s oversight role | Ex-Post | 2016-12-01 | 2016-12-01 | Awarded
Office of the Cabinet | Supply of Binds |  | Shopping |  | 3.4.2.2.5 | 655.17 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.4 Enhancing Parliament´s oversight role | Ex-Post | 2016-12-01 | 2016-12-01 | Awarded
Office of the Cabinet | Supply of Printer |  | Shopping |  | 3.4.2.2.2 | 2736.34 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.4 Enhancing Parliament´s oversight role | Ex-Post | 2016-12-01 | 2016-12-01 | Awarded
Office of the Cabinet | Supply of Printers for the Office of the Cabinet |  | National Competitive Bidding |  | 4.5 | 24106.14 | 100 |  | Component 4 Administrative | Ex-Post | 2015-11-01 | January 5, 2016 | Awarded
Office of the Cabinet | Supply of Computers for the Office of the Cabinet |  | National Competitive Bidding |  | 4.6 | 73145 | 100 |  | Component 4 Administrative | Ex-Post | 2016-11-01 | 2017-02-01 | Awarded
Office of the Cabinet | CUG Phones for Project Execution Unit |  | Shopping |  | 4.12 | 4976.36 | 100 |  | Component 4 Administrative | Ex-Post | 2017-02-01 | 2017-08-01 | Awarded
NON CONSULTING SERVICES
Executing Agency: | Activity: | Additional Information: | Procurement Method (Select one of the options): | Lots Quantity: | Process Number: | Estimated Amount |  |  | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments - for UCS include selection method
[6 empty] | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount Counterpart %: |  |  | Bidding Documents | Contract Signature
Office of the Cabinet | Videotaping and Editing |  | Shopping |  | 1.1.1.41 | 469 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2016-08-01 | 2016-08-01 | awarded
Office of the Cabinet | Training Facility Rental |  | Direct Contracting |  | 1.1.1.42 | 629 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2016-08-01 | 2016-08-01 | awarded
Office of the Cabinet | Accommodation - HR Operating Model Workshop |  | Shopping |  | 1.1.1.43 | 27990 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2016-06-01 | 2016-06-01 | awarded
Office of the Cabinet | Advertisement for Change Management Specialist |  | Direct Contracting |  | 1.1.1.44 | 295.98 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2016-08-01 | 2016-08-01 | awarded
Office of the Cabinet | Hosting of Communication Strategy for the sensitization of new integrated HR & Payroll System |  | Shopping |  | 1.1.1.45 | 1885.38 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2016-10-01 | 2016-10-01 | awarded
Office of the Cabinet | Catering Services for Fifteen (15) days training of Human Capital Management Enterprise System (HCMES) with Payroll. |  | Shopping |  | 1.1.1.46 | 7630 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2016-10-01 | 2016-10-01 | awarded
Office of the Cabinet | Design and Print Posters |  | Direct Contracting |  | 1.1.1.47 | 462 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2016-10-01 | 2016-10-01 | awarded
Office of the Cabinet | Workshop - HR training |  | Shopping |  | 1.1.1.48 | 439.65 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2016-10-01 | 2016-10-01 | awarded
Office of the Cabinet | Catering Services for HR transition meeting |  | Shopping |  | 1.1.1.49 | 297.63 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2016-10-01 | 2016-10-01 | awarded
Office of the Cabinet | Workshop |  | Shopping |  | 1.1.1.50 | 86.25 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2016-10-01 | 2016-10-01 | awarded
Office of the Cabinet | HCMES Training - Food |  | Shopping |  | 1.1.1.51 | 8819 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2016-10-01 | 2016-10-01 | awarded
Office of the Cabinet | Workshop |  | Shopping |  | 1.1.1.52 | 10006.36 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2017-01-01 | 2017-02-01 | awarded
Office of the Cabinet | Change Management Workshop |  | Shopping |  | 1.1.1.76a | 7041.72 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2017-10-01 | 2017-11-01 | awarded
Office of the Cabinet | Change Management Workshop |  | Shopping |  | 1.1.1.76b | 1842.06 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2017-11-01 | 2017-12-01 | awarded
Office of the Cabinet | Change Management Workshop |  | Shopping |  | 1.1.1.76c | 2409.12 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2017-12-01 | 2017-12-01 | awarded
Office of the Cabinet | Change Management - Facilitator |  | Shopping |  | 1.1.1.76d | 476.19 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2017-12-01 | 2017-12-01 | awarded
Office of the Cabinet | Trademark the Name and Logo for HCMES/ Payroll System |  | Direct Contracting |  | 1.1.1.79 | 137.98 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Ante | 2017-03-01 | 2017-03-01 | awarded
Office of the Cabinet | CUG |  | Direct Contracting |  | 1.1.1.58 | 7752 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2016-09-01 | 2016-10-01 | awarded
Office of the Cabinet | Workshop - Communication |  | Shopping |  | 1.1.1.78a | 22100 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2017-02-01 | 2017-03-01 | Awarded
Office of the Cabinet | Workshop - Communication |  | Shopping |  | 1.1.1.78b | 2409.12 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2017-11-01 | 2017-12-01 | Awarded
Office of the Cabinet | Workshop on international experiences on workforce planning delivered - Human Resource Mangement Conference |  | Shopping |  | 1.2.1 | 40598.49 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.2 Strengthening the Capacity of Strategic Human Resource Management Division (SHRMD) | Ex-Post | 2017-07-01 | 2017-07-01 | Awarded
Office of the Cabinet | Workshop |  | Direct Contracting |  | 1.2 | 394 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.2 Strengthening the Capacity of Strategic Human Resource Management Division (SHRMD) | Ex-Post | 2016-08-01 | 2016-08-01 | awarded
Office of the Cabinet | Workshop |  | Shopping |  | 1.2.3 | 120.93 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.2 Strengthening the Capacity of Strategic Human Resource Management Division (SHRMD) | Ex-Post | 2017-01-01 | 2017-01-01 | awarded
Office of the Cabinet | Workshop |  | Shopping |  | 1.2.3 | 2297.49 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.2 Strengthening the Capacity of Strategic Human Resource Management Division (SHRMD) | Ex-Post | 2017-01-01 | 2017-01-01 | awarded
Office of the Cabinet | Training facility rental -Workshops |  | Shopping |  | 2.1.1.1.4a | 10000 | 100 |  | Component 2 Information & Communication Technologies Management (ICTM), sub-component 2.1 Institutional strengthening of the new ICT governance framework | Ex-Post | 2015-06-01 | 2015-08-01 | awarded
Office of the Cabinet | Training facility rental -Workshops |  | Shopping |  | 2.1.1.1.4a | 3241 | 100 |  | Component 2 Information & Communication Technologies Management (ICTM), sub-component 2.1 Institutional strengthening of the new ICT governance framework | Ex-Post | 2016-09-01 | 2016-09-01 | awarded
Office of the Cabinet | Training Facility Rental |  | Shopping |  | 3.2.4.1b | 10000 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.2 Strengthening the Internal Audit System capacity | Ex-Post | 2015-10-01 | 2015-10-01 | awarded
Office of the Cabinet | Hosting Services for TeamMate Software |  | Direct Contracting |  | 3.2.2.2d | 10859.8 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.2 Strengthening the Internal Audit System capacity | Ex-Ante | 2015-02-01 | 2015-03-01 | awarded
Office of the Cabinet | IT support/maintenance for additional yrs for 240 licences Contractor: PricewaterhouseCoopers |  | Direct Contracting |  | 3.2.2.5 | 179250 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.2 Strengthening the Internal Audit System capacity | Ex-Ante | 2016-10-01 | 2016-12-01 | awarded
Office of the Cabinet | Hosting Service for TeamMate Software Contractor: EGOV Jamaica td. |  | Direct Contracting |  | 3.2.2.3 | 17860 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.2 Strengthening the Internal Audit System capacity | Ex-Ante | 2016-10-01 | 2016-12-01 | awarded
Office of the Cabinet | Venue Rental for sensitization and awareness campaign Contractor: Urban Development Corporation |  | Shopping |  | 3.3.3.1 | 20,318.95 EUR15,277.41 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.3 Procurement Process Efficiency Improved | Ex-Post | 2015-11-01 | 2016-01-01 | awarded
Office of the Cabinet | Hotel Accommodation - CSME |  | Shopping |  | 3.3.3.1 | 227 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.3 Procurement Process Efficiency Improved | Ex-Post | 2016-08-01 | 2016-08-01 | awarded
Office of the Cabinet | Sensitisation Session - Food |  | Shopping |  | 3.3.3.1 | 449 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.3 Procurement Process Efficiency Improved | Ex-Post | 2016-07-01 | 2016-07-01 | awarded
Office of the Cabinet | Infrastructure Conference - Hotel Accommodation Contractor: GRAN BAHIA PRINCIPE JAMAICA |  | Shopping |  | 3.3.3.1 | 26,658 EU20,201.4 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.3 Procurement Process Efficiency Improved | Ex-Post | 2016-08-01 | 2016-08-01 | awarded
Office of the Cabinet | Hotel Accommodation |  | Shopping |  | 3.3.3.1 | 960 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.3 Procurement Process Efficiency Improved | Ex-Post | 2016-07-01 | 2016-07-01 | awarded
Office of the Cabinet | Hotel Accommodation |  | Shopping |  | 3.3.3.1 | 4822 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.3 Procurement Process Efficiency Improved | Ex-Post | 2016-07-01 | 2016-07-01 | awarded
Office of the Cabinet | Hotel Accommodation |  | Shopping |  | 3.3.3.1 | 227 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.3 Procurement Process Efficiency Improved | Ex-Post | 2016-07-01 | 2016-07-01 | awarded
Office of the Cabinet | Venue Rental for sensitization and awareness campaign |  | Shopping |  | 3.3.3.1 | 721 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.3 Procurement Process Efficiency Improved | Ex-Post | 2016-07-01 | 2016-07-01 | awarded
Office of the Cabinet | Security Services for PBO and TSRU |  | Direct Contracting |  | 3.4.2.2.4 | 2465.46 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.4 Enhancing Parliament´s oversight role | Ex-Ante | 2016-12-01 | 2016-12-01 | awarded
Office of the Cabinet | David Thomas, L. Nelson & S. Smith & Compact Vacations (Per diem and accommodation re UNDP CIPS training- Introductory certificate in Public Procurement CIPS Accredited LEVEL 3) |  | Direct Contracting |  | 4.7a | 4192 | 100 |  | Component 4 Administrative | Ex-Ante | 2016-07-01 | 2016-07-01 | awarded
Office of the Cabinet | David Thomas, L. Nelson & S. Smith & Compact Vacations (Per diem and airfare re Third sub regional Caribbean public procurement conference in Barbados) |  | Direct Contracting |  | 4.7b | 6209 | 100 |  | Component 4 Administrative | Ex-Ante | 2016-06-01 | 2016-06-01 | awarded
Office of the Cabinet | Cheryl Gibson & Compact Vacation (Per diem & Airfare re Parliamentary Budget Officers Conference in Washington DC) |  | Direct Contracting |  | 4.8 | 2613.8 | 100 |  | Component 4 Administrative | Ex-Ante | 2016-06-01 | 2016-06-01 | awarded
Office of the Cabinet | Anika Shuttleworth, S. Francis & J. Ferrigon, eGov Jamaica & Compact Vacations(Visa Application fees, per diem and airfares re eGov & ePart 2016 conference in Guimaraes Portugal) |  | Direct Contracting |  | 4.9 | 13989.6 | 100 |  | Component 4 Administrative | Ex-Ante | 2016-08-01 | 2016-08-01 | awarded
Office of the Cabinet | Chessane Brandon - 65th Westminster Seminar on Parliamentary Practice and Procedure (airfare, meal and warm clothing) |  | Direct Contracting |  | 4.10a | 815 | 100 |  | Component 4 Administrative | Ex-Ante | 2016-12-01 | 2016-12-01 | awarded
Office of the Cabinet | Chesanne Brandon - 65th Westminster Seminar on Parliamentary Practice and Procedure (airfare) (Total Travel Services) |  | Direct Contracting |  | 4.10b | 1735 | 100 |  | Component 4 Administrative | Ex-Ante | 2016-12-01 | 2016-12-01 | awarded
Office of the Cabinet | XII Inter-American Network Meeting on Government Procurement Conference (Hilton Rose Hall Resort and Spa) |  | Direct Contracting |  | 4.11 | 1016.55 | 100 |  | Component 4 Administrative | Ex-Ante | 2016-12-01 | 2016-12-01 | awarded
Office of the Cabinet | Project Management Institute Conference |  | Direct Contracting |  | 4.18 | 8932.13 | 100 |  | Component 4 Administrative | Ex-Ante | 2017-09-01 | 2017-10-01 | awarded
CONSULTING FIRMS
Executing Agency: | Activity: | Additional Information: | Procurement Method (Select one of the options): | Process Number: | Estimated Amount |  |  | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments - for UCS include selection method
[5 empty] | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount Counterpart %: |  |  | Specific Procurement notice | Contract Signature
Office of the Cabinet | Programming Fees – eCensus Enhancements/TRN Validation |  | Direct Contracting | 1.1.1.81 | 20000 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Ante | 2017-07-01 | 2017-08-01 | awarded
Office of the Cabinet | To provide Support to the Public Sector Efficiency Programme (PSEP) in the acquisition of the Human Capital Management Enterprise System (HCMES) |  | Single Source Selection | 1.1a | 33307 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Ante | May 13, 2015 | August 31,2015 | awarded
Office of the Cabinet | To provide Support to the Public Sector Efficiency Programme (PSEP) in the acquisition of the Human Capital Management Enterprise System (HCMES) |  | Single Source Selection | 1.1b | 42128 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Ante | September 7, 2015 | October 2, 2015 | awarded
Office of the Cabinet | Support to the Public Sector Efficiency Programme (PSEP) in the Implementation of the Human Capital Management Enterprise System (HCMES) with Payroll |  | Single Source Selection | 1.1c | 102143.78 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Ante | January 11, 2016 | February 29, 2016 | awarded
Office of the Cabinet | Enhancement of the E-Census Application |  | Single Source Selection | 1.1.1.4 | 15748 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Ante | 2016-04-01 | 2016-05-01 | awarded
Office of the Cabinet | End User Training for MDAs |  | Single Source Selection | 1.1.1.67 | 500000 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Ante | 2016-04-01 | 2017-03-01 | awarded
Office of the Cabinet | To conduct a Learning Needs Analysis and Develop a Detailed Training Strategy |  | Single Source Selection | 1.2.3.1 | 103330 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.2 Strengthening the Capacity of Strategic Human Resource Management Division (SHRMD) | Ex-Ante | 2016-05-01 | 2016-07-01 | awarded
Office of the Cabinet | Leadership Essentials for the Strategic Human Resource Management Division |  | Single Source Selection | 1.2.3.2 | 18785 | 100 |  | Component 1 Human Resources Management (HRM), sub-component 1.2 Strengthening the Capacity of Strategic Human Resource Management Division (SHRMD) | Ex-Ante | 2016-10-01 | 2017-01-01 | awarded
Office of the Cabinet | ICT Training Plan |  | Single Source Selection | 2.1.3.9 | 132351.86 | 100 |  | Component 2 Information & Communication Technologies Management (ICTM), sub-component 2.1 Institutional strengthening of the new ICT governance framework | Ex-Ante | 2016-09-01 | 2017-03-01 | awarded
Office of the Cabinet | Automation of the Government Electrical Inspection Processes Utilizing the Application Management and Data Automation (AMANDA) Software |  | Single Source Selection | 2.2.2 | 400000 | 100 |  | Component 2 Information & Communication Technologies Management (ICTM), sub-component 2.2 Streamlining the process of the GEI | Ex-Ante | 2015-12-01 | 2017-08-01 | awarded
Office of the Cabinet | Individual Constultant - GEI business process reengineering roadmap |  | Single Source Selection | 2.2.1 | 40000 | 100 |  | Component 2 Information & Communication Technologies Management (ICTM), sub-component 2.2 Streamlining the process of the GEI | Ex-Ante | 2015-12-01 | 2017-08-01 | awarded
Office of the Cabinet | Application Development consulting - Software Expertise using IBM Forms Software to Create a Formatted XFDL Form for the Business Registration Form (BRF) |  | Quality and Cost Based Selection | 2.3.1.3 | 73000 | 100 |  | Component 2 Information & Communication Technologies Management (ICTM), sub-component 2.3 Establishment of a One-Stop-Shop for Business Registration | Ex-Ante | 2014-10-01 | 2015-04-01 | awarded
Office of the Cabinet | Project Management and Development Assistance on the Electronic Business Registration Form Application |  | Single Source Selection | 2.3.1.5 | 155973.64 | 100 |  | Component 2 Information & Communication Technologies Management (ICTM), sub-component 2.3 Establishment of a One-Stop-Shop for Business Registration | Ex-Ante | 2016-09-01 | 2016-12-01 | awarded
Office of the Cabinet | Auditors trained in Jamaica (Financial Statement Audit Training) Contractor: National Audit Office |  | Single Source Selection | 3.1.3 | 86440 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.1 Strengthening the AGD's capacity for Performance Audit and Information Technology Audit | Ex-Ante | 2015-01-01 | 2015-07-01 | awarded
Office of the Cabinet | Auditors trained in country (ITA) and ITA Manual drafted and disseminated Contractor: Cowater International Inc. |  | Quality and Cost Based Selection | 3.1.2. | 144294 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.1 Strengthening the AGD's capacity for Performance Audit and Information Technology Audit | Ex-Ante | 2016-01-01 | 2016-06-01 | awarded
Office of the Cabinet | Auditors trained in-country (Performance Audit) Contractor: National Audit Office |  | Single Source Selection | 3.1.1.1 | 132950 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.1 Strengthening the AGD's capacity for Performance Audit and Information Technology Audit | Ex-Ante | 2016-09-01 | 2016-12-01 | awarded
Office of the Cabinet | IA employees trained on Performance Audit (PA) KOSI Corporation Limited |  | Quality and Cost Based Selection | 3.2.4.1a | 87,792.60 EUR85,236 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.2 Strengthening the Internal Audit System capacity | Ex-Ante | 2015-05-01 | 2015-10-01 | awarded
Office of the Cabinet | TeamMate Training Contractor: PricewaterhouseCoopers |  | Single Source Selection | 3.2.2.2g | 28,611.26 EUR27,259.63 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.2 Strengthening the Internal Audit System capacity | Ex-Ante | 2015-03-01 | 2015-03-01 | awarded
Office of the Cabinet | Professional Development Framework Contractor: Arthur Lok Jack Graduate School of Business, The University of the West Indies, St. Augustine |  | Quality and Cost Based Selection | 3.2.1 | 90462 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.2 Strengthening the Internal Audit System capacity | Ex-Post | 2016-05-01 | 2016-12-01 | awarded
Office of the Cabinet | Senior Procurement Practioners and Lawyers trained Contractor: Management Institute for National Development |  | Single Source Selection | 3.3.4.1 | 67,765.42 EUR | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.3 Procurement process efficiency improved | Ex-Ante | 2014-04-01 | 2014-05-01 | awarded
Office of the Cabinet | Advanced Procurement Law Contractor: Management Institute for National Development |  | Single Source Selection | 3.3.4.2 | 100,359.52 EUR | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.3 Procurement process efficiency improved | Ex-Ante | 2014-12-01 | February 23, 2015 | awarded
Office of the Cabinet | Insurance Training Contractor: College of Insurance and Professional Services |  | Single Source Selection | 3.3.4.3 | 25,388.00 EUR19,088.72 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.3 Procurement process efficiency improved | Ex-Ante | 2015-09-01 | January 25, 2016 | awarded
Office of the Cabinet | Redrafting of Procurement Manual and Bidding Documents Contractor: Charles Kendall and Partners |  | Quality and Cost Based Selection | 3.3.1.1 | 141,348.00 EUR106,276.69 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.3 Procurement process efficiency improved | Ex-Ante | 2015-10-01 | 2016-04-01 | awarded
Office of the Cabinet | UNDP CIPS training Contractor: Mananagement Institute for National Development |  | Single Source Selection | 3.3.4.4 | 144,849 EUR108,909.02 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.3 Procurement process efficiency improved | Ex-Ante | 2015-11-01 | 2016-09-01 | awarded
Office of the Cabinet | Preparing curricula and training material for 8-module training program Contractor: Charles Kendall and Partners |  | Quality and Cost Based Selection | 3.3.2.1 | 313340 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.3 Procurement process efficiency improved | Ex-Ante | 2016-09-01 | 2016-12-01 | awarded
Office of the Cabinet | Preparing national curricula training - National Public Procurement Centre at MIND Contractor: MIND |  | Single Source Selection | 3.3.2.2 | 211853.63 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.3 Procurement process efficiency improved | Ex-Ante | 2016-09-01 | 2016-12-01 | awarded
Office of the Cabinet | Designing of the Technical and Budget office Contractor: Infocivitas |  | Single Source Selection | 3.4.2.1 | 283687.5 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.4 Enhancing Parliament´s oversight role | Ex-Ante | 2016-03-01 | 2016-11-01 | awarded
Office of the Cabinet | Training for all Committees for Parliament Contractor: MIND |  | Single Source Selection | 3.4.3 | 202883 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.4 Enhancing Parliament´s oversight role | Ex-Ante | 2016-10-01 | 2016-12-01 | awarded
Office of the Cabinet | To Design and Deliver Realtime Stenotype Training for the Hansard Staff at the Houses of Parliament Contractor: Justice Training Institue |  | Selection Based on the Consultants' Qualifications | 3.4.2.7 | 19852 | 100 |  | Component 3 Control Systems and Accountability, sub-component 3.4 Enhancing Parliament´s oversight role | Ex-Post | 2016-11-01 | 2016-12-01 | awarded
Office of the Cabinet | Project Management Professional Training |  | Single Source Selection | 4.15 | 41779.66 | 100 |  | Component 4 Administrative | Ex-Post | 2017-04-01 | 2017-06-01 | awarded
Office of the Cabinet | External Auditors |  | Single Source Selection | 4.3 | 36200 | 100 |  | Component 4 Administrative | Ex-Post | 2016-02-01 | 2016-06-01 | awarded
Office of the Cabinet | External Auditors |  | Single Source Selection | 4.16 | 56878.35 | 100 |  | Component 4 Administrative | Ex-Ante | 2017-02-01 | 2017-06-01 | awarded
INDIVIDUAL CONSULTANTS
Executing Agency: | Activity: | Additional Information: | Procurement Method (Select one of the options): | Process Number: | Estimated Amount |  |  | Estimated Number of Consultants: | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments - for UCS include selection method
[5 empty] | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount Counterpart %: |  |  |  | No Objection to TOR's | Contract Signature
Office of the Cabinet | Programmer Analyst |  | Comparison of Qualifications - National Individual Consultant | 1.1.1.64 | 70833.33 | 100 |  | 1 | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2017-07-01 | 2017-10-01 | Awarded
Office of the Cabinet | Business Analysts Officer |  | Comparison of Qualifications - National Individual Consultant | 1.1.1.66 | 141666.66 | 100 |  | 2 | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2017-07-01 | 2017-10-01 | Awarded
Office of the Cabinet | Systems Support Officer - 2 officers |  | Comparison of Qualifications - National Individual Consultant | 1.1.1.89 | 141666.66 | 100 |  | 2 | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2017-07-01 | 2017-09-01 | Awarded
Office of the Cabinet | Data and Test Lead |  | Comparison of Qualifications - National Individual Consultant | 1.1.1.9 | 52000 | 100 |  | 1 | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2015-11-01 | April 18, 2016 | Awarded
Office of the Cabinet | Senior Programme Management Lead |  | Comparison of Qualifications - National Individual Consultant | 1.1.1.8 | 70612.08 | 100 |  | 1 | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2015-12-08 | January 18, 2016 | Awarded
Office of the Cabinet | Business Analyst |  | Comparison of Qualifications - National Individual Consultant | 1.1.1.7 | 73896.36 | 100 |  | 1 | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2014-07-01 | January 18, 2016 | Awarded
Office of the Cabinet | Application Solutions Expert |  | Comparison of Qualifications - National Individual Consultant | 1.1.1.1 | 63492.06 | 100 |  | 1 | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2016-01-01 | June 22, 2016 | Awarded
Office of the Cabinet | Systems Support Lead |  | Comparison of Qualifications - National Individual Consultant | 1.1.1.2 | 47619.05 | 100 |  | 1 | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2016-01-01 | June 27, 2016 | Awarded
Office of the Cabinet | Infrastructure & Networks Lead |  | Comparison of Qualifications - National Individual Consultant | 1.1.1.3 | 43650.79 | 100 |  | 1 | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2016-04-01 | July 4, 2016 | Awarded
Office of the Cabinet | Communications Officer |  | Comparison of Qualifications - National Individual Consultant | 1.1.1.5 | 43650.79 | 100 |  | 1 | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2016-01-01 | June 27, 2016 | Awarded
Office of the Cabinet | HCMES Training - Lead |  | Comparison of Qualifications - National Individual Consultant | 1.1.1.6 | 31007.75 | 100 |  | 1 | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2016-11-01 | 2017-02-01 | Awarded
Office of the Cabinet | Technical Administrator |  | Comparison of Qualifications - National Individual Consultant | 1.1.1.65 | 48000 | 100 |  | 1 | Component 1 Human Resources Management (HRM), sub-component 1.1 Implementation of HCMES | Ex-Post | 2017-02-01 | 2017-05-01 | Awarded
Office of the Cabinet | To Assist Information and Communication Technologies Jamaica with Project Management |  | Comparison of Qualifications - National Individual Consultant | 2.1.1.5 | 56000 | 100 |  | 1 | Component 2 Information & Communication Technologies Management (ICTM), sub-component 2.1 Institutional strengthening of the new ICT governance framework | Ex-Post | 2015-08-01 | January 25, 2016 | Awarded
Office of the Cabinet | To Assist Information and Communication Technologies Jamaica with the Development of an ICT Governance Framework |  | Comparison of Qualifications - National Individual Consultant | 2.1.1.6 | 20000 | 100 |  | 1 | Component 2 Information & Communication Technologies Management (ICTM), sub-component 2.1 Institutional strengthening of the new ICT governance framework | Ex-Post | 2015-08-01 | February 22, 2016 | Awarded
Office of the Cabinet | To Assist Information and Communication Technology (ICT) Jamaica with the Development of a Communication and Consultation Plan |  | Comparison of Qualifications - National Individual Consultant | 2.1.1.1c | 29003.83 | 100 |  | 1 | Component 2 Information & Communication Technologies Management (ICTM), sub-component 2.1 Institutional strengthening of the new ICT governance framework | Ex-Ante | 2016-02-01 | March 21, 2016 | Awarded
Office of the Cabinet | Facilitator of Workshop - Key instruments and policies to support new e-government framework |  | Comparison of Qualifications - National Individual Consultant | 2.1.1.5 | 10000 | 100 |  | 1 | Component 2 Information & Communication Technologies Management (ICTM), sub-component 2.1 Institutional strengthening of the new ICT governance framework | Ex-Post | 2015-09-01 | 2015-09-01 | Awarded
Office of the Cabinet | Project Manager |  | Comparison of Qualifications - National Individual Consultant | 2.3.1.1 | 40000 | 100 |  | 1 | Component 2 Information & Communication Technologies Management (ICTM), sub-component 2.3 Establishment of a One-Stop-Shop for Business Registration | Ex-Ante | 2014-09-30 | 2015-02-01 | Awarded
Office of the Cabinet | To Facilitate the Implementation of Training and Sensitisation Programme to Support the Online Filing of the Business Registration Form (eBRF) |  | Single Source Selection | 2.3.3.1 | 12000 | 100 |  | 1 | Component 2 Information & Communication Technologies Management (ICTM), sub-component 2.3 Establishment of a One-Stop-Shop for Business Registration | Ex-Ante | 2016-03-01 | April 26, 2016 | awarded
Office of the Cabinet | To Provide Software Programming Expertise to Support Online Filing of the Business Registration Form - Microsoft .NET |  | Comparison of Qualifications - National Individual Consultant | 2.3.1.2 | 40000 | 100 |  | 1 | Component 2 Information & Communication Technologies Management (ICTM), sub-component 2.3 Establishment of a One-Stop-Shop for Business Registration | Ex-Ante | 2014-10-30 | 2015-02-01 | Awarded
Office of the Cabinet | Head of SCS Workstream |  | Comparison of Qualifications - National Individual Consultant | 2.4.2.1 | 131782.95 | 100 |  | 1 | Component 2 Information & Communication Technologies Management (ICTM), sub-component 2.4 Introduction of Shared Corporate Services | Ex-Post | 2016-12-01 | 2017-02-01 | Awarded
Office of the Cabinet | Project Management for the Implementation of an Enterprise Content Management Solution (ECM) Contractor: Andrea Williams-Stewart |  | Comparison of Qualifications - National Individual Consultant | 3.1.5.1 | 90000 | 100 |  | 1 | Component 3 Control Systems and Accountability, sub-component 3.1 Strengthening the AGD's capacity for Performance Audit and Information Technology Audit | Ex-Post |  | 2016-12-01 | Awarded
Office of the Cabinet | Solution Architect to provide technical expertise for the Implementation of an Enterprise Content Management System Contractor: Jerome Campbell |  | Comparison of Qualifications - National Individual Consultant | 3.1.5.2 | 60000 | 100 |  | 1 | Component 3 Control Systems and Accountability, sub-component 3.1 Strengthening the AGD's capacity for Performance Audit and Information Technology Audit | Ex-Post |  | 2016-12-01 | Awarded
Office of the Cabinet | Individual Consultant - Internal Audit Manual Contractor: Jacqueline Johnson |  | Comparison of Qualifications - National Individual Consultant | 3.2.3 | 44356 | 100 |  | 1 | Component 3 Control Systems and Accountability, sub-component 3.2 Strengthening the Internal Audit System capacity | Ex-Post | 2015-07-01 | 2016-11-28 | Awarded
Office of the Cabinet | Individual Consultancy for Project Management Contractor: John Thompson |  | Single Source Selection | 3.3.5.4 | 100,000.00 EUR75,187.97 | 100 |  | 1 | Component 3 Control Systems and Accountability, sub-component 3.3 Procurement process efficiency improved | Ex-Ante | 2016-01-01 | 2016-01-01 | Awarded
Office of the Cabinet | Development of Systems Specifications for a Contractor Registration/Management System for the National Contracts Commission Contractor: David McDermont |  | Comparison of Qualifications - National Individual Consultant | 3.3.5.1 | 71,420 EUR69,339.81 | 100 |  | 1 | Component 3 Control Systems and Accountability, sub-component 3.3 Procurement process efficiency improved | Ex-Post |  | 2016-07-01 | Awarded
Office of the Cabinet | Lead Procurement Specialist |  | Comparison of Qualifications - National Individual Consultant | 3.3.2.3 | 203178 | 100 |  | 1 | Component 3 Control Systems and Accountability, sub-component 3.3 Procurement process efficiency improved | Ex-Post | 2016-07-01 | 2016-12-01 | Awarded
Office of the Cabinet | Senior Business Analyst |  | Comparison of Qualifications - National Individual Consultant | 3.3.5.5 | 62000 | 100 |  | 1 | Component 3 Control Systems and Accountability, sub-component 3.3 Procurement process efficiency improved | Ex-Post | 2016-09-01 | 2016-12-01 | Awarded
Office of the Cabinet | Strategic Review for the Houses of Parliament Contractor: Paul Belisle |  | Single Source Selection | 3.4.1.1 | 72,686.00 EUR70,112.78 | 100 |  | 1 | Component 3 Control Systems and Accountability, sub-component 3.4 Enhancing Parliament´s oversight role | Ex-Ante | 2015-07-01 | 2015-09-01 | Awarded
Office of the Cabinet | Comprehensive Assessment of the Parliament and Design of a Management Accountability Framework (MAF) for the Parliament Contractor: Gerry Westland |  | Single Source Selection | 3.4.1.2 | 93250 | 100 |  | 1 | Component 3 Control Systems and Accountability, sub-component 3.4 Enhancing Parliament´s oversight role | Ex-Ante | 2015-08-01 | 2016-07-01 | Awarded
Office of the Cabinet | Develop a Strategic Business Plan, Operational Plan and Management Accountability Framework for the Office of the Clerk to the Houses of Parliament Contractor: Pail Belisle |  | Single Source Selection | 3.4.1.3 | 80000 | 100 |  | 1 | Component 3 Control Systems and Accountability, sub-component 3.4 Enhancing Parliament´s oversight role | Ex-Ante | 2016-11-10 | 2016-12-01 | Awarded
Office of the Cabinet | consultancy services for the Parliamentary Budget Office (PBO) and Technical Research Unit (TRSU) at the Houses of Parliament - Research Officer Contractor: Ornella Kelly |  | Comparison of Qualifications - National Individual Consultant | 3.4.2.3.1 | 49730.98 | 100 |  | 1 | Component 3 Control Systems and Accountability, sub-component 3.4 Enhancing Parliament´s oversight role | Ex-Post |  | 2016-12-02 | Awarded
Office of the Cabinet | consultancy services for the Parliamentary Budget Office (PBO) and Technical Research Unit (TRSU) at the Houses of Parliament Contractor: Racquel Artwell |  | Comparison of Qualifications - National Individual Consultant | 3.4.2.3.2 | 49730.98 | 100 |  | 1 | Component 3 Control Systems and Accountability, sub-component 3.4 Enhancing Parliament´s oversight role | Ex-Post |  | 2016-12-03 | Awarded
Office of the Cabinet | consultancy services for the Parliamentary Budget Office (PBO) and Technical Research Unit (TRSU) at the Houses of Parliament - Principal Researcher Contractor: Kacy West |  | Comparison of Qualifications - National Individual Consultant | 3.4.2.3.3 | 85788.05 | 100 |  | 1 | Component 3 Control Systems and Accountability, sub-component 3.4 Enhancing Parliament´s oversight role | Ex-Post |  | 2016-12-04 | Awarded
Office of the Cabinet | consultancy services for the Parliamentary Budget Office (PBO) and Technical Research Unit (TRSU) at the Houses of Parliament - Project Administration Contractor: Angela McGregor |  | Comparison of Qualifications - National Individual Consultant | 3.4.2.3.4 | 41674.42 | 100 |  | 1 | Component 3 Control Systems and Accountability, sub-component 3.4 Enhancing Parliament´s oversight role | Ex-Post |  | 2016-12-05 | Awarded
Office of the Cabinet | Impact Evaluation Field Coordinator |  | Comparison of Qualifications - National Individual Consultant | 4.14 | 23255.81 | 100 |  | 1 | Component 4 Administration | Ex-Post |  | 2017-04-01 | Awarded