## Detailed Procurement Plan
PROCUREMENT PLAN INFORMATION - EDUCATION QUALITY IMPROVEMENT PROGRAM (EQIP) (3186/OC-BL) February 2018 to May 2019
WORKS
Executing Agency: | Activity: | Additional Information: | Procurement Method (Select one of the options): | Lots Quantity: | Process Number: | Amount in u$s : |  |  | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments
[6 empty] | Estimated Amount, in u$s : | Estimated Amount, BID %: | Estimated Amount, Counterpart %: |  |  | Specific Procurement notice | Contract Signature
N/A
GOODS
Executing Agency: | Activity: | Additional Information: | Procurement Method (Select one of the options): | Lots Quantity: | Process Number: | Amount in u$s : |  |  | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments
[6 empty] | Estimated Amount, in u$s : | Estimated Amount, BID %: | Estimated Amount, Counterpart %: |  |  | Specific Procurement notice | Contract Signature
PEU | Procure Office Equipment | Office Equipment | Shopping |  |  | 10404.425 | 100% | 0 | Project Management | Ex-Ante | 2015-04-01 | 2015-05-01 | Completed
PEU | Procure Furniture & Office Supplies | Furniture & Office Supplies | Shopping |  |  | 6337.25 | 100% | 0 | Project Management | Ex-Ante | 2015-04-01 | 2015-05-01 | Completed
PEU | Procure Video-Study equipment | Video-Study Equipment | Shopping |  |  | 15000 | 100% | 0 | Project Management | Ex-Ante | 2018-09-18
PEU | Procure Office Equipment | Office and Video conference equipment, computers, projector | Shopping |  |  | 30000 | 100% | 0 | Project Management | Ex-Ante | 2018-10-18
PEU | Procure Furniture Vehicle | Vehicle | Shopping |  |  | 24500 | 100% | 0 | Project Management | Ex-Ante |  | 2018-09-18 | Pending
NON CONSULTING SERVICES
Executing Agency: | Activity: | Additional Information: | Procurement Method (Select one of the options): | Lots Quantity: | Process Number: | Amount in u$s : |  |  | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments
[6 empty] | Estimated Amount, in u$s : | Estimated Amount, BID %: | Estimated Amount, Counterpart %: |  |  | Bidding Documents | Contract Signature
PEU | Develop and execute a marketing campaign | The objective of the MC is threefold: (1) elevating the prestige of teachers; (2) reach out to potential applicants with the purpose of attracting qualified teacher candidates to Belize’s Teacher Education Institutes (TEI); and (3) increasing the proportion of new male student teacher candidates in Teacher Education Institutes | Fixed Budget |  |  | 633360 | 100% | 0% | Component I: Improving the Quality of Teachers. | Ex-Ante | 2015-12-15 | 2016-06-30 | ongoing
PEU | Storage facility | Rental of storage facility to keep documents produced by the enumerators | Price comparison |  |  | 5100 | 100% | 0% | Component 3 | Ex-Ante | 2014 | 2014 | Completed
CONSULTING FIRMS
Executing Agency: | Activity: | Additional Information: | Procurement Method (Select one of the options): | Process Number: | Amount in u$s : |  |  | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments
[5 empty] | Estimated Amount, in u$s : | Estimated Amount, BID %: | Estimated Amount, Counterpart %: |  |  | Specific Procurement notice | Contract Signature
PEU | Video study as part of the longitudinal Study of Teacher Candidates and Pre-post analysis of the pre-service teacher training. | The entry mechanism for teacher training will be evaluated by applying non-cognitive and cognitive tests for all applicants to the teacher training. Also, for the pre-post analysis the analysis will compare the results of the entry into teacher training exam with the entry into the profession exam. | Quality and Cost Based Selection | 1.1 b) Changed to fixed price quality based selection | 341000 | 100% | 0% | Component 3 | Ex-Ante | 2016-04-01 | 2017-01-24 | Ongoing; Contract time will be amended and expiration date will be November 2018
PEU | On-site Practical Professional Development Training and tutoring of primary teacher educators and supporting instructors; and training, mentoring and technical assistance. | The aim would be for training and mentoring TEI's Dept Heads& Admin.; Capacity building of TEI to improve teacher training in contents and pedagogy for Math, Science & English. Lessons plans for Math, Science and English using the Visible and Tangible model in Math and student centered apporach in the others. Develop a formative assessment instrument to do constinuous assessments of students competences. Implementation of the lessons plans and formative assessment in the classrooms. | Single Source Selection | 1.2.1 ; 1.2.2; 1.3.1; 1.3.2; 1.3.3-MSVU | 3441863 | 100% | 0% | Component I: Improving the Quality of Teachers. | Ex-Ante | N/A | 2015-04-01 | Ongoing
PEU | Technical assistance in the creation of a feedback system for TEIs with respect to how their graduates perform; plus monitoring to assure quality control. | The feedback system will strengthen the capacity of TEI to monitor the quality of their services and outputs. Training and monitoring Principals, Dept. Heads and Adm. of TEI on how to monitor and ensure quality of services. | Quality and Cost Based Selection | 2.1.1; 2.1.2 (F) | 366900 | 100% | 0% | Component II: Governance of the Education System. | Ex-Ante | 2016-06-30 | 2017-01-23 | Ongoing
PEU | Implementation of a teacher profession entry exam as a requirement for a teaching license. | Develop, pilot and implement a teacher profession entry exam as a requirement for a teaching license. | Single Source Selection | 2.1.3 SSS-CXC | 677592.6 | 100% | 0% | Component II: Governance of the Education System. | Ex-Ante | N/A | 2015-01-01 | Ongoing; contract amendment was signed May 17, 2018
PEU | Training and technical assistance to principals to promote their leadership as the vehicle for improving school and student performance; and training and technical assistance to parents to increase their participation in school management. | The training would have the following features: (a) principal training in School Based Management; (b) technical assistance to principals to improve data collection and reporting processes to the MOEY, and to use student data at the school level to identify teacher professional development needs and develop school improvement plans; and (c) continued assistance to principals in the efficient use of resources. With respect to parents, the training aims to (a) inform parents about school and student assessments, with comparisons with other schools in the area, the district and the nation; and (b) raise awareness among members of parent and teacher associations about parental rights and responsibilities; and about what makes a good school in order to improve the accountability of schools to parents. | Quality Based Selection | 2.2.1 and 2.2.4(G) With CDB - MSVU | 926655 | 100% | 0% | Component II: Governance of the Education System. | Ex-Ante | 2016-05-01 | 2016-09-10 | ongoing
PEU | Creation of an integrated Education Management Information System (EMIS). | The objective is to implement the open source software OpenEMIS. The objective of OpenEMIS is to enable education policy planning and quality assurance, including the monitoring of student achievement, school resource use, and performance on a fair and objective basis. | Single Source Selection | 2.2.2 & 2.2.3 SSS- CSF | 2048446 | 100% | 0% | Component II: Governance of the Education System. | Ex-Ante | N/A | 2014-12-01 | Ongoing; contract amendment for USD$244,240
PEU | Data collection by enumerators | EQIP will support the financing of non-cognitive and cognitive assessments to screen teacher candidates. The results of such assessments will assist the MOEYS and TEI in identifying those contenders who need remedial assistance during their teacher training | Single Source Selection | 3.1.1 | 775818 | 100% | 0% | Component 3 | Ex-Ante | 2016-01-15 | 2016-04-01 | Data Collection by Enumerators ( 1st contract value $369,409; disbursed USD120,057.89 and was terminated for a new contract with value USD655,760)
PEU | STEAM Laboratory school | Conceptual Desing of the STEAM Laboratory Schools | Fixed Budget | 2.1 | 100000 | 100% | 0% | Component 2 | Ex-Ante | 2018-11-01 | 2018-01-01 | 50% will be finance from resources from BL-T1100
PEU | Audit | Project audit | Quality and Cost Based Selection | Audit | 82582 | 100% | 0% | Project Execution | Ex-Ante | 2015-05-01 | 2015-06-01 | Audit (1st contract USD45,283.88, disbursed to date USD44,240.12; New contract amendment USD38,342.31)
INDIVIDUAL CONSULTANTS
Executing Agency: | Activity: | Additional Information: | Procurement Method (Select one of the options): | Process Number: | Amount in u$s : |  |  | Estimated Number of Consultants: | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments
[5 empty] | Estimated Amount, in u$s : | Estimated Amount, BID %: | Estimated Amount, Counterpart %: |  |  |  | No Objection to TOR's | Contract Signature
PEU | Support for Longitudinal Study: Survey Supervisor for baseline data collection of the EQIP | The consultant will have the overall responsibility for the administration of survey questionnaires to TEI teacher applicants, principals, teachers, parents and students, and testing instruments to students and teachers at the beginning of the academic year 2015-16. | Single Source Selection | Part of process 3.1.2 | 59000 | 100% | 0% | 1 | Component 3 | Ex-Ante | 2015-02-02 | 2015-02-01 | completed.
PEU | Senior Consultant for the Development and Validation of Learning Assessments in Mathematics and Science | The consultant will develop and validate test for Infant II through to Standard VI in Mathematics and Science. | Comparison of Qualifications - International Individual Consultant | Part of process 3.1.1 | 48274 | 100% | 0% | 1 | Component 3 | Ex-Ante | 2017-02-01 | 2017-03-01 | completed
PEU | Senior Consultant for the Development and Validation of Learning Assessments in English Language Arts | The consultant will develop and validate test for Infant II through to Standard VI in English Language Arts. | Comparison of Qualifications - International Individual Consultant | Part of process 3.1.1 | 45856 | 100% | 0% | 1 | Component 3 | Ex-Ante | 2017-02-01 | 2017-03-01 | completed
PEU | Procurement Specialist | PEU support | Comparison of Qualifications - National Individual Consultant | 4.1(PS) | 49831.45 | 100% | 0% | 1 | Project Management | Ex-Ante | 2014-08-14 | 2016-06-16 | Completed
PEU | Financial Specialist | PEU support | Comparison of Qualifications - National Individual Consultant | 4.1(FS) | 85470 | 100% | 0% | 1 | Project Management | Ex-Ante | 2014-08-01 | 2015-10-01 | ongoing
PEU | Program Officer | To support the PEU in the coordination and execution of the EQIP | Comparison of Qualifications - National Individual Consultant | 4.1(PO) | 12095 | 100% | 0% | 1 | Project Management | Ex-Ante | 2014-08-01 | 2016-03-01 | Completed
PEU | PEU support/Long-Term International Consultant (LTC) | Consultant objective is to support the execution of EQIP on technical matters. The LTC will have the responsibility of assisting the PEU and MOEYS’s technical units in the execution of program components and subcomponents, by assessing the progress made up to date and addressing the challenges facing the program (see LTC TORs in annex 1). The LTC will also support the PEU in gathering and analyzing the information required by the semi-annual and annual reports to the IDB. | Comparison of Qualifications - International Individual Consultant | 4.1(LTC) | 78650 | 100% | 0% | 1 | Project Management | Ex-Ante | 2015-05-01 | 2015-09-01 | completed
PEU | Mid-term review | As required by the project. | Comparison of Qualifications - International Individual Consultant | 4.2 | 41500 | 100% | 0% | 1 | Project Management | Ex-Ante |  | 2017-03-17 | Completed
PEU | Ex-post economic analysis | As required by the project. | Comparison of Qualifications - International Individual Consultant | 4.3 | 20000 | 100% | 0% | 1 | Project Management | Ex-Ante |  | 2018-09-01 | Pending
PEU | Doc. Management System | The objective of this consultancy is to support the PEU in the design and implementation of a document management information system for the EQIP program in order to have an internal control structure | Single Source Selection |  | 2500 | 100% | 0% | 1 | Project Management | Ex-Ante | 2015-05-01 | 2015-06-01 | completed
PEU | Development of a new national Education strategy | Development of a new national Education strategy | Single Source Selection | 2.2 | 10000 | 100% | 0% |  | Component 2 | Ex-Ante | 2018-11-01 | 2018-12-01 | 5.4(d)
PEU | Study of the alignment of teacher training programs against the approved teacher education standards | The objective of this consultancy is to determine gaps between current teacher training program and approved teacher educaiton standards and provide recommendations. | Single Source Selection | 1.1 | 12500 | 100% | 0% | 1 | Component 1 | Ex-Ante | 2018-11-01 | 2018-12-01 | 5.4(b)
TRAINING
Executing Agency: | Activity: | Additional Information: | Procurement Method (Select one of the options): | Process Number: | Amount in u$s : |  |  | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments
[5 empty] | Estimated Amount, in u$s : | Estimated Amount, BID %: | Estimated Amount, Counterpart %: |  |  | Annual Training Plan (ATP) | End of Activity
TRANSFERS
Executing Agency: | Transfer Purpose: | Additional Information: | Process Number: | Amount in u$s : |  |  | Associated Component: | Estimated Number of Transfers: | Dates |  | Comments
|  |  |  | Estimated Amount, in u$s : | Estimated Amount, BID %: | Estimated Amount, Counterpart %: |  |  | Contract Signature | Transfer Date
N/A
|  |  |  | TOTAL - US$ | 9951234.725
` |  |  |  | Op cost w/o goods | 47195 | Admin Costs
|  |  |  | Tot. w/ Goods | 9998429.725

## Budget
INFORMATION FOR PROCUREMENT PLAN ONGOING ONGOING AND/OR LAST PRESENTED
EDUCATION QUALITY IMPROVEMENT (3186/OC-BL; BL-L1018)
1. Procurement Plan Coverage
Data | From | Until
Procurement Plan Coverage: | Sept. 2018 | 2019-05-01
2. Procurement Plan Details
Version ( 2-2018) : 42 months | 08-2018
3. Amounts by Investment Category
Investment Category | Amount Financed by the Bank | Total Amount (Including counterpart)
Works | 0 | 0
Goods | 86241.675 | 86241.675
Non Consulting Services | 633360 | 633360
Training | 0 | 0
Operative Costs (w/o Goods) | 47195 | 47195
Consulting Services (Firms + Individuals) | 9231633.05 | 9231633.05
Transfers | 0 | 100000
Community Participation | 0 | 0
Unassigned | 0 | 0
Total | 9998429.725 | 10098429.725
4. Components
Project Components | Amount Financed by the Bank | Total Amount (Including counterpart)
Improving the Quality of Teachers | 4428723 | 4428723
Governance of the Education System | #VALUE! | #VALUE!
Project Evaluation | 153130 | 153130
Project Execution & Supervision | 377728.45 | 504586.45
Admin Expenses (includes Goods) | 133436.675 | 133436.675
Contingency | 0 | 0
| 0 | 0
Total | #VALUE! | #VALUE!