## Sheet1
Inter-American Development Bank
IFD/ICS
PROCUREMENT PLAN FOR NON-REIMBURSABLE TECHNICAL COOPERATIONS
Country: Regional |  |  |  |  | Executing agency: IFD/ICS |  |  |  |  | Public or private sector: Public Sector
Project number: RG-T2458 |  |  |  |  | Title of Project: Development of Critical Infrastructure Protection (CIP) Plan
Period covered by the plan:
Threshold for ex-post review of procurements: |  |  |  | Goods and services (in US$):___0_________ |  |  |  | Consulting services(in US$):____________ | 540000
Item Nº | Ref. AWP | Description (1) | Estimated contract cost (US$) | Procurement Method (2) | Review of procurement (ex-ante or ex-post) (3) | Source of financing and percentage |  | Estimated date of the procurement notice or start of the contract | Technical review by the PTL (4) | Comments
[6 empty] | IDB/MIF % | Local/other %
1 |  | Component 1 |  | QCBS/IIC
|  | Conduct research on best practice cases of leading countries in CIP by cluster. | 120000 |  |  | 100%
2 |  | Component 2 |  | QCBS
|  | Survey and analysis of CIP status of LAC countries by cluster | 180000 |  |  | 100%
3 |  | Component 3 |  | QCBS/IIC
|  | Provide the master plan for critical infrastructure protection consisting of change of laws, organizational structure, institutional capacity building by cluster | 140000 |  |  | 100%
4 |  | Component 4 |  | QCBS/IIC
|  | Suggest technological measures to support effective prevention, detection and counteraction by cluster | 90000 |  |  | 100%
5 |  | Component 5 |  | QCBS/IIC
|  | Diseminaton | 10000
Total |  |  | 540000 | Prepared by: Antonio Garcia Zaballos |  |  | Date: 5/16/2014
(1) Grouping together of similar procurement is recommended, such as computer hardware, publications, travel, etc. If there are a number of similar individual contracts to be executed at different times, they can be grouped together under a single heading, with an explanation in the comments column indicating the average individual amount and the period during which the contract would be executed. For example: an export promotion project that includes travel to participate in fairs would have an item called "airfare for fairs", an estimated total value od US$5,000, and an explanation in the Comments column: "This is for approximately four different airfares to participate in fairs in the region in years X and X1".
(2) Goods and works: CB: Competitive bidding; PC: Price comparison; DC: Direct contracting.
(2) Consulting firms: CQS: Selection Based on the Consultants' Qualifications; QCBS: Quality and cost-based selection; LCS: Least Cost Selection; FBS: Selection under a Fixed Budget; SSS: Single Source Selection; QBS: Quality Based selection.
(2) Individual consultants: IICQ: International Individual Consultant Selection Based on Qualifications; SSS: Single Source Selection.
(3) Ex-ante/ex-post review: In general, depending on the institutional capacity and level of risk associated with the procurement, ex-post review is the standard modality. Ex-ante review can be specified for critical or complex process.
(4) Technical review: The PTL will use this column to define those procurement he/she considers "critical"or "complex"that require ex ante review of the terms of reference, technical specifications, reports, outputs, or other items.