PROJECT PERFORMANCE COMPLETION REPORT

CAPACITY BUILDING FOR

TRADE & INVESTMENT PROMOTION

(ATN/MT-8047-BL)

| I. Basic Project Data |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Country: BELIZE Project Title: Capacity Building for Trade and Investment Promotion TC Number (s): TC0107015 MIF/AT: ATN Number (s): ATN/MT-8047-BL Executing Agency (ies): BELTRAIDE CO Specialist responsible: Harold Arzu HQ Specialist responsible: Fabrizio Operti Date of Report: January 2006 Date of approval by Representative: N/A Date of CRG: Date of final approval: 04 October 2002 |  |  |  |  |  |  |  |  |  |  | Date of Donor Approval (Month/day/year): 04 October 2002 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Date of Contract Signature: 13 November 2002 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Date of Contract Validity: 13 November 2002 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Date of First Eligibility for First Disbursement: 15 April 2003 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Date of Total Eligibility for First Disbursement: 15 April 2003 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Date of First Disbursement: 07 May 2003 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Original Date for Final Disbursement: 12 May 2005 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Actual Date of Final Disbursement: 22 July 2005 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Original Date for Final Execution: 12 November 2004 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Actual Date of Final Execution: 22 June 2005 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Extensions granted for final execution (months): 7.3 months |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Extensions granted for final disbursement (months): 2.3 months |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Extension granted as percentage of original execution period: _30.4 % |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Extension granted as percentage of original disbursement period: _7.67 % |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| II. Project Financing Data. |  |
| 1. MIF Financing: - Original amount: US$490,000 - Actual amount: US$416,348 - Total amount cancelled: US$73,652 |  |  |  |  | 2. Counterpart contribution from EA: - Original amount: US$210,000 - Actual amount: US$268,271 3. Counterpart contribution from other sources: - Original amount: - Actual amount: 4. Total Counterpart contribution (2 + 3): - Original amount: US$210,000 - Actual amount: US$268,271 |  |  |  |  |  |  |  | - Project Total Cost (1 + 4): - Original amount: US$700,000 - Actual amount: US$684,619 |  |  |  |  |  |  |  |  |  |  |  |  |
| Actual Disbursements of MIF funds: - Amount: $418,348 - Percent of original funds (%): 85% |  |  |  |  |  |  |  | Actual Disbursements of Counterpart funds: - Amount: $268,271 - Percent of original funds (%): 128% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| III. Project Performance Data. |  |
| # No Yes Were objectives and indicators been agreed to with beneficiary/executing agencies? [ ] [X ] Were original development objective(s) and/or indicators been officially reformulated? [ X ] [ ] Were components and/or indicators been officially restructured? [X ] [ ] Were indicators reviewed during execution: ? [ ] [ X ] Did the beneficiary/executing agency maintained performance indicator data? [ ] [X ] Was there a defined data gathering system in place with baseline information? [ ] [X ] Has the beneficiary/executing agency rated the performance of the project? [ ] [X ] If yes, what were the IP and DO classifications IP [ S ] DO [HP] Did the beneficiary/executing agency ratings differ from the Bank’s? [ X ] [ ] If yes, provide a brief explanation of the difference: What is the Executing Agency rating of Bank’s Performance VS [ ] S [ X ] U [ ] VU [ ] What was the date of final evaluation:__July 2005 ____ |  |  |  |  |  |  | Historical MPPMR Ratings: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Dec. |  |  | June | Dec. | June |  | Dec. | June |  | Dec. |  | June |  | Dec. |  | Final |  |  |
|  |  |  |  |  |  |  | (year) |  |  | ____ | 2002 | 2003 |  | 2003 | 2004 |  | 2004 |  | 2005 |  | _____ |  | _____ |  |  |
|  |  |  |  |  |  |  | IP [ ] |  |  | [ ] | [S] | [S] |  | [S] | [S] |  | [S] |  | [S] |  | [ ] |  | [ S] |  |  |
|  |  |  |  |  |  |  | DO [ ] |  |  | [ ] | [H] | [H] |  | [H] | [H] |  | [H] |  | [H] |  | [ ] |  | [H] |  |  |
|  |  |  |  |  |  |  | AS [ ] |  |  | [ ] | [HP | [HP] |  | [HP] | [HP] |  | [HP] |  | [HP |  | [ ] |  | [HP] |  |  |
|  |  |  |  |  |  |  | Summarize project’s major outcomes and likely impact, indicating if it met original expectations and if sustainability after completion is probable. Create incentives and opportunities in order to increase levels of Belizean exports and flow of foreign equity investment in country Briefly comment if (external) Assumptions were favorable or unfavorable for project outcomes and explain the reasons why. Assumptions favorable for project outcomes and allows BELTRAIDE to strategically refocus its activities and to deliver value added services in some areas. Assumptions have been integrated into strategic plans and agendas and serve as the basis for some core activities. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| # IV. Project Results Data |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| # IV. A Project Outcomes (Purpose) And Impact |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Outcomes (DO or Purpose in the Logical Framework) |  |  |  |  |  | # Key Delivery Performance Indicators of Outcomes: |  |  |  |  |  |  |  |  |  | # Rating of Outcomes (DO) |  |  |  |  |  |  |  |  |  |
| # Create incentives and opportunities in order to increase levels of Belizean exports and flow of foreign equity investment in country |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | VE |  | E |  | ME |  | I |  |
| Put in place new mechanisms and techniques in order to strengthen BELTRAIDE’s institutional capacity building |  |  |  |  |  | 1 Transfer of knowledge and best practices in export and investment promotion to public & private sectors |  |  |  |  |  |  |  |  |  | 1 |  |  |  |  |  |  |  |  |  |
| Transfer of best practices in trade and investment promotion to BELTRAIDE in order to foster specific export and FDI opportunities for Belizean companies |  |  |  |  |  | 2 Private sector involvement in definition of objectives and policies in trade & investment promotion |  |  |  |  |  |  |  |  |  | 2 |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | 3 Export & invetment business opportunities created and materialized |  |  |  |  |  |  |  |  |  | 3 |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | Etc. |  |  |  |  |  |  |  |  |  | etc. |  |  |  |  |  |  |  |  |  |
| Summary Effectiveness Ratings in terms of project outcomes (DO): VE [ ], E [ X ], ME [ ], I [ ] |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Criteria for classification of Outcomes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Very Effective (VE) |  |  | The project: a) achieved all the expected outcomes (indicators); b) is likely to sustain the flow of benefits initiated by the project for the target population; c) has very high probability of achieving future outcomes and impacts. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Effective (E) |  |  | The project: a) achieved most of the expected outcomes (indicators); b) is likely to sustain most of the benefits initiated by the project for the target population; c) has high probability of achieving future outcomes and impacts. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Marginally Effective (ME) |  |  | The project: a) has achieved some of the expected outcomes (indicators); b) is not likely to sustain the flow of benefits initiated by the project for the target population; c) has low probability of achieving future project outcomes and impacts. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Ineffective (I) |  |  | The project: a) did not achieve the expected outcomes (indicators); b) is not sustainable, c) is unlikely to achieve future outcomes and impacts. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Description of project results in relation with its development objectives (DO or purpose in the project Logical Framework): - Based on DO classification above, describe the achieved outcomes (effects) of the project and compare with the expected outcomes in terms of its specific development objective. Provide a brief explanation for any major differences. There has been transfer of knowledge and best practices in export and investment promotion to public and private sectors. With regards to other outcomes such as an annual increase of 5 percent in private investment and total exports, other factors impinge on these indicators such as a stable investment climate etc. - Comment on the likelihood of achieving the desirable impact (Goal in the Logical Framework) in the short and medium term (next 2/3 years) upon project’s beneficiaries, taking into consideration the expected sustainability of actions initiated by the project. Compare with the expected goals (as defined in the Logical Framework) and provide a brief explanation of differences. As long as confidence in the macroeconomic conditions improve, there is a strong probability that the impacts will be achieved given that the outputs are already in place. c) Indicate other outcomes not originally foreseen. DO served as basis for strategic refocusing of BELTRAIDE including enhancing its export promotion activities. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| # IV. B Project Outputs (Products). |
| Outputs (Components in the Logical Framework) 1.Implementation of Export Promotion Plan 2. Implementation of Investment Attraction Plan 3. Institutional Capacity Building |  |  |  |  |  | # Key Delivery Performance Indicators of Outputs: 1Priority products & destination markets selected 2 Country Image Marketing Campaign developed 3 Public-private dialogue enhanced |  |  |  |  |  |  |  |  |  | # Rating of Outputs (IP) |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | VS |  | S |  | UE |  | VU |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1 |  |  |  | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2 |  |  |  | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 3 |  |  |  | X |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | etc. |  |  |  |  |  |  |  |  |  |
| Summary Effectiveness Ratings in terms of project Outputs (IP): VS [ ], S [ X ], U [ ], VU [ ] |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Criteria for classification of Outputs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Very Satisfactory (VS) |  | The project achieved all or exceeded the expected outputs in accordance with their respective indicators within the expected quality, reasonable timeframe, and reasonable costs. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Satisfactory (S) |  | The project achieved most (say, > 65%, < 100%) of the expected outputs in accordance with their respective indicators within the expected quality, reasonable timeframe, and reasonable costs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Unsatisfactory (U) |  | The project achieved some (say, > 50%, < 65%)of the expected outputs in accordance with their respective indicators within the expected quality, reasonable timeframe, and reasonable costs. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Very Unsatisfactory (VU) |  | The project achieve only a limited number of the expected outputs (say, <50%) in accordance with their respective indicators within the expected quality, reasonable timeframe, and reasonable costs. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Based on IP classification above, describe the achievement of each outputs (products) of the project and compare them with the expected outputs in terms of its implementation progress in the Logical Framework. Provide a brief explanation for any major differences. This description should be specific and referred to each indicator included in the original or modified Logical Framework. Indicate other outputs not originally foreseen. Component 1: Professional food image campaign developed and BELTRAIDE increased its export promotion initiatives. The manuals for participation in international trade promotion events now serve as a template for guiding BELTRAIDE’s facilitation activities. Component 2: Country image branding first attempt to establish a country brand outside of that traditionally marketed by the Belize Tourism Board. Corporate Contact program remains to be implemented and this is constrained by financial resources. Component 3: Decision was taken to have the Board of Directors of BELTRAIDE serve as the key stakeholders of the Consultative Export/Investment Forum in particular because its was comprised of public and private sector representatives. In this regard, an additional achievement was setting out of mechanisms for strengthening the functioning of the Board of Directors. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| # V. External Factors That Affected Project Performance (Assumptions). |
| Project Outcomes Describe the major external factors that have either enhanced or negatively affected the achievement of project outcomes. Indicate if these factors were originally contemplated as Assumptions in the Logical Framework. High staff turnover (not anticipated Repeat changes of Ministerial portfolios and of Minister responsible for BELTRAIDE (not anticipated) |  |  |  |  |  |  |  |  | Project Outputs Describe the major external factors that have either enhanced or negatively affected the achievement of project outputs. Indicate if these factors were originally contemplated as Assumptions in the Logical Framework. High staff turnover (not anticipated Repeat changes of Ministerial portfolios and of Minister responsible for BELTRAIDE (not anticipated) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| # VI. Efficiency in Project Implementation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicate the implementation Efficiency Rating in accordance with the criteria below: HE [ ], E [ X ], I [ ], VI [ ] |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Highly Efficient (HE): |  |  |  | The project was implemented within the original schedule and budget |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Efficient (E): |  |  |  | a) Most of the components of the project were implemented within the original or revised schedule and budget, and b) the overall implementation time delay is less than 15% of the original or revised schedule and budget |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Inefficient (I): |  |  |  | a) Significant components of the project were implemented with delays in accordance with the original or revised schedule and budget, and b) the overall implementation time delays is more than 15% and less than 50% of the original schedule and budget |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Very Inefficient (VI): |  |  |  | The project was implemented with delays representing more than 50% of the original schedule and budget |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicate the major reasons that affected the efficiency in project implementation in accordance with the following criteria, and provide a brief explanation below: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| [ ] Delays in 1egislative approvals; [X ] Poor supplier/contractor performance; [ ] Qualified external audit. [ ] Lack of borrower/executing agency commitment and/or ownership; [ ] Inadequate project/component design; [ ] National Policy changes. [ ] Counterpart funding shortfall; [ ] Contract condition compliance delays; [ ] Executing agency Policy changes. [X ] Weak executing agency institutional capacity; [ ] Bank efficiency (response delays); [ ] Bank Policy changes. [ ] Community/political opposition; [ X ] Procurement difficulties; [ ] Other (please specify). [ ] Inadequate consultant performance; [ ] Inadequate cost estimates. [ ] Difficulties in inter-agency coordination; [ ] Cost overrun. |
| Provide brief explanation of the major factors affecting (positively or negatively) implementation efficiency: Initial lack of familiarity by BELTRAIDE with the Banks procedures and requirements for implementation created some delays. This included a slight delay in provision of letter of financial cash support (counterpart) from the relevant line Ministry. Campaign period for 2003 General Elections led to diluted focus by BELTRAIDE and to a period of lack of policy direction and support from the relevant Ministries of Government. Constant changes of Ministerial portfolios led to some uncertainty as to the ability to build institutional capacity. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| # VII. Sustainability Analysis |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Comment on the project sustainability after completion taking into consideration the strengthening of the a) institutional, b) technical and c) financial capacities resulting from project activities. BELTRAIDE has been able to (a) strengthen the operation of its Board as it relates to handling trade and investment matters; and (b) rationalize its approach to participation in international trade events. Sustainability unaffected at end of project as compared to that expected at beginning. BELTRAIDE still has to implement web-based fee paying services however delay may be justified by organization refocusing and restructuring. Indicate if in your view there are major internal or external factors that may affect the sustainability of the project in the future. Reduction of financial support from the Government of Belize may lead to some destabilization of BELTRAIDE in the transition period. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Considering the previous analysis, rate the probability for the sustainability of this project during the next three (3) years |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  Very Probable (VP)  Probable (P)  Low Probability (LP)  Improbable (I) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Very Probable (VP) | Most of the factors influencing project sustainability were included in the project design; during project execution there was significant progress in its institutionalization; at the project completion future actions required to ensure sustainability and a strong commitment is observed from the national authorities to maintain an ongoing flow of project outputs. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Probable (P) | Some factors influencing project sustainability were included in the project design; during project execution some efforts were made towards its institutionalization; at the project completion future actions required have been foreseen in order to ensure sustainability of the project. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Low Probability (LP) | Some factors influencing project sustainability were included in the project design; during project execution few efforts were made towards its institutionalization; at the project completion the future actions to be taken in order to ensure project sustainability, are not clear. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Improbable (I) | There are no foundations to expect project sustainability. The factors influencing project sustainability were not considered, neither during project design nor execution. No progress is observed towards the project institutionalization and no future actions required have been established to ensure project sustainability |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| VIII. Lessons Learned |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ### Provide a detailed account of lessons learned from the implementation of the project, considering critical factors that affected the design,, approval, negotiation, execution, monitoring and completion of the project.. In this analysis, consider a) technical, b) institutional and c) operational factors related to the project, as well as external factors that affected project performance. In addition, make recommendations for the improvement of future project design and execution, specifying measures and actions to improve project performance and results, as well as those for strengthening project supervision and monitoring. The level of staff turnover within BELTRAIDE coupled with the constant changes in Ministerial portfolios and hence with the Minister responsible for BELRTAIDE led to some uncertainty as it relates to institutional capacity building. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Provide a summary of the Final Report of the Executing Agency, emphasizing results obtained and lessons learned and action to be taken to ensure project sustainability, as well as its own evaluation of the Bank’s performance. Include said report as an Annex IX. Completion Report of the Executing Agency. |
| X. Other Annexes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Include any other document that may contribute to a better understanding of the development results of the project. See Final Evaluation Report. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |