Final Evaluation Report

Technical Cooperation Agreement

Capacity Building for Trade and Investment Promotion

(TC-01-07-01-05)

Implementing Agent: BELTRAIDE

Submitted by Marion Cayetano

RME Consultants Group

1st July 2005

Table of Contents

Introduction	3

The IDB/BELTRAIDE Technical Cooperation Agreement	3

The Evaluation	4

The Tasks of the Evaluation	4

The Methodology of the Evaluation	5

The Political, Social and Economic Context of the Project	6

Reliance on the ‘Big Three’	7

Belize’s Markets	7

BELTRAIDE	7

The Project Design	8

The Project Assumptions	11

Project Management	12

The Project Outputs	14

The Consultative Export and Investment Promotion Forum	19

Selective Foreign Direct Investment Pre-Feasibility Studies	20

Implementation of the Export Promotion Plan	20

Investment Attraction Plan	21

Institutional Capacity Building	22

Procurement of Consulting Services	24

Lessons Learnt	24

Conclusions	25

Recommendation	26

# Introduction

Belize Trade and Investment Development Service (BELTRAIDE) is a statutory institution governed by a Board of Directors, the principal policy-making organ. The Board is made up of representatives from the private sector, Government and Civil Society.

Belize Trade and Investment Development Service (BELTRAIDE), is committed to offering local and foreign investors the services of a one-stop center for investment and trade activities. The Investment Attraction, Export Promotion, Business Facilitation and Trade & Research departments strive to respond to requests, inquiries and needs of investors and business persons.

BELTRAIDE’s Mission is ‘to foster economic growth by creating the conditions that are conducive to local and international investment, job creation and national development.  Its policy is to promote investments that create job opportunities and increase foreign currency earnings for Belize.

BELTRAIDE's main objectives are:

- Attract and facilitate new investments.

- Efficiently manage the Fiscal Incentives Program for the Government of Belize.

- Identify new non-traditional export products and markets, while supporting traditional exporters.

- Tender advice and recommendations to the Government on trade promotion

- Develop trade policies and participate in trade negotiations

- Provide accurate, timely data and research on trade matters

# The IDB/BELTRAIDE Technical Cooperation Agreement

On November 13, 2002 the Ministry of Budget Management, Investment and Home Affairs and the Inter American Development Bank signed an agreement granting non-reimbursable resources for the Technical Cooperation “Capacity Building for Trade and Investment.  The overall goal of the program was to create incentives and opportunities to increase the level of Belizean exports and inflow of direct foreign equity investment into the country.  This goal would be achieved through the strengthening of BELTRAIDE’s capacity to effectively reach and fulfill the promotional needs of actual and potential exporters and small and medium sized Belizean Companies and to attract foreign investment into the country.

The overall project was divided into three related, and to some extent, overlapping components, each with its own objective.  They are:

Implementation of an Export Promotion plan

The objective of this component was to contribute to the increase in Belizean Exports by stimulating foreign market’s awareness of Belizean products and services

Implementation of an Investment Attraction Plan

The objective of this component was to expand awareness of Belize as a potential foreign direct investment (FDI) destination by focusing on selected priority industry sectors and high-value added services.

Institutional Capacity Building

The objective of this component was to increase the efficiency and effectiveness of the services delivered by BELTRAIDE

The project was scheduled for completion in November of 2004 but because of delays with the first disbursement, the completion date was amended to April/May 2005.

# The Evaluation

In accordance with the Technical Cooperation Agreement, the Bank contracted a consultant to conduct an evaluation of the project.  The purpose of the evaluation is to determine the extent to which the project goals and objectives were met; to determine the existence of any unforeseen obstacles and opportunities that influenced the project outputs and outcomes; to outline and examine lessons learnt in associated with project design and execution; and to make recommendations for consideration in successor projects.

## The Tasks of the Evaluation

The consultant was to carry out the following tasks:

- Assess the extent to which the political, social and economic context of the project is still relevant.

- Determine project relevance based on the original design, assumptions, outputs and expected impacts

- Assess the efficiency of project management with particular focus on Standards and quality control; cost and cost control; human resource deployment and utilization

- Assess the timeliness with which contractual requirements under the Technical Cooperation agreements were met as well as the quality of the reports submitted to the Bank

- Assess the effectiveness and efficiency of inter-agency communication, collaboration ad general support with special emphasis on support from the bank; private sector agencies; and other public sector agencies

- Analyze and evaluate the effectiveness of project execution based on the extent to which the goals and purpose were achieved.  The consultant will seek to establish if the outputs were as expected; if the output achieved led to fulfillment of the purpose and if purpose realization contributed to the project’s goal.

- Assess project execution as it relates to the procurement of consultancies services, performance of consulting firms, the overall management of the consultancy and the timeliness and usefulness of outputs delivered by the consultants

- Review the extent to which the goals and verifiable indicators as outlined in the project’s logical framework were met; appropriate; realistic. Review the project to gauge the impact and effect of the project, both planned and unplanned.  Evaluate why anticipated effects and impacts were not achieved.

- Determine the timeliness and effectiveness of the provision of counterpart resources as stipulated under the Technical Cooperation Agreement.

- Determine the effectiveness of transfer of knowledge from consultants to BELTRAIDE’s staff and other project stakeholders.

## The Methodology of the Evaluation

The consultant used a combination of desk study and interviews to assess the technical cooperation, and come to the conclusions of the evaluation.  The major part of the time was spent reviewing the project files.  This included the products of the Technical Cooperation Agreement, contracts, correspondence with the Bank, and with consultants, progress reports and other related project documents.  Given that BELTRAIDE was the executing agency and the primary beneficiary, BELTRAIDE documents that were not directly the product of the Technical Cooperation agreement were also reviewed.

After the review of project documents the consultant carried out some face to face and telephone interviews with BELTRAIDE staff, executive Director and Board members as well as with other parties in the private sector.  The purpose of the interviews was to get clarification on conclusions drawn from the files and to discuss issues related to project implementation and project follow-up.

Once the interviews began the process became iterative; after conversations with people associated with the project there would be more review of the files followed by more questions.  Some people were interviewed multiple times and others just once.  In general, no notice was given to the staff and others associated with the project prior to discussion with them.

The primary reason for reviewing the files before discussions began with the staff and others associated with the project was to be informed about project implementation and to make a judgment about how well the paper trail captured the sequence of events.  The interviews were useful because they were done after the consultant had become familiar with the project through the project document and the paper trail of project implementation.

# The Political, Social and Economic Context of the Project

At the time that the project, which formed the basis of the Technical Cooperation Agreement for Capacity Building for Trade and Investment, was being formulated, Belize was described as a small open economy, endowed with abundant natural resources and with a rapidly growing population.  The country was facing the phasing-out of preferential market access to the United States of America and European markets.  It was projected that Belize would be facing significant challenges over the ensuing three to five years as a result of the threat to its major export markets and it’s sourcing of new foreign investments.  There was a need to take action to adapt to and benefit from global and increasingly liberalized trade and investment patterns.  One of the solutions identified was for Belize to improve its capacity to expand trade and attract foreign investment.

The projections with respect to loss of preferential markets are coming to pass and there is increasing competition for direct foreign investment from neighboring countries.   The need to expand exports and attract new foreign investments continues to be relevant.  During the time that this evaluation was being conducted the European Union announced that it would be reducing the price for sugar by 39% over the next four years being this year.

## Reliance on the ‘Big Three’

At the time of project formulation, Belize’s export situation was characterized by excessive reliance on the ‘big three’ agricultural commodity products (bananas; citrus products; sugar) for almost 60% of exports.   While the ‘big three’s’ proportion of exports had decreased from about 71% of exports it was still significant.  Seafood and other agricultural produce had become significant contributors to the economy and were though to have potential for continued growth in export value.

## Belize’s Markets

In terms of market, Belize was seen to be reliant on the United States of America and the United Kingdom which together accounted for 72% of Belize’s export.  While it was expected that these would continue to be important markets there was a need to expand the market base

There was a need to expand the range of goods and services that Belize exports and the markets to which it sells its exports.  This need for expansion in export products and services continue to be relevant today.

## BELTRAIDE

BELTRAIDE was established by the BELTRIDE Act in April 2000, as an autonomous institution.  It is an Arm of the Ministry of Investment which evolved out of the Trade and Investment Promotion Service (TIPS), established in 1997-1998.  BELTRAIDE and its predecessor, TIPS, were envisioned to be a one-stop-shop for local and foreign investors and entrepreneurs who were interested in production and provision of high-value service.  ‘TIPS’ was designed to be the source for all trade and investment information and facilitation.  It sought to liaise between the government and investors; in effect, being a conduit for all trade and investment information.    BELTRAIDE redefined and broadened the scope of TIPS.  It was established to provide broad policy guidelines on export and investment promotion; rationalize, streamline, and strengthen the export and investment promotion service; provide a mechanism for implementing an export expansion program for non-traditional exports; establish Belize as a reputable exporting country; perform the functions and duties of an official trade and investment promotion organization in and for Belize; and supply Belizean industries with timely and reliable trade information on a continuous basis.   It provided for the participation of private sector and civil society in decisions related to trade and investment promotion.   The Board of Directors is the principal policy-making organ.

The Government of Belize remains committed to developing its export products and services and its export markets.  It is also committed to increasing new foreign direct investment in the country.

The business community sees the importance of a concerted effort at product development, the improvement of market readiness and the attraction of direct foreign investment.  They, like the government saw the IDB/BELTRAIDE Technical Cooperation agreement as relevant and timely.  The project remained relevant throughout its implementation because the issues that it was meant to help Belize address continue to challenge the country.

# The Project Design

A logical framework was developed for the project that underpinned the technical Cooperation Agreement.  The project had three components with an objective for each. A set of activities and deliverables were identified for each component.

Overall, the project deliverables were met.  The overall indicators of success listed in the logical framework are:

- Transfer of knowledge and best practices in export and investment promotion

- Private sector involvement in the definition of objectives and policies in trade and investment promotion

- Private sector demand for BELTRAIDE services

- Export and investment opportunities created and transactions materialized

There weren’t any timeframe attached to the overall indicators.  However one can assess the extent to which they were achieved.  From the discussions with various people involved with project implementation, or associated with the project in some way, and from a review of the project files one can say that the first two indicators were clearly achieved; i.e. there was transfer of knowledge and best practice in export and investment promotion, and their was private sector participation in the definition of Belize’s priorities.

A review of the activities and the products of the project suggest that most were geared toward enabling BELTRAIDE, and to provide opportunities for private sector buy-in.  The staff at BELTRAIDE are of the opinion that they are better equipped to carry out their functions; both in terms of knowledge, and materials for use in export and investment promotion.  The staff played a key role in the production of the tangible products of the project and in the best practice research.

There was significant consultation with the private sector in the identification of the priority sectors and industries for investment.  They helped to set the criteria for selection and policies and approaches used to complete the task.  They also participated in discussions related to the logo, slogan.  It seems clear that the private sector is on board.

The staff and Board of BELTRAIDE and the private sector own the priority sector study and the branding and market image that has been developed.  There is a confidence that has developed and the people that work there are of the opinion that they know what they are about and what they should be doing.

The other two indicators; private sector demand for BELTRAIDE services and export and investment opportunities will take longer than the life of the Technical Cooperation to be realized.  In addition, it will require that additional investments be made to truly realize them.  It is clear that some of the tools required to see demand for BELTRAIDE’s services and to see export opportunities created and investment realized are now in place.  However, those tools will need to be put to work before those indicators can truly be measured.

The above notwithstanding, BELTRAIDE is providing some services for a fee, and is generating revenue through this medium.  However, there is potential to expand the basket of services that it provides and increase the revenue generated.  Indications are that efforts will be made to increase the revenue generation potential of BELTRAIDE.

There is work that has been done toward the attraction of new direct foreign investment into Belize.  The priority sectors for investments have been identified, and an initial list of priority industries has been developed.  Investment plans have been prepared for the hot pepper and for furniture making and BELTRIADE intends to prepare similar plans for other industry.  Along with this, an initial list of potential investors has been compiled by BELTRAIDE.  It is now in the process of reviewing the list and identifying those who could be a good fit for Belize and pursue them.  Given the aforementioned, one can say that the underpinnings for an investment attraction program is in place but has not yet been worked to yield a return.

Summary comments about the overall goal of the project as outlined in the Logical Framework for the Technical Cooperation agreement are presented in the table below.  It shows that strides were made toward the overall goals but that the products of the Technical Cooperation will need to be put to work to achieve the overall goals.

Summary Comments on the Goals and Indicators of the Technical Cooperation

| Goal | Indicators | Source of Verification | Comments |
| --- | --- | --- | --- |
| Create incentives and opportunities in order to increase the level of Belizean exports and inflow of foreign equity investment into the country | Transfer of Knowledge and best practices in export and investment promotion | Some tangible products of the technical cooperation included an investment attraction plan, and an export promotion plan | Both the IAP and the EPP ptovide the fundamental tools to increase exports and direct investment through promotion. They have not yet brought any direct results but have the potential to do so if the requisite investment is made and the tools are applied. |
| Put in place new mechanisms and techniques in order to strengthen BELTRAIDE’s institutional capacity in export and investment promotion | Private sector involvement in the definition of objectives and policies in trade and investment promotion Private sector demand for use of BELTRIDE services | This Indicator does not measure if new mechanisms and techniques in export promotion was adopted by BELTRAIDE This demand will grow as BELTRIADE demonstrates its competence to promote exports and attract FDI. The Technical Cooperation (TC) did not bring this about during its implementation. BELTRAIDE will need to apply the tools developed during the TC to grow the demand for its services | The private sector participates in export promotion with BELTRAIDE. A promotion kit was developed and capacity to do export promotion and participate in trade shows was developed. The staff at BELTRAIDE demonstrated a level of confidence that implies that capacity was developed. The export promotion approaches provided by the consultants were tested and accepted as valid by the BELTRIADE team. The issue now is financing to utilize the approaches adopted. |
| Transfer of best practices in trade and investment promotion to BELTRAIDE in order to foster specific export and FDI opportunities for Belizean Companies | Export and investment business opportunities created and transactions materializes | Capacity to promote export and investment was developed. BELTRAIDE’s team participated in the development of the food image and country image for Belize. They have not been able to utilize the products of the technical cooperation to attract FDI or to promote exports. Financing for implementation is lacking. | The promotional materials were produced but there is need for financing to really make use of the tools that the Technical Cooperation provided. |

## The Project Assumptions

Three overall assumptions were made with respect to the project.  These are:

- Trade and investment promotion remains a top public policy priority.

- The joint participation of the public sector, private sector, and civil society in trade and investment promotion remains dynamic and catalyzes increased involvement.

- Readiness of Belizean productive and service industries.

The first two assumptions continue to hold true; expansion of trade and increase in new direct foreign investment continue to be a priority.  The country needs all the foreign exchange that it can earn and it needs to attract direct foreign investment to couple with local investors and entrepreneurs to expand production.  BELTRAIDE is serving as the public sector – private sector link.  The confidence that BETRAIDE is generating is fostering more cooperation.

With respect to the readiness of Belizean products and service industries, there is need for more work for this to hold true.  Some products are export-ready and are making it into the markets, but many need to be improved and packaged for export.  Work is needed to get the potential exports ready for the market.

# Project Management

The project which underpinned the Technical Cooperation Agreement was managed by a project manager.  The project manager operated at the same level as the division managers and reported directly to the Executive Director.  The division managers, the project manager and the executive director formed the Project Management Team.  Together they led the project implementation. The Project Management Team reported to the Project Guidance Team, who was also the Board of Directors of BELTRAIDE, through the Executive Director.  From that perspective, one can say that the management team and by extension there staff was very involved in the project.  The records also show that the Board is conversant with the project and participated in the discussions that led to many of the final products.

The reporting, contracting of consultants, and coordination of the project activities was the responsibility of the project manager.  The project manager was hired in November 2002 and served for the life of the project.  He is currently in discussion with BELTRAIDE to coordinate the formulation of a national export promotion strategy.  The Strategy will take some of the products of the Technical Agreement and dialogue with producers about the course of action that can be taken to develop and expand export and attract direct foreign Investment.

The project manager demonstrated commitment to the project and did what was within his power to ensure that the project objectives were achieved.  He was provided the support required from BELTRAIDE and from the Inter American Development Bank.  In the end, the project achieved its immediate objectives; capacity building and institutional strengthening of BELTRAIDE and introduction of best practices in the areas of export promotion and attraction of direct foreign investment.

The project was scheduled to begin shortly after signing.  The first disbursement was delayed by about six months. The records are not absolutely clear about why the delay occurred however it would seem that there were issues related to conditions prior to first disbursement.  The first disbursement was made in May of 2003.  Once the first disbursement was made, the project began to flow relatively smoothly.  One extension to the Technical Cooperation Agreement of six months was requested.  The justification was that more time was needed to complete the project.  The bank gave its ‘no objection’ so the project ended in May 2005 rather than November 2004; approximately twenty-four months after the first Disbursement.

Overall, the project was well managed.  Most of the project outputs were realized and there is general satisfaction within BELTRAIDE (Staff and Board) about project implementation and its accomplishments.  The staff and Board are of the opinion that the Technical Cooperation contributed significantly to the growth and development of BELTRAIDE.  Furthermore, they have taken ownership of the benefits of the project and have managed to integrate them into the work of the various divisions.

A related issue is the level of effort required from BELTRAIDE’s staff to complete the products of the project.  There is a general belief in Belize that if one hires a consultant there should not be any need for in-house work.  This belief is a fallacy.  The reality is that to get the best value from a consultant, the client must engage in the works if they are to take ownership of the products that result from the works.

The staff at BELTRAIDE is satisfied with the quality of the completed works but was of the opinion that they carried a significant share of the workload to achieve the quality received.   Whether it was an unfair share or not, the staff has taken ownership of the products, and feel competent to carry out BELTRAIDE’s mandate.  The production of the works resulted in some strategic thinking on the part of BELTRAIDE’s staff and board and consequently, there is a renewed energy and a high level of confidence, and in general, one can say that there is a renewed focus on what needs to be done to expand trade and investment for the benefit of Belize and Belizeans.

There was some staff turnover at the onset of the project.  This could have had negative impacts on the project.  The project manager warned that such turnovers could jeopardize the project and from the paper trail one could conclude that he insisted that mitigating actions to offset the negative impact that staff turnover could have on achieving the expected outcomes of the project.

In hindsight, the potential negative impacts were mitigated and the current team at BELTRAIDE was involved in producing the project outcomes.  They have taken ownership of the project products and feel competent in their abilities to utilize them.  Most of the current staff (especially the senior staff) were at BELTRAIDE for at least half of the life of the Technical Cooperation Agreement and there.  The staffing situation has been stabilized and the current team is committed to the mission and goal of BELTRAIDE.

Less mentioned but also important was the changes in ministerial portfolios in the Government.  At the signing of the agreement BELTRAIDE fell under the purview of the Minister of Finance, Home Affairs and Investment.  Over the life of the project the Minister responsible changed three times.   These changes did not seem to have a negative impact on project implementation.  This could suggest that the Ministers provided BELTRAIDE the autonomy it needed to carry out its function.  It could also mean that the project management team, under the leadership of the Executive Director were in full control of the project and were implementing it in line with the logical framework and the technical cooperation agreement.

One could also say that the project remained relevant throughout its implementation and given the financial challenges that Belize faces and the global context where trade liberalization is the trend, continue to be relevant.  Now more than ever, Belize needs to expand trade.  It needs to increase exports and attract new direct foreign investment.

# The Project Outputs

The project underlying the Technical Cooperation Agreement had several tangible outputs in the three components of the project.  The key outputs by components are:

Component 1: Implementation of an Export Promotion Plan

- Priority Export Sectors selected

- Development of a Food Image Marketing Program

- Strategic Assistance for participation in international export promotion activities

- Development of market information supply capability

Component 2: Implementation of an Investment Attraction Plan

- Priority Sectors for investment selected

- Country Image Program

- Corporate contact program

- Selective Foreign Direct Investment pre-feasibility studies elaborated

Component 3: Institutional Capacity Building

- Consultative Export and investment promotion forum created

- Training program for Foreign Service Officers

- BELTRAIDE’S Website

Most of the tangible outputs identified in the logical framework of the project were completed.  The table below shows which consulting firm or individual undertook the various consultancies to produce the outputs.

| Objectives | Indicators | Verification | Comments |
| --- | --- | --- | --- |
| Component 1 Contribute to increased Belizean exports by stimulating foreign markets’ awareness of Belizean products and services | EPP is implemented jointly with international consulting firm, BELTRAIDE, and private sector | The Export Promotion Plan was prepared and the various parties had the opportunity to participate in the process. | BELTRAIDE demonstrates an ownership of the plan. They own the country image and the food image |
|  | Priority products, services and destination markets for Belizean products are selected | A promotion kit was developed and tested. A list of priority trade shows was developed and the confidence to use the promotional materials exist within BELTRAIDE | BELTRAIDE needs to plug away at export promotion to leverage the investment made so far in capacity building and identification of destination markets. |
|  | Professional food image marketing campaign developed | A food image has been developed and accepted. It now has to be used in the export of food products | BELTRAIDE is carrying a set of internal discussion to make decisions on how to use the country and food image to promote Belizean exports. |
|  | Annual trade event strategic assistance reports developed | The promotion kit is in place and is being used. | BELTRAIDE has a list of trade events that it wants to attend each year. The list is based on the destination market, the products being promoted and the cost of participation. There isn’t sufficient financing within BELTRAIDE to attend all the trade events that would be beneficial. |
|  | Annual market information supply inventory developed | Market information is being developed by BELTRAIDE. Information collected so far is not generally available to the public. | Building such a database takes some time and effort It need to be linked to exports that are being promoted or will be promoted |
| Component 2 Contribute to expand awareness of Belize as a potential FDI destination by focusing on a few selected priority industry sectors and high value-added services. | Priority industry sectors and geographical target markets for potential FDI sources selected | Priority industry sectors were selected. It was a participatory process. Priority destination markets were also selected. | The industry is dynamic and the list will not always remain the same. There is a need to work the current list and there will be a need to revisit the list within a few years. |
|  | Professional country image marketing campaign developed | A Country Image campaign was developed but has not yet been implemented. All the materials for the campaign have been finalized. There is a need work those materials. | Financing of the campaign is a limiting factor. The team at BELTRAIDE are currently strategizing on how they could effectively use the country image and food image campaign that was developed under the TC. |
|  | Strategic partnership between BELTRAIDE and Selected Investment bank undertaken |  |  |
|  | Five sector specific investment projects are completed | These have not yet been prepared. The original thinking was that those interested in the particular sector would help to finance the preparation of the investment projects | In hind sight, these need to be prepared by BELTRAIDE and used in the pursuit of FDI. There is a need for that kind of preparatory work to complement the corporate contact program. |
| Component 3 Contribute to increase the efficiency, effectiveness and sustainability of the services provided by BELTRAIDE | Institutional trade and investment promotion public-private channel implemented | The project envisioned a forum for dialogue between the public and private sectors. During implementation it was decided that The Board of Directors of BELTRAIDE provided the best opportunity for a forum. The board has public and private sector representation. Furthermore, private sector representatives come have from membership organizations. | It has since been recognized that the tourism industry is not represented on the BELTRAIDE Board. Recommendations are being made for changes in the BELTRAIDE /Act to include public sector and private sector tourism representation. |
|  | Commercial and promotional responsibilities of FSO expanded | Modular training program for the training of FSOs is being finalized. One training session (in which the draft materials were used) was held during the period of the TC. This was led by the consultants. BELTRAIDE staff gave feedback to the materials and they were revised to reflect the issues that were raised. | The final draft is now available and the intent is to work with the Ministry of Foreign Affairs to train FSO. The long term is for commercial attachés to have the competence through training and support materials from BELTRAIDE. BELTRAIDE see the use of FSO as a viable strategy to support the direct promotion work that they do. It is not clear how the training itself would be delivered on a sustainable basis. The use of a training organization (college/ university/ institute) may provide the opportunity to build sustainability. |
|  | Information and communication technologies utilization for information and training service delivery | There is a website that was developed under the project. It was built during the project while the other products were being produced. A new site is being built that reflect the new look of BELTRIADE. The new site, developed under the project will replace the current site on the same domain. It not clear what the timeframe for replacement is. Nothing was seen on the use of distance learning technology. | There is a myriad of other technological applications that could be considered by BELTRAIDE. Video Conferencing, the use of smart boards, and the use of a Geographic Information System to house their database are some examples. |

While most of the project outputs were produced, some took longer than previously anticipated and some required a higher level of input and participation by BELTRAIDE staff than was initially anticipated by those involved in project implementation and those whose competencies were to be expanded during the course of project implementation.  One project outputs was modified and one was not undertaken.  The Consultative Export and Investment Promotion Forum output was modified to a Board Development Kit, and the Selective Foreign Direct Investment Pre-Feasibility Studies was not undertaken at all.

## The Consultative Export and Investment Promotion Forum

No documentation of the justification for the change from a consultative forum to board development was seen however there is evidence that a discussion or series of discussions triggered the change.  A likely explanation was that the change evolved; it did not occur in a single moment.   Whatever the specific reason, in the end, a Board development kit was prepared instead of the development of a consultative forum.

In hindsight, projects like these should pay attention to Board development, because the long term success is contingent on a strong and committed Board.  The BELTRAIDE Board is particularly challenging, because most of the seats are filled by organizations (Government Ministries and Business umbrella organizations).  There is also a seat appointed by the Minister.  Change at the head of the representing organizations is reflected in the actual composition of the Board of Directors of BELTRAIDE.  This means that faces on the board can change during the term of a Board.  For this and other reasons, there is value in consciously working on Board development.

The Board development kit has not been used much since its formulation.  Nonetheless it is potentially a useful tool for building commitment to the ideals, and aspirations of BELTRAIDE and for rallying the Board to drive the development of exports and investment in Belize.  A strong Board can create a more sustainable consultative forum.

## Selective Foreign Direct Investment Pre-Feasibility Studies

It was envisioned that studies targeted at potential corporate investors that have shown commitment to invest in Belize and have shown interest in joint ventures or strategic alliances with local companies would share the cost of the elaboration of the pre-feasibility studies.   The early thought was that the Corporate Contact Program would identify such potential investors.

Given the magnitude of the development program that was undertaken in the technical Cooperation Agreement it was not feasible to carry out the pre-feasibility studies within the timeframe provided, i.e. twenty-four months, especially if potential investors were to co-finance the studies.  It is recognized that these studies are important and they will need to be done.  BELTRAIDE may need to invest in developing the relevant ones and recover the cost by attracting new direct foreign investments.

## Implementation of the Export Promotion Plan

The objective of this component was to contribute to the increase in Belizean exports by stimulating foreign markets’ awareness of Belizean products and services.  The plan included the selection of priority export sectors; development of a food image program; participation if export promotion activities and development of market information supply capability.  Three consultants and the staff at BELTRAIDE were involved in the implementation of the Export Promotion Plan: A-Z Information Jamaica Ltd. Led the selection of the priority export sectors; B G 
Consulting led the development of the food image program; and Mr. Joachim Eissler led the strategic assistance for participation in export promotion activities.  Interns were hired to assist with the development of market information supply capability.

The priority sectors were selected, a food image marketing program was developed and strategic assistance in export promotion was provided.  A priority export sector report now exists.  It is being used to guide the selection and development of export products.  A food image program now exists.  It was developed in conjunction with the country image program.  Both will need to be utilized over the next three years to really produce fruits.  There is more capacity to carry out export promotion activities and an export promotion kit for export promotion has been produced.  It is used being used by BELTRAIDE in export promotion.

Market information has been collected for hot peppers and for furniture manufacture.  Plans are underway within BELTRAIDE to carry out similar work for other products and markets.

Overall, this component has produced the outputs anticipated in the logical framework.  The products have provided a foundation on which BELTRAIDE needs to build.  The products, of themselves are not sufficient for the implementation of the export promotion plan.  With the help of the Commonwealth Secretariat BELTRAIDE will be using some of the products of the IDB/BELTRAIDE Technical Cooperation Agreement in the formulation of a National Export Strategy for Belize.  It is expected that the strategy will have national buy-in and that their will be a continued and growing commitment toward export promotion among Belizeans.

## Investment Attraction Plan

The objective of the investment attraction plan was to expand awareness of Belize as a potential foreign direct investment (FDI) destination by focusing on a few selected priority industry sectors and high value-added services.  The Investment attraction Plan (IAP) would target a carefully selected list of foreign corporations in priority sectors and strategic countries focusing on Belize’s environmental strengths, political stability, and quality of life among other variables.

The priority industry sectors formed the basis for the Investment Attraction Plan.  A-Z Information Jamaica Ltd. did the selection of priority sectors for investment while BG consulting prepared the Corporate Contact Program and the Country Image Program.  It seems that BG Consulting also did an assessment of priority industries for investment as part of its work on developing the Corporate Contact Program.

With respect to the Corporate Contact Program, the objective was to identify corporations that had the potential to make direct foreign investments and to initiate a process through which some of these corporations would come to Belize to invest.  Experience has shown that it takes about two years from the first contact with a potential investor to the time when an investment flow begins.

An initial list of potential contacts has been compiled and it is now being reviewed to identify those that could have a fit with Belize.  Those who could make a good fit will be pursued for discussion with the intention of getting a subset of them to actually invest in Belize.  BELTRAIDE seems to be committed to continuing with the work started in the Corporate Contact Program.

The execution of a corporate contact program requires significant resource commitment from BELTRAIDE because the cost of such programs is high. The primary barrier that BELTRAIDE will face in implementing the program will be their ability to dedicate sufficient human resources to the project. The Investment Promotion staff has a good understanding of the local economy, but their responsibilities in the processing of fiscal incentives takes away from their ability to focus on other investment promotion activities. Another barrier that BELTRAIDE will face in implementing the program is the high cost of mailings and long distance phone calls that are required for such a program. A direct marketing campaign can be a useful method of targeting, but conducting such a campaign from Belize would be expensive however, BELTRAIDE could work in conjunction with the Belizean diplomatic offices or a private firm in the target market.

The Country Image program is an integral part of the Investment Attraction Plan.  It includes the establishment of a market profile and positioning of the country to make potential foreign investors aware of Belize as an investment possibility.  This component of the IAP was successfully completed.

Overall the outputs for Component B of the Technical Cooperation Agreement were accomplished.  The exception is the Selective Foreign Direct Investment Pre-Feasibility Studies.  The pre-feasibility studies continue to be important and will be produced by BELTRAIDE.  These outputs now need to be worked to accomplish the broader objective of attracting direct foreign investment into the country.

## Institutional Capacity Building

Every aspect of the Technical Cooperation Agreement has contributed to capacity building within BELTRAIDE.  The purpose of this component

The Website is up and operating but not yet functioning as a virtual one-stop shop.  It seems to still be a work in progress and there is an urgent need to complete it.  The staff at BELTRAIDE sees the value of it and has given their feedback to the existing site.  The developers need to take the feedback into consideration and complete the revision.  Once completed, there need to be clear provisions for maintenance and update of the site.  It is not clear that these provisions are already in place.

All the other products of the project have been completed.  A major challenge in the process was getting the right consultants/consulting firms.  At times to pool to draw from seemed thin and at other times, the amounts allocated for consulting services was less that the cost that the market for such goods could bear.  Despite these challenges, the overall project was within budget.  However there was some reallocation of funds between line items.

Project Outputs and Consulting Firm

| Consultancy | Firm | Start date/Delivery date |
| --- | --- | --- |
| Component 1 |  |  |
| Priority Export Sectors selected | A-Z Information Jamaica Ltd. |  |
| Development of a Food Image Marketing Program | BG Consulting |  |
| Strategic Assistance for participation in international export promotion activities | Mr. Joachim Eissler | Feb 2004/May 2004 |
| Development of market information supply capability | None |  |
| Component 2 |  |  |
| Priority Sectors for investment selected | A-Z Information Jamaica Ltd. | Nov 3rd 2003/ |
| Country Image Program | BG Consulting |  |
| Corporate contact program/Investment Attraction Plan | BG Consulting |  |
| Selective Foreign Direct Investment pre-feasibility studies elaborated |  |  |
| Component 3 |  |  |
| Consultative created (This became a Board Development Kit) | Mr. Joachim Eissler | Mid May 2004/Mid June 2004 |
| Training program for Foreign Service Officers | BG Consulting |  |
| BELTRAIDE’S Website and virtual one-stop-shop | Naturalight Productions Ltd. |  |

# Procurement of Consulting Services

As shown in the table above, several consultants were contracted to produce the project output.  The Limited International Tender process was used to select the consultants.   Several consultants submitted proposals for more than one output.  Only two consultants were selected for more than one of the outputs.  The Bank gave its no objection for all the consultants and accepted all the reports.

The consultants worked very closely with the Project Manager and the Technical Coordinators.  Staff from the various divisions also worked with the consultants as necessary to ensure that the products were as good as they could be.  None of the consultancies were terminated before completion.

The outputs were generally of good quality though most took longer than the timeframe originally agreed to.  Nonetheless they were completed within the timeframe of the project.  All the products can be built on by BELTRAIDE and are immediately useful.  As a set, the outputs place BELTRAIDE in a good position to pursue its mandate.

# Lessons Learnt

  - Technical Cooperation Agreements can facilitate capacity building if they are well thought out and if the counterparts participate in the capacity building process.

  - Strong leadership is required if the expected outcomes of the project are to be achieved.  This was the case with the IDB/BELTRAIDE Technical Cooperation Agreement.  The Project Manager was diligent about achieving the objectives of the project and was committed to seeing the project through.  It would have been easy to drag him into other BELTRAIDE Tasks to the detriment of the project.  The project manager insisted that his role was to coordinate the implementation of the capacity building project.

  - The beneficiary organization needs to put the mechanism for project management and project implementation in place and support it.  For Technical cooperation agreements to work the beneficiary organization needs to commit resources and personnel to the process.  In the case of BELTRAIDE, counterparts were assigned, and they and their team needed to contribute to the development of the products of the project.  Members of the staff were of the opinion that the consultants should have done most of the work but along the way they realized that they needed to do their share if they were to get quality and relevant products, take ownership of the products, and integrate them into the work of the organization.

  - For a Technical Cooperation to be successful the underlying project must help the beneficiary do its work better.  It has to be relevant to the beneficiary.  This is the case with the IDB/BELTRAIDE technical cooperation.  It has helped BELTRAIDE to rethink its role and the options that it has to carry out its mandate.  All of the outputs are relevant to BELTRAIDE’s work.  It has also helped to build confidence among the staff and within the whole organization.

  - Beneficiaries of non-reimbursable grant financing must be ready to use the grant and must demonstrate their commitment.  How the commitment is demonstrated can vary, but it must be unequivocal.

# Conclusions

Overall, the IDB/BELTRAIDE Technical Cooperation was successfully implemented.  The outputs were produced at a quality that makes them useful and there was a transfer of best practice, and competence in export promotion and the attraction of direct foreign investment to the BELTRAIDE staff as a result of the implementation of the Capacity Building for Trade and Investment project.

While the project was clearly relevant to BELTRAIDE, and while it was meant to position the organization to better promote exports and attract direct foreign investment there were some constraints.  Important among those is that it was sometimes difficult to allocate the level of staff time required to produce the outputs.  This situation was exacerbated by the notion that the consultants are hired to carry out certain tasks and therefore they should get on with it with little participation by the client.  It should be pointed out that the notion that consultants should deliver quality without the participation of the client is not unique to BELTRAIDE.

The project manager played a key role in ensuring that the project underlying the Technical Cooperation Agreement was a success.  His diligence and work ethic was exemplary and it made a difference.  He was able to dedicate the time needed to manage the consultants and coordinate the input of BELTRAIDE’s staff in project implementation.   Over the duration of the project the BELTRAIDE staff became more and more involved in project implementation and there has been a cultural shift toward higher participation with consultants in the production of project products.

Now that the project has been completed, and most of the products were produced, BELTRAIDE is now positioned to carry out its mandate.  Resources to carry out that mandate constitute a critical issue.  Investment attraction, and export promotion are costly business.  At the same time they are critical if BELTRAIDE is to maintain credibility.  Given the financial challenges that Belize faces, it is unlikely that the Government will be able to provide the level of financing required to utilize the products of the technical cooperation to continue the work at the level necessary to promote exports and attract direct foreign investment.  Without the financial resources BELTRAIDE may be forced to continue with the regular work of processing fiscal incentives.  The primary issue that BELTRAIDE faces is the amount of time spent processing fiscal incentive applications, compared to the amount of time and effort that should be spent on export promotion and the attraction of FDI. While the fiscal incentives are indeed a measure meant to promote investment, the processing of these applications is mundane work that requires a different skill set than that required in the more proactive trade and investment promotion activities on which the Technical Cooperation focused. Ideally, the export and investment promotion staff should be completely freed from the task of processing fiscal incentives.   This can only happen if there is financing to carry out the corporate contact program, export promotion and helping producers to make their products export ready.

It came across clearly that BELTRAIDE wants to carry out the proactive work of export promotion and investment attraction as perceived in the Technical Cooperation Agreement and are currently developing a National Export Strategy using the products of the capacity building project and a process of national consultation.  This strategy should be completed before the end of 2005.  However, as mentioned earlier there is a need for financial support to carry out the Corporate Contact Program and the Export Promotion Activities in the priority sectors.

# Recommendation

Given the success of the Technical Cooperation, the enthusiasm among the BELTRAIDE staff, and the financial challenges that Belize currently faces; and given the team stability that currently exists at BELTRAIDE, it is recommended that the Bank seriously consider a follow-up project to implement the Investment Attraction Plan and Export Promotion Activities for the next two to three years.

There is a level of enthusiasm and confidence among the BELTRAIDE staff and there is a set of products that are relevant and must be used within the next few years if they are to bring the results envisaged in the Technical Cooperation Agreement.  Given the current financial constraints that Belize currently faces, it is possible that little will be done to leverage the products of the Technical Cooperation if additional financing is not identified within the next year.

The arrangement in which there is a project manager responsible for project implementation who reports to the Executive Director worked well for this technical cooperation and should be used again if further assistance is applied.  BELTRAIDE learned how to integrate a project into its mainstream work and this augurs well for future projects.  The selection of the right project manager is important for this approach to be successful; but it has been demonstrated that this is possible.

There are a number of projects that could be identified but at this juncture the best way to assist BELTRAIDE is to follow up on the Technical Cooperation Agreement.  The implementation of the Investment Attraction Plan and Export Promotion Activities are seen as the two tangible areas for follow up.  With respect to export promotion activities, some of the investment should be directed at making potential products export ready.  Such follow up would help to ensure that the technical cooperation achieve its goal.  The reality is that the goal of the TC could not be achieved in twenty-four months but the foundation to achieve the goal is well built.  Unfortunately, given Belize’s financial position at this time, further investment is required to develop the country’s exports.  The reality is that Belize’s exports need to increase significantly if the country is to generate the foreign exchange needed.

List of people interviewed:

1.  Ms. Lourdes Smith, Executive director BELTRAIDE

2.  Mr. Roberto Harrison, Export Promotion Manager, BELTRAIDE r,

3. Mr. Wendell Middleton, Investment Promotion Manager, BELTRAIDE

4. Mr. David Gomez, Project Manager for the Technical Cooperation Agreement

5. Ms. Flory Usher, Accounts Manager, BELTRAIDE

6. Mr. Darrell Carter, Member Board of Directors, BELTRAIDE

7. Jon  Schmid, BG Consulting

Most of the people on the list below were interviewed multiple times.