## Sheet1
Inter-American Development Bank
PROCUREMENT PLAN FOR IDB-EXECUTED OPERATIONS
Country: Chile | [5 empty] | Executing Agency: IDB | [7 empty] | UDR: CSD/CCS (HQ)
Project number: CH-T1223 |  |  |  |  | Project name: Strengthening Chile’s climate change agenda and support for the organization of COP25
Period covered by the Plan: 24 months |  |  |  |  | Total Project Amount: |  | 600000
Component | Procurement Type (1) (2) | Service type (1) (2) | Description | Estimated contract cost (US$) | Selection Method (2) | Type of Contract | Source of Financing and Percentage |  |  |  | Estimated date of the procurement notice | Estimated contract start date | Estimated contract length | Comments
[7 empty] | IDB/MIF |  | Other External Donor
[7 empty] | Amount | % | Amount | % |  |  |  |  | Direct Contracting
Select comp | Select Proc. Type | Goods Included in Firm Cons. RFP | Consultant 1: brief description |  | select method | Select Cont. Type |  |  |  |  | 2016-03-01 |  |  |  | International Competitive Bidding
Component 1 | A. Consulting services | Corporate Procurement (GN-2303) | Workshops organized throughout the country for citizen engagement regarding COP | 100000 | SCS | Lump Sum | 100000 | 16.67% | 0 | 0% | 2019-07-01 | 2020-06-01 | 11 monhts |  | National Competitive Bidding
Component 1 | A. Consulting services | Individual Consultant (AM-650) | Design and execution of a COP Presidency coordination plan | 50000 | ICQ | Lump Sum | 50000 | 8.333% | 0 | 0% | 2019-07-01 | 2020-01-01 | 6 months |  | Shopping
Component 1 | A. Consulting services | Corporate Procurement (GN-2303) | Development of a climate action citizen engagement agenda | 30000 | ICQ | Lump Sum | 30000 | 5% | 0 | 0% | 2019-07-01 | 2019-10-01 | 3 months
Component 1 | A. Consulting services | Individual Consultant (AM-650) | Support to the MMA for the update of Chile's NDC in mitigation actions | 70000 | ICQ | Lump Sum | 70000 | 11.67% | 0 | 0% | 2019-07-01 | 2020-04-01 | 9 monhts |  | Quality and Cost Based Selection
Component 1 | A. Consulting services | Corporate Procurement (GN-2303) | Development of a private sector climate action strategy | 50000 | ICQ | Lump Sum | 50000 | 8.333% | 0 | 0% | 2019-07-01 | 2020-01-01 | 6 months |  | Least-Cost Selection
Component 2 | A. Consulting services | Corporate Procurement (GN-2303) | Public consultations tied to the framework climate change law | 30000 | ICQ | Lump Sum | 30000 | 5% | 0 | 0% | 2020-01-01 | 2020-05-01 | 4 months
Component 2 | A. Consulting services | Individual Consultant (AM-650) | Support to the Ministry of Finance for the development of a mitigation database | 20000 | ICQ | Lump Sum | 20000 | 3.333% | 0 | 0% | 2019-08-01 | 2020-11-01 | 3 months |  | Quality Based Selection
Component 2 | A. Consulting services | Individual Consultant (AM-650) | Support to the Ministry of Finance for the update and upgrade of the ministry's model for the economic impact assessement of mitigation policies. | 60000 | ICQ | Lump Sum | 60000 | 10% | 0 | 0% | 2019-09-01 | 2020-03-01 | 6 months |  | Selection Based on the Consultants' Qualifications
Component 2 | A. Consulting services | Corporate Procurement (GN-2303) | Support to Ministry of Finance and Environment to cover travel costs to attend international climate conferences | 20000 | SSS | Lump Sum | 20000 | 3.333% | 0 | 0% | 2019-08-01 | 2019-08-01 | 4 months |  | Selection under a Fixed Budget
Component 2 | A. Consulting services | Individual Consultant (AM-650) | Support to the ministry of finance in developping and executing a Coalition of Finance Minister's workplan | 30000 | ICQ | Lump Sum | 30000 | 5% | 0 | 0% | 2019-09-01 | 2019-12-01 | 4 months
Component 2 | A. Consulting services | Individual Consultant (AM-650) | Development of a public expenditure and climate tagging system proposal | 30000 | ICQ | Lump Sum | 30000 | 5% | 0 | 0% | 2020-02-01 | 2020-08-01 | 6 months
Component 2 | C. Non consulting services | Corporate Procurement (GN-2303) | Workshops organized to present and discuss climate change public expenditure tagging system proposal | 10000 | SCS | Lump Sum | 10000 | 1.667% | 0 | 0% | 2020-10-01 | 2020-10-01 | 1 month
Component 3 | A. Consulting services | Individual Consultant (AM-650) | Development of a white paper on the implications of action for 1.5 degrees celsius from the perspective of the ministries of finance, to be shared by Chile with LAC MoFs | 65000 | ICQ | Lump Sum | 65000 | 10.83% | 0 | 0% | 2019-07-01 | 2020-01-01 | 6 months
Component 3 | C. Non consulting services | Corporate Procurement (GN-2303) | Workshops organized to present and discuss white paper on the implications of 1.5 degrees celsius | 35000 | SCS | Lump Sum | 35000 | 5.833% | 0 | 0% | 2019-11-01 | 2019-11-10 | 1 month
Prepared by: | Federico Brusa (Fbrusa@iadb.org) |  | TOTALS | 600000 |  |  | 600000 | 100% | 0 | 0%
(1) Grouping together of similar procurement is recommended, such as publications, travel, etc. If there are a number of similar individual contracts to be executed at different times, they can be grouped together under a single heading with an explanation in the comments column indicating the average individual amount and the period during which the contract would be executed. For example: an export promotion project that includes travel to participate in fairs would have an item called "airfare for fairs", an estimated total value od US$5,000, and an explanation in the Comments column: "This is for approximately four different airfares to participate in fairs in the region in years X and X1".
(2) (i) Individual consultants: ICQ: Individual Consultant Selection Based on Qualifications; SSS: Single Source Selection. Selection process to be done in accordance with AM-650.
(2) (ii) Consulting firms: Per GN-2765-1, Consulting Firm selection methods for Bank-executed Operations are: Single Source Selection (SSS); Simplified Competitive Selection (<=250K) (SCS); Fully Competitive (>250K) (FCS); and Framework Agreement Task Order (TO). All Consulting Firm selection processes under this policy must use the electronic module in Convergence.
(2) (iii) Goods: Per GN-2765-1, par. A.2.2.c: "The procurement of goods and related services, except when such goods and related services are necessary to achieve the objectives of the Bank-executed Operational Work and are included in the consulting services contract and represent less than ten percent (10%) of the consulting services contract value."
Table for Data Validation
Select Comp: | Select Procurement Type: | Select Service Type: | description | amount | Select Method: | Select Cont. Type:
Component 1 | A. Consulting services | Individual Consultant (AM-650) |  |  | SSS | Lump Sum
Component 2 | B. Goods (2)(iii) | Consulting Firm (GN-2765) |  |  | ICQ | Framework Agreement
Component 3 | C. Non consulting services | Goods included in Cons. Firm RFP |  |  | SCS
Component 4 |  | Corporate Procurement (GN-2303) |  |  | FCS
Component 5 |  |  |  |  | TO
Component 6
Component 7
Component 8
Other