## Sept 2021
PROCUREMENT PLAN FOR THE PERIOD: |  | January 01, 2022 to June 30, 2023
PROJECT NAME: |  | DEPLOYMENT OF CLEANER FUELS AND RENEWABLE ENERGIES IN BARBADOS
PROJECT NUMBER: |  | BA-L1012
LOAN CONTRACT NUMBER: |  | 3843/OC-BA
DATE: |  | 2022-01-28
BUDGET: |  | US$34,000,000
Ref. No.¹ /Procurement No. | Description and type of procurement contract | Estimated/Actual contract cost (US$) | Procurement Type | Procurement method² | Review (ex ante or ex post) | Source of financing and percentage |  | Pre-qualification³ (Yes/No) | Estimated/Actual dates |  |  | Status⁴ (pending, in process, in preparation, awarded, cancelled) | Comments
[6 empty] | IDB | Local/Other % |  | Publication of specific procurement notice | Contract Signature Dates | Completion of contract
GOODS
Component 1 - NG Infrastructure
1.1.1.1 | Acquisition and Installation of ArcGIS Desktop Software and Maintenance Agreement (3 years) | 27459.36 | Goods | SSS | Ex-Post | 100 | 0 | No | 2017-05-01 | 2017-07-05 | 2021-08-31 | Completed
1.1.1.2 | Acquisition of GIS Enterprise and ArcPad Software and maintenance agreement (3 years) | 33899 | Goods | SSS | Ex-ante | 100 | 0 | No | 2017-10-29 | 2018-03-15 | 2022-04-30 | In Execution
1.1.1.3 | Acquisition of GIS/GNSS Equipment and Software | 123205.8 | Goods | Shopping | Ex-ante | 100 | 0 | No | 2018-03-23 | 2018-06-15 | 2019-01-11 | Completed
1.1.2.1 | Acquisition & Installation of Servers for Virtualisation, related software and Networking Equipment | 302883.95 | Goods | ICB | Ex-ante | 100 | 0 | No | 2018-03-14 | 2018-09-12 | 2019-07-22 | Completed
1.1.2.2 | Acquisition and Installation of SCADA System | 3029837 | Goods | ICB | Ex-ante | 100 | 0 | No | 2019-03-11 | 2019-10-25 | 2023-06-30 | In Execution
1.1.2.3 | Acquisition and Installation of Document Management System (DMS) | 123231 | Goods | Shopping | Ex-ante | 100 | 0 | No | 2017-10-02 | 2018-04-30 | 2021-05-28 | Completed
1.1.2.4 | Acquisition and Installation of Emergency Monitoring System for Lone Workers | 26200 | Goods | Shopping | Ex-ante | 100 | 0 | No | 2019-01-14 | 2019-06-12 | 2020-03-01 | Completed
1.1.2.5 | Acquisition of Mobile Solutions for Field Workers | 75000 | Goods | Shopping | Ex-ante | 100 | 0 | No | 2022-03-03 | 2022-07-07 | 2023-01-31 | Pending
1.1.3.1 | Acquisition of Ultrasonic NG Meters | 160083.8 | Goods | Shopping | Ex-ante | 100 | 0 | No | 2017-10-19 | 2018-06-15 | 2019-01-22 | Completed
1.1.3.2 | Acquisition and Installation of Meter Calibration Provers | 216434 | Goods | DC | Ex-ante | 100 | 0 | No | 2019-03-15 | 2021-02-14 | 2023-06-14 | In Execution
1.1.3.3 | Acquisition and Installation of Automatic Metering Infrastructure (AMI) | 0 | Goods | ICB | Ex-ante | 100 | 0 | No |  |  |  | Cancelled
1.3.1.1 | Acquisition and Installation of Compressors (2) for NG Plant | 900000 | Goods | ICB | Ex-ante | 100 | 0 | No | 2022-04-15 | 2022-12-07 | 2023-06-23 | Pending
1.4.1.1 | Acquisition of On Road Distribution Fleet | 829467.02 | Goods | ICB | Ex-ante | 100 | 0 | No | 2019-01-07 | 2019-08-20 | 2023-04-03 | In Execution
1.5.1.1 | Acquisition of Polyethylene Pipe, Fittings, Appurtenances and Equipment | 663134.5 | Goods | ICB | Ex-ante | 100 | 0 | No | 2020-09-07 | 2021-05-18 | 2022-02-28 | In Execution
1.5.1.2 | Acquisition of Polyethylene Pipes and Fittings for Highway 1 | 99858.88 | Goods | Shopping | Ex-ante | 100 | 0 | No | 2020-06-15 | 2020-08-17 | 2021-03-05 | Completed
Component 2 - Smart Energy Solutions
2.1.1.1 | Design, Acquisition & Installation of Renewable Energy Systems (PVs) | 6958309.04 | Goods | ICB | Ex-ante | 100 | 0 | No | 2018-04-17 | 2019-02-19 | 2023-06-11 | In Execution
2.2.1.1 | Acquisition and Installation of Energy Efficient (EE) Lights and Smart System | 200000 | Goods | ICB | Ex-ante | 100 | 0 | No | 2022-03-21 | 2022-11-15 | 2023-06-23 | Pending
2.5.1.1 | Design, Acquisition and Installation of a Battery Energy Storage System (BESS) at BNTCL | 0 | Goods | ICB | Ex-ante | 100 | 0 | No |  |  |  | Cancelled
Component 5 - Project Management and Monitoring
5.1.1 | Laptops with docking Stations | 25205 | Goods | Shopping | Ex-Post | 100 | 0 | No | 2017-03-01 | 2017-08-04 | 2017-10-30 | Completed
5.1.2 | Printer/Scanner | 3364 | Goods | SSS | Ex-Post | 100 | 0 | No | 2017-03-01 | 2017-07-13 | 2017-07-25 | Completed
5.1.3 | Software | 0 | Goods | Shopping | Ex-ante | 100 | 0 | No | 2022-03-28 | 2022-06-30 | 2023-08-16 | Cancelled
5.2.1 | Office Desk & workstations | 6248 | Goods | Shopping | Ex-Post | 100 | 0 | No | 2017-03-01 | 2017-06-26 | 2017-07-24 | Completed
5.2.2 | Office Chairs | 3479 | Goods | Shopping | Ex-Post | 100 | 0 | No | 2017-03-02 | 2017-08-22 | 2017-09-07 | Completed
5.3 | Office Supplies | 50000 | Goods | Shopping | Ex-post | 100 | 0 | No | 2021-12-01 |  | 2023-05-31 | Pending
5.7.1 | Acquisition and Installation of Project Signs at the various PV sites | 12000 | Goods | Shopping | Ex-post | 100 | 0 | No | 2022-02-15 | 2022-05-31 | 2022-08-31 | Pending
WORKS
Component 1 - NG Infrastructure
1.2.1.1 | Acquisition of Design and Build (D&B) Contractor for Small LNG Facility | 0 | Works | ICB | Ex-ante | 100 | 0 | No |  |  |  | Cancelled
1.5.2.1 | Infrastructural Replacement for Component A and Component B works packages | 5300000 | Works | - | Ex-ante | 100 | 0 | No | 2021-03-24 | 2022-02-08 | 2023-06-22 | Cancelled
1.5.2.1.1 | Procurement of Civil Works Contractor for the Infrastructural Replacement Works - Component B works package | 2459200 | Works | ICB | Ex-ante | 100 | 0 | No | 2021-03-24 | 2022-02-01 | 2023-06-22 | In Progress
1.5.2.1.2 | Procurement of Civil Works Contractor for the Infrastructural Replacement Works - Component A works package | 2840800 | Works | Shopping | Ex-ante | 100 | 0 | No | 2021-10-21 | 2022-02-08 | 2023-06-22 | In Progress
1.5.2.2 | Pipeline Replacement and Live Connections | 350000 | Works | FA | Ex-ante | 100 | 0 | No | n/a | 2022-02-28 | 2023-06-08 | In Progress | Connecting operational pipelines to replaced pipelines is specialized work that is only undertaken by the NPC. The Agreement Document between the PEU and the NPC for the live connections will be submitted to the Bank by February 2022
Component 2 - Smart Energy Solutions
2.1.2.1 | Design, Acquisition & Installation of a Renewable Energy System Solution at the Barbados National Terminal Co. Ltd. (BNTCL) | 8294871 | Works | ICB | Ex-ante | 100 | 0 | No | 2021-10-21 | 2022-07-31 | 2023-06-23 | In Progress
CONSULTANCY SERVICES
Component 1 - NG Infrastructure
1.1.1.5 | Acquisition of Consultancy Services for The Design, Installation and Implementation of an Enterprise Geographic Information System | 182345 | Consulting Firm | CQS | Ex-ante | 100 | 0 | No | 2020-09-09 | 2021-11-11 | 2023-01-02 | In Progress
1.2.2 | Acquisition of Oversight Supervisor for the Small LNG Facility | 0 | Consulting Firm | QCBS | Ex-ante | 100 | 0 | No |  |  |  | Cancelled
1.5.3.1 | Acquisition of Consulting Firm for Supervisory Services - NG Infrastructural Replacement | 500000 | Consulting Firm | QCBS | Ex-ante | 100 | 0 | No | 2021-01-28 | 2022-02-06 | 2023-06-23 | In Progress
Component 2 - Smart Energy Solutions
2.3.1.1 | Acquisition of Consultancy Services to prepare a Technical Feasibility Study for a Wind Turbine Facility in Barbados | 551274.77 | Consulting Firm | QCBS | Ex-ante | 100 | 0 | No | 2018-07-09 | 2019-08-16 | 2023-06-01 | In Execution
Component 3 - Technical Advisory Services
3.1.1.1 | Completing Operational Audits (Review NG Processing, Distribution and Accounting Systems) for NPC/BNOCL | 397530.87 | Consulting Firm | QCBS | Ex-ante | 100 | 0 | No | 2018-04-13 | 2019-03-27 | 2021-02-28 | Completed
3.1.1.2 | Acquisition of Consultancy Services for the Provision of Standard Operating Procedures (SOP) for NPC/BNOCL including Governance functions | 0 | Consulting Firm | QCBS | Ex-ante | 100 | 0 | No | n/a | n/a | n/a | Cancelled
3.1.1.3 | Acquisition of Consultancy Services for the Implementation of Employee Integration Programmes for the Newly Formed Company | 51851.85 | Consulting Firm | DC | Ex-ante | 100 | 0 | No | 2018-02-09 | 2019-12-12 | 2021-12-31 | In Execution
3.1.1.4 | Acquisition of Consultancy Services for the development of Quality Management System (QMS) - ISO Consultation | 180000 | Consulting Firm | CQS | Ex-ante | 100 | 0 | No | 2022-03-31 | 2022-10-14 | 2023-06-23 | Pending
3.1.1.5 | Acquisition of Consultancy Services for ISO Certification (NPC/BNOCL Staff) | 270000 | Consulting Firm | SSS | Ex-ante | 100 | 0 | No | n/a | 2022-12-20 | 2023-06-30 | Pending | Given the market where ISO Certification Registrars have the propensity not to respond to public tenders, the no-objection was granted to SSS. The selected firm has a reputation of being one of the world’s leading certification bodies and is a provider of accredited management systems certification. They serve as a technical adviser to the oil and gas industry and they have extensive experience offering inspection, risk management and technical advisory services to clients across the world.
3.2.1.1 | Acquisition of Consultancy Services for the Assessment, Report Building and Training on the Installed ERP Software SAP | 40000 | Consulting Firm | CQS | Ex-ante | 100 | 0 | No | 2022-04-11 | 2022-11-22 | 2023-02-06 | Pending
3.2.2 | Training in PPP contract negotiation, Large Infrastructure Project Design, Execution and Management | 0 | Consulting Firm | QCBS | Ex-ante | 100 | 0 | No | n/a | n/a | n/a | Cancelled
Component 4 - Project Evaluation
4.1.1.1 | Acquisition of Consultant for Midterm Evaluation | 28800 | Individual Consultant | IICQ | Ex-post | 100 | 0 | No | 2020-09-25 | 2020-12-21 | 2021-12-31 | Completed
4.1.1.2 | Procurement of Consultant for Final Evaluation | 45000 | Individual Consultant | IICQ | Ex-Post | 100 | 0 | No | 2022-09-01 | 2023-02-15 | 2023-10-30 | Pending
Component 5 - Project Management and Monitoring
5.4.1.1 | Acquisition of External Financial Auditor | 82654.318 | Consulting Firm | DC | Ex-ante | 100 | 0 | No | 2018-09-24 | 2019-05-29 | 2023-07-31 | In Execution
5.4.1.2 | Consultancy for Accounting Services for External Audit Preparation | 0 | Individual Consultant | SSS | Ex-post | 100 | 0 | No |  |  |  | Cancelled
5.4.2.1 | Acquisition of an External Financial Auditor for Final Financial Audit | 50000 | Consulting Firm | QCBS | Ex-ante | 100 | 0 | No | 2022-04-18 | 2022-11-15 | 2023-10-30 | Pending
5.5.1 | Project Manager | 559210 | Individual Consultant | NICQ | Ex-ante | 100 | 0 | No | 2017-03-01 | 2017-09-01 | 2023-01-31 | In Execution
5.5.1.1 | Project Manager (1) | 169954.77 | Individual Consultant | NICQ | Ex-ante | 100 | 0 | No | 2017-03-02 | 2017-09-02 | 2019-08-31 | Completed
5.5.1.2 | Project Manager (2) | 293676.58 | Individual Consultant | NICQ | Ex-ante | 100 | 0 | No | N/A | 2019-09-01 | 2023-01-31 | In Execution
5.5.2 | Procurement Officer | 369635 | Individual Consultant | NICQ | Ex-ante | 100 | 0 | No | 2017-03-02 | 2017-08-01 | 2023-06-30 | In Execution
5.5.2.1 | Procurement Officer (1) | 96724.34 | Individual Consultant | NICQ | Ex-ante | 100 | 0 | No | 2017-03-02 | 2017-08-01 | 2019-07-29 | Completed
5.5.2.2 | Procurement Officer (2) | 64750.82 | Individual Consultant | NICQ | Ex-ante | 100 | 0 | No | N/A | 2019-07-30 | 2020-11-06 | Completed
5.5.2.3 | Procurement Officer (3) | 126499.38 | Individual Consultant | NICQ | Ex-ante | 100 | 0 | No | 2020-10-01 | 2020-11-26 | 2023-06-30 | In Execution
5.5.3 | Project Accountant | 390107 | Individual Consultant | NICQ | Ex-ante | 100 | 0 | No | 2017-02-03 | 2017-06-12 | 2023-10-31 | In Execution
5.5.3.1 | Project Accountant (1) | 37451 | Individual Consultant | NICQ | Ex-ante | 100 | 0 | No | 2017-02-03 | 2017-06-12 | 2018-02-23 | Completed
5.5.3.2 | Project Accountant (2) | 50443.87 | Individual Consultant | NICQ | Ex-ante | 100 | 0 | No | 2018-02-04 | 2018-03-19 | 2019-02-15 | Completed
5.5.3.3 | Project Accountant (3) | 4755.4 | Individual Consultant | NICQ | Ex-ante | 100 | 0 | No | 2019-02-26 | 2019-04-15 | 2019-05-22 | Completed
5.5.3.4 | Project Accountant (4) | 108736 | Individual Consultant | NICQ | Ex-ante | 100 | 0 | No | 2019-02-26 | 2019-07-01 | 2021-06-30 | Completed
5.5.3.5 | Project Accountant (5) | 108736 | Individual Consultant | NICQ | Ex-ante | 100 | 0 | No | 2021-07-30 | 2021-11-15 | 2023-10-31 | In Execution
5.5.4 | Project Engineer (Technical Coordinator) | 417594 | Individual Consultant | NICQ | Ex-ante | 100 | 0 | No | N/A | 2017-01-01 | 2023-09-30 | In Execution
5.5.4.1 | Project Engineer (Technical Coordinator) (1) | 70051.83 | Individual Consultant | NICQ | Ex-ante | 100 | 0 | No | N/A | 2017-01-01 | 2018-12-31 | Completed
5.5.4.2 | Project Engineer (Technical Coordinator) (2) | 296578.57 | Individual Consultant | NICQ | Ex-ante | 100 | 0 | No | N/A | 2019-01-01 | 2023-09-30 | In Execution
5.5.5 | Technician-GIS | 207904.83 | Individual Consultant | NICQ | Ex-ante | 100 | 0 | No | 2017-03-05 | 2017-06-12 | 2020-06-30 | Completed
5.5.5.1 | Technician-GIS (RG) | 123456.09 | Individual Consultant | NICQ | Ex-ante | 100 | 0 | No | 2017-03-05 | 2020-06-12 | 2019-12-31 | Completed
5.5.5.1.1 | Technician-GIS (RG) (1) | 77965.65 | Individual Consultant | NICQ | Ex-ante | 100 | 0 | No | 2017-03-06 | 2017-06-12 | 2019-06-11 | Completed
5.5.5.1.2 | Technician-GIS (RG) (2) | 45490.44 | Individual Consultant | NICQ | Ex-ante | 100 | 0 | No | N/A | 2019-06-12 | 2020-06-30 | Completed
5.5.5.2 | Technician-GIS (SC) | 84448.74 | Individual Consultant | NICQ | Ex-ante | 100 | 0 | No | 2017-03-06 | 2019-06-13 | 2019-07-31 | Completed
5.5.5.2.1 | Technician-GIS (SC) (1) | 79289.44 | Individual Consultant | NICQ | Ex-ante | 100 | 0 | No | 2017-03-06 | 2017-06-12 | 2019-06-11 | Completed
5.5.5.2.2 | Technician-GIS (SC) (2) | 5159.3 | Individual Consultant | NICQ | Ex-ante | 100 | 0 | No | N/A | 2019-06-13 | 2019-07-31 | Completed
5.5.6 | Project Engineer | 124869.18 | Individual Consultant | NICQ | Ex-post | 100 | 0 | No | 2020-04-26 | 2020-07-08 | 2022-07-14 | In Execution
5.5.6.1 | Project Engineer (1) | 62434.59 | Individual Consultant | NICQ | Ex-post | 100 | 0 | No | 2020-04-26 | 2020-07-08 | 2021-07-07 | Completed
5.5.6.2 | Project Engineer (2) | 62434.59 | Individual Consultant | NICQ | Ex-post | 100 | 0 | No | N/A | 2021-07-08 | 2022-07-07 | In Execution
5.5.7 | Project Officer | 308482.65 | Individual Consultant | NICQ | Ex-ante | 100 | 0 | No | 2017-03-06 | 2017-09-01 | 2023-06-14 | In Execution
5.5.7.1 | Project Officer - Quality Assurance (1) | 103066.3 | Individual Consultant | NICQ | Ex-ante | 100 | 0 | No | 2017-03-07 | 2017-09-01 | 2019-07-31 | Completed
5.5.7.2 | Project Officer - Quality Assurance (2) | 96680.06 | Individual Consultant | NICQ | Ex-ante | 100 | 0 | No | 2019-06-15 | 2019-08-01 | 2021-07-01 | Completed
5.5.7.3 | Project Officer - Monitoring and Evaluation (3) | 108736.29 | Individual Consultant | NICQ | Ex-ante | 100 | 0 | No | 2022-04-30 | 2022-06-30 | 2023-06-14 | Pending
5.5.8 | Project Administrator | 446455 | Individual Consultant | NICQ | Ex-ante | 100 | 0 | No | 2017-03-08 | 2017-06-12 | 2022-07-31 | In Execution
5.5.8.1 | Project Administrator (1) | 138957.1062 | Individual Consultant | NICQ | Ex-ante | 100 | 0 | No | 2017-03-08 | 2017-06-12 | 2019-06-10 | Completed
5.5.8.2 | Project Administrator (2) | 178529.45 | Individual Consultant | NICQ | Ex-ante | 100 | 0 | No | 2019-06-15 | 2019-08-01 | 2022-07-31 | In Execution
5.5.9 | Electrical Engineering Technician | 50568.27 | Individual Consultant | NICQ | Ex-ante | 100 | 0 | No | 2018-02-08 | 2018-04-03 | 2020-01-10 | Completed
5.8.1 | Acquisition of Consultant for Accounting Services | 0 | Individual Consultant | SSS | Ex-ante | 100 | 0 | No | n/a | 2021-09-15 | 2021-10-15 | Cancelled
5.8.2 | Acquisition of Consultant for Project Management Services | 14500 | Individual Consultant | SSS | Ex-ante | 100 | 0 | No | n/a | 2021-10-08 | 2022-02-28 | In Execution
NON-CONSULTANCY SERVICES
Component 5 - Project Management and Monitoring
1.5.1.3 | Procurement of Line Tamer Operation Training | 10590 | NonConsulting Service | SSS | Ex-ante | 100 | 0 | No | N/A | 2022-01-13 | 2022-02-28 | Pending
3.2.1.2 | Procurement of Training Services on the ERP Software KRONOS | 10000 | NonConsulting Service | Shopping | Ex-ante | 100 | 0 | No | 2022-04-11 | 2022-11-22 | 2023-02-06 | Pending
5.6 | Training/Certification of PEU staff, affiliated training cost (rental of venue, catering, rental of equipment, etc.) | 75000 | Non Consulting Service | Shopping | Ex-post | 100 | 0 | No | 2021-01-01 |  | 2023-06-14 | Pending
5.7 | Promotional/Marketing Materials | 38000 | Non Consulting Service | Shopping | Ex-post | 100 | 0 | No | 2021-01-01 |  | 2023-06-15 | Pending
| Grand Total | 16691542.29
1 If there are a number of similar individual contracts to be executed in different places or at different times, these can be grouped together under a single heading, with an explanation in the comments column, indicating the average individual amount and the period during which the contracts would be executed. For example: an education Program that includes school construction might include an item labelled “School Construction” for an estimated cost of US$20 million and an explanation under the Comments column such as this: “This item encompasses some 200 contracts for school construction averaging US$100,000 each, to be awarded individually by the participating municipal governments over a three-year period between January 2006 and December 2008.”
2 Goods and Works: ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; Consulting Firms: QCBS: Quality- and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection; Individual Consultants: NICQ National individual Consultant Selection based on comparison of qualifications; IICQ: International Individual Consultant Selection based on comparison of qualifications.
3 Applicable only to Goods and Works in case the new Policies apply. In the case of previous Policies, it is applicable to Goods, Works and Consulting Services.
4 Column “Status” will be used for retroactive procurement and when updating the procurement plan.
Key: | In Progress | The procurement process is underway
| Pending | The procurement activity has not yet started
| Completed | Contractual obligations have been completed
| In Execution | Contractual obligations are underway
| Cancelled | The procurement activity has been cancelled
Kindly note that the Grand Total of the Procurement Plan reflects the salaries of the members of the Project Unit for the full duration of the project.