## Sheet1
PROCUREMENT PLAN FOR THE PERIOD: March 01, 2020 - September 30, 2021
PROJECT NAME: DEPLOYMENT OF CLEANER FUELS AND RENEWABLE ENERGIES IN BARBADOS
PROJECT NUMBER: BA-L1012
LOAN CONTRACT NUMBER: 3843/OC-BA
DATE: 4-June-20
BUDGET: USD$34,000,000
Ref. No.¹ | Description and type of procurement contract | Estimated/Actual contract cost (US$) | Procurement Type | Procurement method² | Review (ex ante or ex post) | Source of financing and percentage |  | Pre-qualification³ (Yes/No) | Estimated/Actual dates |  |  | Status⁴ (pending, in process, in preparation, awarded, cancelled) | Comments
[6 empty] | IDB % | Local/Other % |  | Publication of specific procurement notice | Contract Signature Dates | Completion of contract
GOODS
Procurement No.
1.1.1.1 | Acquisition and Installation of ArcGIS Desktop Software and Maintenance Agreement | 27459.36 | Goods | SSS | Ex-Post | 100 | 0 | No | 2017-05-01 | 2017-07-05 | 2021-08-31 | In Execution | Maintenance Period commenced 09/01/2018
1.1.1.2 | Acquisition and installation of GIS Enterprise and ArcPad Software and maintenance agreement (3 years | 33899 | Goods | SSS | Ex-ante | 100 | 0 | No | 2017-10-29 | 2018-03-15 | 2021-03-09 | In Execution
1.1.1.3 | Acquisition of GIS/GNSS Equipment and Software | 123205.8 | Goods | Shopping | Ex-ante | 100 | 0 | No | 2018-03-23 | 2018-06-15 | 2019-01-11 | Completed
1.1.2.1 | Acquisition & Installation of Servers for Virtualisation, related software and Networking Equipment | 302883.95 | Goods | ICB | Ex-ante | 100 | 0 | No | 2018-03-14 | 2018-09-12 | 2019-07-22 | Completed
1.1.2.2 | Acquisition and Installation of SCADA System | 2849328 | Goods | ICB | Ex-ante | 100 | 0 | No | 2019-03-11 | 2019-10-25 | 2022-06-30 | In Execution
1.1.2.3 | Acquisition and Installation of Document Management System (DMS) | 123231 | Goods | Shopping | Ex-ante | 100 | 0 | No | 2017-10-02 | 2018-04-30 | 2020-08-31 | In Execution
1.1.2.4 | Acquisition and Installation of Emergency Monitoring System for Lone Workers | 26200 | Goods | Shopping | Ex-ante | 100 | 0 | No | 2019-01-14 | 2019-06-12 | 2020-03-01 | In Execution
1.1.2.5 | Acquisition of Mobile Solutions for Field Workers | 75000 | Goods | Shopping | Ex-ante | 100 | 0 | No | 2020-07-15 | 2020-11-06 | 2022-04-06 | In Progress
1.1.3.1 | Acquisition of Ultrasonic NG Meters | 160083.8 | Goods | Shopping | Ex-ante | 100 | 0 | No | 2017-10-19 | 2018-06-15 | 2019-01-22 | Completed
1.1.3.2 | Acquisition and Installation of Meter Calibration Provers | 200000 | Goods | ICB | Ex-ante | 100 | 0 | No | 2019-03-15 | 2020-05-30 | 2023-06-14 | In Progress
1.1.3.3 | Acquisition and Installation of Automatic Metering Infrastructure (AMI) | 2016000 | Goods | ICB | Ex-ante | 100 | 0 | No | 2020-12-09 | 2021-06-16 | 2023-06-14 | Pending
1.4.1.1 | Acquisition of On Road Distribution Fleet | 856834.69 | Goods | ICB | Ex-ante | 100 | 0 | No | 2019-01-07 | 2019-08-20 | 2023-06-23 | In Execution
1.5.1.1 | Acquisition of Polyethylene Pipe, fittings and equipment | 500000 | Goods | ICB | Ex-ante | 100 | 0 | No | 2020-06-30 | 2020-12-20 | 2021-06-08 | In Progress
1.5.1.2 | Acquisition of Polyethylene Pipes and fittings for Highway 1 | 125000 | Goods | Shopping | Ex-ante | 100 | 0 | No | 2020-06-05 | 2020-06-15 | 2020-07-31 | In Progress
Component 2 - Smart Energy Solutions
2.1.1.1 | Design, Acquisition & Installation of Renewable Energy Systems (PVs) | 6958309.04 | Goods | ICB | Ex-ante | 100 | 0 | No | 2018-04-17 | 2019-02-19 | 2023-06-11 | In Execution | The increase in Contract Award value is reflective of the change in scope to include the integration to the Grid and the concrete contingency required to secure the mounting structure to the terrain.
2.2.1.1 | Acquisition and Installation of Compressors (2) for NG Plant | 850000 | Goods | ICB | Ex-ante | 100 | 0 | No | 2020-08-11 | 2021-05-02 | 2023-05-07 | Pending
2.2.2.1 | Acquisition and Installation of Energy Efficient (EE) Lights and Smart System | 200000 | Goods | ICB | Ex-ante | 100 | 0 | No | 2020-11-03 | 2021-05-28 | 2022-12-20 | Pending | Maintenance Agreement to be agreed to by both signatories hence the change in contract completion date
2.5.1.1 | Design, Acquisition and Installation of a Battery Energy Storage System at BNTCL | 1555460 | Goods | ICB | Ex-ante | 100 | 0 | No | 2020-11-02 | 2021-06-10 | 2023-06-15 | Pending
Component 5 - Project Management and Monitoring
5.1.1 | Laptops with docking Stations | 25205 | Goods | Shopping | Ex-Post | 100 | 0 | No | 2017-03-01 | 2017-08-04 | 2017-10-30 | Completed
5.1.2 | Printer/Scanner | 3364 | Goods | SSS | Ex-Post | 100 | 0 | No | 2017-03-01 | 2017-07-13 | 2017-07-25 | Completed
5.1.3 | Software | 53482 | Goods | Shopping | Ex-ante | 100 | 0 | No | 2020-12-04 | 2021-03-04 | 2023-06-19 | Pending
5.2.1 | Office Desk & workstations | 6248 | Goods | Shopping | Ex-Post | 100 | 0 | No | 2017-03-01 | 2017-06-26 | 2017-07-24 | Completed
5.2.2 | Office Chairs | 3479 | Goods | Shopping | Ex-Post | 100 | 0 | No | 2017-03-02 | 2017-08-22 | 2017-09-07 | Completed
5.3 | Office Supplies | 50000 | Goods | Shopping | Ex-post | 100 | 0 | No | 2019-12-07 |  | 2021-09-30 | In Execution
WORKS
Component 1 - NG Infrastructure
1.3.1.1 | Execution of Electrical and Civil Upgrades Required at the NG Plant | 50000 | Works | Shopping | Ex-ante | 100 | 0 | No | 2021-01-05 | 2021-04-21 | 2021-09-16 | Pending
1.5.2.1 | Pipeline Installation and Replacement Component 1, Component 2 and Component 3 works package | 5150000 | Works | ICB | Ex-ante | 100 | 0 | No | 2020-07-24 | 2021-02-04 | 2023-01-13 | In Progress
1.5.2.2 | Pipeline Replacement and Live Connections | 1400000 | Works | FA | Ex-ante | 100 | 0 | No | n/a | 2020-07-30 | 2022-12-09 | Pending | Connecting operational pipelines to replaced pipelines is specialized work that is only undertaken by the NPC. The Agreement Document between the PEU and the NPC for the live connections will be submitted to the Bank by June 2020
2.4.1.1 | Design, Acquisition & Installation of a Renewable Energy System Solution at Barbados National Terminal Company Limited (BNTCL) | 4000000 | Works | ICB | Ex-ante | 100 | 0 | No | 2020-07-31 | 2020-02-15 | 2023-06-14 | In Progress
CONSULTANCY
Component 1 - NG Infrastructure
1.1.1.5 | Acquisition of Consultancy Services for The Design, Installation and Implementation of an Enterprise Geographic Information System | 100000 | Consulting Firm | CQS | Ex-ante | 100 | 0 | No | 2020-06-30 | 2020-09-24 | 2021-03-15 | In Progress
1.5.3 | Acquisition of Consulting Firm for Supervisory Services - NG Infrastructural Replacement | 500000 | Consulting Firm | QCBS | Ex-ante | 100 | 0 | No | 2020-06-30 | 2020-11-29 | 2023-02-14 | In Progress
Component 2 - Smart Energy Solutions
2.3.1.1 | Acquisition of Consultancy Services to prepare a Technical Feasibility Study for a Wind Turbine Facility in Barbados | 551274.77 | Consulting Firm | QCBS | Ex-ante | 100 | 0 | No | 2018-07-09 | 2019-08-16 | 2021-12-31 | In Execution
Component 3 - Technical Advisory Services
3.1.1.2 | Training on Operational Software (SAP, KRONOS) | 50000 | Consulting Firm | CQS | Ex-ante | 100 | 0 | No | 2020-10-30 | 2020-12-31 | 2021-03-26 | Pending
3.1.2.1 | Completing Operational Audits (Review NG Processing, Distribution and Accounting Systems) for NPC/BNOCL | 400000 | Consulting Firm | QCBS | Ex-ante | 100 | 0 | No | 2018-04-13 | 2019-03-27 | 2020-07-20 | In Execution
3.1.2.3 | Acquisition of Consultancy Services for the Implementation of Employee Integration Programmes for the Newly Formed Company | 51851.85 | Consulting Firm | DC | Ex-ante | 100 | 0 | No | 2018-02-09 | 2019-12-12 | 2020-12-21 | In Execution
3.1.2.4.1 | Acquisition of Consultancy Services for the development of Quality Management System (QMS) - ISO Consultation | 180000 | Consulting Firm | QCBS | Ex-ante | 100 | 0 | No | 2020-09-07 | 2021-06-22 | 2023-03-20 | Pending
3.1.2.4.2 | Acquisition of Consultancy Services for ISO Certification (NPC/BNOCL Staff) | 270000 | Consulting Firm | QCBS | Ex-ante | 100 | 0 | No | 2020-09-20 | 2021-06-21 | 2023-06-21 | Pending
Component 4 - Project Evaluation
4.1.1.1 | Acquisition of Consultant for Midterm Evaluation | 30000 | Individual Consultant | IICQ | Ex-post | 100 | 0 | No | 2020-05-06 | 2020-09-08 | 2021-02-28 | Pending
Component 5 - Project Management and Monitoring
5.4.1 | Acquisition of External Financial Auditor | 71223.82 | Consulting Firm | DC | Ex-ante | 100 | 0 | No | 2018-09-24 | 2019-05-29 | 2023-07-31 | In Execution
5.4.1.2 | Consultancy for Accounting Services for External Audit Preparation | 1234.57 | Individual Consultant | SSS | Ex-post | 100 | 0 | No | 2019-06-01 | 2019-06-15 | 2019-09-15 | Completed
5.5.1 | Project Manager | 514059.07 | Individual Consultant | NICQ | Ex-ante | 100 | 0 | No | 2017-03-01 | 2017-09-01 | 2023-09-30 | In Execution
5.5.1.1 | Project Manager (1) | 169954.77 | Individual Consultant | NICQ | Ex-ante | 100 | 0 | No | 2017-03-02 | 2017-09-02 | 2019-08-31 | Completed
5.5.1.2 | Project Manager (2) | 344104.3 | Individual Consultant | NICQ | Ex-ante | 100 | 0 | No | N/A | 2019-09-01 | 2023-09-30 | In Execution
5.5.2 | Procurement Officer | 244306.95 | Individual Consultant | NICQ | Ex-ante | 100 | 0 | No | 2017-03-02 | 2017-08-01 | 2022-07-29 | In Execution
5.5.2.1 | Procurement Officer (1) | 96724.34 | Individual Consultant | NICQ | Ex-ante | 100 | 0 | No | 2017-03-02 | 2017-08-01 | 2019-07-29 | Completed
5.5.2.2 | Procurement Officer (2) | 147582.61 | Individual Consultant | NICQ | Ex-ante | 100 | 0 | No | N/A | 2019-07-30 | 2022-07-29 | In Execution
5.5.3 | Project Accountant | 201386.27 | Individual Consultant | NICQ | Ex-ante | 100 | 0 | No | 2017-02-03 | 2017-06-12 | 2021-06-30 | In Execution
5.5.3.1 | Project Accountant (1) | 37451 | Individual Consultant | NICQ | Ex-ante | 100 | 0 | No | 2017-02-03 | 2017-06-12 | 2018-02-23 | Completed
5.5.3.2 | Project Accountant (2) | 50443.87 | Individual Consultant | NICQ | Ex-ante | 100 | 0 | No | 2018-02-04 | 2018-03-19 | 2019-02-15 | Completed
5.5.3.3 | Project Accountant (3) | 4755.4 | Individual Consultant | NICQ | Ex-ante | 100 | 0 | No | 2019-02-26 | 2019-04-15 | 2019-05-22 | Completed
5.5.3.4 | Project Accountant (4) | 108736 | Individual Consultant | NICQ | Ex-ante | 100 | 0 | No | 2019-02-26 | 2019-07-01 | 2021-06-30 | In Execution
5.5.4 | Project Engineer (Technical Coordinator) | 366630.4 | Individual Consultant | NICQ | Ex-ante | 100 | 0 | No | N/A | 2017-01-01 | 2023-09-30 | In Execution
5.5.4.1 | Project Engineer (Technical Coordinator) (1) | 70051.83 | Individual Consultant | NICQ | Ex-ante | 100 | 0 | No | N/A | 2017-01-01 | 2018-12-31 | Completed
5.5.4.2 | Project Engineer (Technical Coordinator) (2) | 296578.57 | Individual Consultant | NICQ | Ex-ante | 100 | 0 | No | N/A | 2019-01-01 | 2023-09-30 | In Execution
5.5.5 | Technician-GIS | 204521.52 | Individual Consultant | NICQ | Ex-ante | 100 | 0 | No | 2017-03-05 | 2017-06-12 | 2020-06-30 | In Execution
5.5.5.1 | Technician-GIS (RG) | 120072.78 | Individual Consultant | NICQ | Ex-ante | 100 | 0 | No | 2017-03-05 | 2019-06-12 | 2019-12-31 | In Execution
5.5.5.1.1 | Technician-GIS (RG) (1) | 80174.47 | Individual Consultant | NICQ | Ex-ante | 100 | 0 | No | 2017-03-06 | 2017-06-12 | 2019-06-11 | Completed
5.5.5.1.2 | Technician-GIS (RG) (2) | 39898.31 | Individual Consultant | NICQ | Ex-ante | 100 | 0 | No | N/A | 2019-06-12 | 2020-06-30 | In Execution
5.5.5.2 | Technician-GIS (SC) | 84448.74 | Individual Consultant | NICQ | Ex-ante | 100 | 0 | No | 2017-03-06 | 2019-06-13 | 2019-07-31 | Completed
5.5.5.2.1 | Technician-GIS (SC) (1) | 79289.44 | Individual Consultant | NICQ | Ex-ante | 100 | 0 | No | 2017-03-06 | 2017-06-12 | 2019-06-11 | Completed
5.5.5.2.2 | Technician-GIS (SC) (2) | 5159.3 | Individual Consultant | NICQ | Ex-ante | 100 | 0 | No | N/A | 2019-06-13 | 2019-07-31 | Completed
5.5.6 | Project Engineer | 87000 | Individual Consultant | NICQ | Ex-post | 100 | 0 | No | 2020-04-30 | 2020-06-30 | 2021-06-30 | Pending
5.5.7 | Project Officer - Quality Assurance | 211802.59 | Individual Consultant | NICQ | Ex-ante | 100 | 0 | No | 2017-03-06 | 2017-09-01 | 2019-07-31 | In Execution
5.5.7.1 | Project Officer - Quality Assurance (1) | 103066.3 | Individual Consultant | NICQ | Ex-ante | 100 | 0 | No | 2017-03-07 | 2017-09-01 | 2019-07-31 | Completed
5.5.7.2 | Project Officer - Quality Assurance (2) | 108736.29 | Individual Consultant | NICQ | Ex-ante | 100 | 0 | No | 2019-06-15 | 2019-08-01 | 2021-07-01 | In Execution
5.5.8 | Project Administrator | 317486.5562 | Individual Consultant | NICQ | Ex-ante | 100 | 0 | No | 2017-03-08 | 2017-06-12 | 2022-07-31 | In Execution
5.5.8.1 | Project Administrator (1) | 138957.1062 | Individual Consultant | NICQ | Ex-ante | 100 | 0 | No | 2017-03-08 | 2017-06-12 | 2019-06-10 | Completed
5.5.8.2 | Project Administrator (2) | 178529.45 | Individual Consultant | NICQ | Ex-ante | 100 | 0 | No | 2019-06-15 | 2019-08-01 | 2022-07-31 | In Execution
5.5.9 | Electrical Engineering Technician | 50568.27 | Individual Consultant | NICQ | Ex-ante | 100 | 0 | No | 2018-02-08 | 2018-04-03 | 2020-01-10 | Completed
Component 5 - Project Management and Monitoring
5.6 | Training/Certification of PEU staff, affiliated training cost (rental of venue, catering, rental of equipment, etc.) | 25000 | Various | Shopping | Ex-post | 100 | 0 | No | 2020-07-01 |  | 2021-09-30 | Pending
5.7 | Promotional/Marketing Materials | 10000 | Various | Shopping | Ex-post | 100 | 0 | No | 2020-07-01 |  | 2021-09-30 | Pending
| Grand Total | 17426942
1 If there are a number of similar individual contracts to be executed in different places or at different times, these can be grouped together under a single heading, with an explanation in the comments column, indicating the average individual amount and the period during which the contracts would be executed. For example: an education Program that includes school construction might include an item labelled “School Construction” for an estimated cost of US$20 million and an explanation under the Comments column such as this: “This item encompasses some 200 contracts for school construction averaging US$100,000 each, to be awarded individually by the participating municipal governments over a three-year period between January 2006 and December 2008.”
2 Goods and Works: ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; Consulting Firms: QCBS: Quality- and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection; Individual Consultants: NICQ National individual Consultant Selection based on comparison of qualifications; IICQ: International Individual Consultant Selection based on comparison of qualifications.
3 Applicable only to Goods and Works in case the new Policies apply. In the case of previous Policies, it is applicable to Goods, Works and Consulting Services.
4 Column “Status” will be used for retroactive procurement and when updating the procurement plan.
Key | In Progress | The procurement process is underway
| Pending | The procurement activity has not yet started
| Completed | Contractual obligations have been completed
| In Execution | Contractual obligations are underway
| Cancelled | The procurement activity has been cancelled
Kindly note that the Grand Total of the Procurement Plan reflects the salaries of the members of the Project Unit for the full duration of the project.