|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| The project expected outcome is to contribute to enhance awareness on the importance of transparency to improve public management in Latin America and the Caribbean | | | | |
| **Component** | **Activities** | **Products (output)** | **Suggested Indicators (outcome)** | **Means of Verification** |
| **Component I** | Participation in external events | AAF-sponsored Panel and site event at the International Anticorruption Conference –IACC | # of times events have resulted in enhanced policy dialogue towards improved transparency, access to information | Survey/Project evaluation report |
| AAF participation in EITI related events |
| Organization of AAF-led events | At least 4 BBL anticorruption events at the IDB, and 2 transparency events at the country level |
| Creation of media products to disseminate the results of AAF-financed activities | At least 2 short videos for RG-T2224; JA-T1078 and/or RG-T2125  At least 1,000 brochures (English and Spanish) for the AAF | # of times media products have been used visited / downloaded | IDB website |
| Country policy dialogue | At least one technical note/ diagnostic/sector note addressing opportunities to enhance transparency at the country level | # of times in which knowledge products have been used to design IDB operations, or to provide policy advice | Survey/Project evaluation report |
| **Component II** | Preparation of high level IDB publications | At least four working papers / technical notes as key inputs to the high level publication | # of times in which knowledge products have been used to design IDB operations, or to provide policy advice | Survey/Project evaluation report |
| Editing, translating, and printing knowledge products | Edited, translated, and published knowledge products |
| **Component III** | External evaluation and publication | Impact evaluation or systematization of results | # of times in which reports/technical notes have been used to design IDB operations | Survey/Project evaluation report |

**DETAILED RESULTS MATRIX**