PROCUREMENT PLAN – April 2011 to March 2013

Loan Contract Number: 2099 OC-BA

Modernisation of the Barbados National Procurement System

| Description and Type of Procurement | Estimated Contract Cost US$ | Source of Financing |  | Review (ex-ante/ Ex-post | Procurement Method | Prequal | Estimated Dates |  | Status | Comments/ Recommendations |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | IDB % | Local/ other |  |  |  | Publication of SPN | Completion of Contract |  |  |
| 1. GOODS – - Technological Infrastructure Modernised and Updated 1.1 – Acquisition of E-Tendering Package 1.1.1 Purchase of E-procurement System - Total amount US$ 500,000 | 500,000 | 100 | 0 | Ex-ante | ICB | NO | February 2012 |  | Pending |  |
| 2. CONSULTING SERVICES - Strengthen Public Procurement Regulatory Framework - 2.1 Procurement Regulations Drafted & Promulgated 2.1.1 –Drafting of Procurement Regulations, Policies & Bidding Documents- FIRM specialised in Public Procurement 2.2 Support to the Implementation of new regulations including training 2.2.1 Training in application of new instruments &Bidding Documents - Total amount US$ 224,446.00 | 164,446.00 60,000.00 | 100 100 | 0 0 | Ex-Post Ex-Ante | ICB N/A | NO NO | 2nd Semester (2009) (November (2009) 1st Semester 2012 | June, 2011 | Awarded Pending | Awarded - Crown Agents Commenced January 2011 |
| 3.CONSULTING SERVICES - Improve Procurement Operations and Marketplace 3.1 Strengthen CPD Operations 3.1.1 Develop and Implement a modernisation plan for CPD supply chain management warehouse – Supply Chain Mgmt. Planning & Implementation 3.1.1.1 Development of a Plan to Modernise CPD Supply chain Mgmt. Total amount US$ 106, 000 | 106,000 | 100 | 0 | Ex-Ante | NCB | NO | 2nd Semester 2011 |  | Pending |  |
| 4. CONSULTING SERVICES - Procurement Institutional Capacity Strengthened 4.1 Strategic Plan to set up Personnel in New Procurement Positions Developed and Executed 4.1.1 Preparation & Execution of Strategic Plan 4.1.1.1 Consultancy to Develop a Plan to Strengthen Procurement Capacity in stakeholder Institutions 4.2 PPU and CPD Organisational Structure and Job Descriptions Developed(US$30,000) 4.2 New Career Stream and Relevant H.R Resource Manual Developed and Implemented (US$90,000) - Consultancy to Develop a Career Stream in Procurement and Related Operational Procedures 4.3 Development and Implementation of Training Programme (US$350,000) - Consultancy to Implement a Capacity Development Program - Total amount US$ 679,801.00 | 206,801.00 123,000.00 350,000.00 | 100 100 100 | 0 0 0 | Ex-Post Ex-Ante Ex-Ante | ICB ICB ICB | NO NO NO | 2nd Semester 2009 (September 2009) 2nd Semester 2011 1st Semester 2012 | June 2011 | Awarded Pending Pending | Awarded to IGS Commenced January 2011 Activities 4.1& 4.2 combined into one consultancy |
| 5. CONSULTING SERVICES - Technological Infrastructure Modernised and Updated 5.1 E-Tendering System Developed & Implemented 5.1.1.1 Assessment of an Electronic Procurement Information System 5.1.1.2 Implementation of E-Procurement System - Total amount US$ 575,500.00 | 75,500.00 500,000.00 | 100 100 | 0 0 | Ex-Post Ex-Ante | NCB ICB | NO NO | 1st Semester 2011 (February 2011) 2nd Semester 2012 |  | In Progress Pending | Awaiting approval of MOU from STC Dependent on results of Assessment Consultancy and consequent acquisition |