**Results Matrix**

**Objective of the Project:** contribute to the production and dissemination of new information on civil registration and identification that will contribute to the upgrading and standardization of registration procedures.

|  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Impact Indicators** | **Unit of Measure** | **Baseline** | | | | **Targets** | | **Source/Means of verification** | | **Remarks** |
| **Value** | | | **Year** | **Value** | **Year** |
| 1. Civil and legal registry information updated in accordance with international standards | # of documents |  | | |  | 3 | 2017 | Final report of the consulting | |  |
| **Output (what they produce. Direct products or services)** | | **Unit of measure** | **Baseline** | | | **Year of base line** | **Year 1** | **Year 2** | **Year 3** | **Target** | **Means of verification** |
| **Component 1: Generation of identity knowledge products** | | | | | | | | | | | |
| 1.1Guidelines of standardization of civil and identification registration procedures has been shared | | # of document | 0 | | | 2014 | 0 | 3 | 1 | 4 | Final evaluation report |
| 1.2 Guidelines of the use of advanced procedures on birth registration has been published | | # of documents | 0 | | | 2014 | 0 | 1 | 1 | 2 | Publication of the guideline |
| **Component 2: Dissemination and technical regional collaboration** | | | | | | | | | | | |
| 2.1 Thematic communication and dissemination strategy has been implemented | | # of documents | 0 | | | 2014 | 0 | 1 | 0 | 1 | Final evaluation of the strategy |
| 2.2 The number of petitions for technical cooperation on civil and legal registries from the borrowing member countries has increased | | # of TC proceeded | 0 | | | 2014 | 0 | 2 | 2 | 4 | TCs processed |
| **Products** | **Unit of measure** | **Associated Results** | | | **Cost** | **Year 1** | **Year 2** | **Year 3** | **Target** | **Means of verification** |
| **Component 1: Generation of identity knowledge products** | | | | | | | | | | |
| 1.1 Development of a guideline for the use of Information and Communication Technology (ICT) for birth registration | # of Documents | | | 1.1 and 1.2 | $ 60.000 | 0 | 1 | 0 | 1 | Publication of the guideline |
| 1.2 Analysis of the transaction cost between social programs and legal registries | # of Documents | | | 1.1 | $ 40.000 | 0 | 1 | 0 | 1 | Final report and approval of the consultancy |
| 1.3 Development of training manuals for registrars to reach the universal registries | # of manuals | | | 1.1 and 1.2 | $45.000 | 0 | 1 | 0 | 1 | Publication of the manual |
| 1.4 Forums to validate and interchange technical documentation | Document | | | 1.1 | $ 40.000 | 0 | 1 | 1 | 2 | Report of activities and list of participants |
| 1.5 Production of policy and technical notes on demand | # of documents | | | 1.1 and 1.2 | $40.000 | 0 | 1 | 1 | 2 | Publication of technical notes |
| **Component 2: Dissemination and technical regional collaboration** | | | | | | | | | | |
| 2.1Design and development of a thematic communication and dissemination strategy | # of documents | | 2.1 and 2.2 | | $ 25.000 | 0 | 1 | 0 | 1 | Final report of the consultancy |
| 2.2 Short term consultancies | # of consultancies | | 2.2 | | $ 60.000 | 2 | 2 | 2 | 6 | Report of activities and final report of the consultancy |
| 2.3 Workshops for sharing of information | # of trainings | | 2.1 and 2.2 | | $ 90.000 | 0 | 2 | 2 | 4 | Report of activities and list of participants |