## Sheet1
Annex 4 – RG-T3328 | [11 empty] | Inter-American Development Bank
PROCUREMENT PLAN FOR IDB-EXECUTED OPERATIONS
Country: Regional | [5 empty] | Executing Agency: IDB | [7 empty] | UDR: CSD/CCS
Project number: RG-T3328 |  |  |  |  | Project name: Supporting climate and disaster risk assessment processes to foster resilient and sustainable development
Period covered by the Plan: 36 months |  |  |  |  | Total Project Amount: |  | 1500000
Component | Procurement Type (1) (2) | Service type (1) (2) | Description | Estimated contract cost (US$) | Selection Method (2) | Type of Contract | Source of Financing and Percentage |  |  |  | Estimated date of the procurement notice | Estimated contract start date | Estimated contract length | Comments
[7 empty] | IDB/MIF |  | Other External Donor
[7 empty] | Amount | % | Amount | % |  |  |  |  | Direct Contracting
Select comp | Select Proc. Type | Goods Included in Firm Cons. RFP | Consultant 1: brief description |  | select method | Select Cont. Type |  |  |  |  | 2016-03-01 |  |  |  | International Competitive Bidding
Component 1 | A. Consulting services | Consulting Firm (GN-2765) | Consultant 1: Formulation of climate change and disaster risk assessment for 1 IDB project (Simple) | 80000 | SSS | Lump Sum | 80000 | 100% | 0 | 0% | 2019-02-01 | 2019-03-20 | 4 months |  | National Competitive Bidding
Component 1 | A. Consulting services | Consulting Firm (GN-2765) | Consultant 2: Formulation of climate change and disaster risk assessment for 1 IDB project (Simple) | 80000 | SSS | Lump Sum | 80000 | 100% | 0 | 0% | 2020-02-01 | 2020-03-20 | 8 months |  | Shopping
Component 1 | A. Consulting services | Consulting Firm (GN-2765) | Consultant 3: Formulation of climate change and disaster risk assessment for 1 IDB project (Full) | 170000 | SSS | Lump Sum | 170000 | 100% | 0 | 0% | 2019-03-01 | 2019-04-30 | 1 year |  | Least-Cost Selection
Component 1 | A. Consulting services | Consulting Firm (GN-2765) | Consultant 4: Formulation of climate change and disaster risk assessment for 1 IDB project (Full) | 170000 | SSS | Lump Sum | 170000 | 100% | 0 | 0% | 2020-03-01 | 2020-04-30 | 1 year |  | Quality and Cost Based Selection
Component 1 | A. Consulting services | Individual Consultant (AM-650) | Consultant 5: Site Visit and Report on climate change and disaster risk for 2 projects (PEC) | 80000 | SSS | Lump Sum | 80000 | 100% | 0 | 0% | 2019-06-01 | 2019-07-01 | 3 months |  | Quality Based Selection
Component 1 | A. Consulting services | Consulting Firm (GN-2765) | Consultant 6: Design and Implementation of Core Curriculum to Build the Capacity of Internal and External Stakeholders | 30000 | SCS | Lump Sum | 30000 | 100% | 0 | 0% | 2019-03-01 | 2019-06-01 | 3 years |  | Selection Based on the Consultants' Qualifications
Component 1 | C. Non consulting services | Corporate Procurement (GN-2303) | Logistics for capacity building workshops (transportation, venue, food service, workshop materials, others) | 10000 |  |  | 10000 | 100% | 0 | 0% | 2019-03-01 | 2019-06-01 | 3 years | ongoing activity (workshops)
Component 1 | C. Non consulting services | Corporate Procurement (GN-2303) | Monitoring Expenses to Supervise climate change and disaster risk Assessments | 10000 |  |  | 10000 | 100% | 0 | 0% | 2019-03-01 | 2019-06-01 | 3 years | ongoing activity (paricipation in workshops and risk assessments)
Component 2 | A. Consulting services | Consulting Firm (GN-2765) | Consultant 7 - RDM study applied to a project to manage climate risks and capacity building | 200000 | SCS | Lump Sum | 200000 | 100% | 0 | 0% | 2019-07-01 | 2019-09-01 | 1 year |  | Selection under a Fixed Budget
Component 2 | A. Consulting services | Consulting Firm (GN-2765) | Consultant 8 - RDM study applied to a project to manage climate risks and capacity building | 200000 | SCS | Lump Sum | 200000 | 100% | 0 | 0% | 2020-03-01 | 2020-06-01 | 1 year |  | Individual Consultant
Component 3 | A. Consulting services | Consulting Firm (GN-2765) | Consultant 9 - Financial system resilience to climate risks - methodology and application (physical risk prevalence) | 200000 | SCS | Lump Sum | 200000 | 100% | 0 | 0% | 2019-07-01 | 2019-09-01 | 1 year
Component 3 | A. Consulting services | Consulting Firm (GN-2765) | Consultant 10 - Financial system resilience to climate risks - methodology and application (transition risk prevalence) | 200000 | SCS | Lump Sum | 200000 | 100% | 0 | 0% | 2020-03-01 | 2020-06-01 | 1 year
Component 4 | A. Consulting services | Individual Consultant (AM-650) | Consultant 11 - climate change and disaster risk contractual support | 70000 | SCS |  | 70000 |  | 0 | 0% | 2019-01-01 | 2019-03-01 | 3 years
Prepared by: |  |  | TOTALS | 1500000 |  |  | 1500000 | 100% | 0 | 0%
(1) Grouping together of similar procurement is recommended, such as publications, travel, etc. If there are a number of similar individual contracts to be executed at different times, they can be grouped together under a single heading with an explanation in the comments column indicating the average individual amount and the period during which the contract would be executed. For example: an export promotion project that includes travel to participate in fairs would have an item called "airfare for fairs", an estimated total value od US$5,000, and an explanation in the Comments column: "This is for approximately four different airfares to participate in fairs in the region in years X and X1".
(2) (i) Individual consultants: ICQ: Individual Consultant Selection Based on Qualifications; SSS: Single Source Selection. Selection process to be done in accordance with AM-650.
(2) (ii) Consulting firms: Per GN-2765-1, Consulting Firm selection methods for Bank-executed Operations are: Single Source Selection (SSS); Simplified Competitive Selection (<=250K) (SCS); Fully Competitive (>250K) (FCS); and Framework Agreement Task Order (TO). All Consulting Firm selection processes under this policy must use the electronic module in Convergence.
(2) (iii) Goods: Per GN-2765-1, par. A.2.2.c: "The procurement of goods and related services, except when such goods and related services are necessary to achieve the objectives of the Bank-executed Operational Work and are included in the consulting services contract and represent less than ten percent (10%) of the consulting services contract value."
Table for Data Validation
Select Comp: | Select Procurement Type: | Select Service Type: | description | amount | Select Method: | Select Cont. Type:
Component 1 | A. Consulting services | Individual Consultant (AM-650) |  |  | SSS | Lump Sum
Component 2 | B. Goods (2)(iii) | Consulting Firm (GN-2765) |  |  | ICQ | Framework Agreement
Component 3 | C. Non consulting services | Goods included in Cons. Firm RFP |  |  | SCS
Component 4 |  | Corporate Procurement (GN-2303) |  |  | FCS
Component 5 |  |  |  |  | TO
Component 6
Component 7
Component 8
Other