LEGIII/BH-683439-06

# ANNEX

THE PROJECT

Information as a Tool for Negotiating Effectiveness

I.	Objective

1.01	The main objective of this Project is to assist the government of The Bahamas in analyzing and successfully managing the most important and complex disciplines it faces as it negotiates greater trade liberalization both at the multilateral and regional level. Specifically, the Project seeks to improve the country’s ability to negotiate market access in services, understand and implement multilateral trade obligations arising from accession to the World Trade Organization (“WTO”), address negotiated rules and obligations pertaining to international investment, and facilitate required adjustments to the operation of the Freeport free trade zone (“FTZ”) that will arise from trade liberalization agreements.

II.	Description

- 2.01	To achieve the objectives described in Section I above, the Project will finance four (4) components:

- Component 1. Expert Advice in Services

  - It is estimated that services account for some ninety per cent (90%) of the country’s Gross Domestic Product (“GDP”). It is essential that The Bahamas formulates an effective negotiating strategy for the various international services negotiations in which it is engaged. The Project will finance an international consultant to assist the country in preparing to negotiate services at the multilateral and regional level. The consultant will undertake  two (2) main tasks: (i) provide training on international trade in services to the public and private sectors; and (ii) assist the country in preparing a market access offer in services. The consultant will be hired for a total of forty (40) working days, of which thirty (30) days will be spent in The Bahamas.

  - Services Training (five (5) days, in-country). The consultant’s first task will be to provide four (4) days of training on services negotiations, focusing on the areas of particular importance to the Bahamian economy. These include tourism services, financial services and maritime transport services. Two (2) days of services training will be given to public sector officials in Nassau and two (2) days of training will be provided to the private sector - one  (1) day in Nassau and one (1) in Freeport. The principal thrust of this training will be to facilitate the effective participation by government and private sector actors in preparing, analyzing and revising market access offers in services.

  - Preparation of Market Access Offers (forty (40) days, twenty (20) of which in-country). Upon completion of the training, the consultant will compile and analyze relevant information on current legislation and prepare a matrix on existing restrictions to trade in services, for submission to the government. He/she will also work with government officials in developing initial services offers for the WTO and other relevant negotiations, taking into account the current situation in the country as well as existing entry barriers of key partner countries. In addition, the consultant will prepare two (2) stages of revised offers. In preparing these initial and revised offers, the consultant will recommend what sub-sectors should be offered when and to what degree and what sectors should be reserved. In doing so, the relative sensitivity for each sector and sub-sector will be identified and the negotiating bottom-lines clarified.

  - In undertaking the preparation of initial and revised offers, the consultant will work closely with and be guided by the Inter-Ministerial body appointed by the government for the purpose of overseeing services negotiations.

  - Following submission to the Ministry of Trade and Industry of a draft report containing the proposed options for services offers, the consultant will discuss the proposed options with the private sector representatives who participated in the initial training.

  - The consultant and the Inter-Ministerial body will work together to refine the offers, taking into account the comments of the private sector. The consultant will then present a final report on options for initial and revised offers.

  - The offer documents prepared by the consultant will be the property of the government of The Bahamas and the consultant will be subject to a strict non-disclosure agreement.

- Component 2. WTO Awareness and Compliance

  - This component is designed to provide the government of The Bahamas with a basic understanding of WTO rules and disciplines, as well as the policy and regulatory changes that would be required by WTO membership. To this effect, two (2) consultants will be hired – one (1) international consultant who is an expert on WTO rules and disciplines and one (1) local consultant who is an expert on Bahamian laws and regulations. The local consultant should also have experience in international economic affairs. Both consultants will be hired for thirty (30) working days. The consultancies will be carried out in three (3) periods of approximately ten (10) working days each.

  - The two (2) consultants will work as a team in preparing an analytical document outlining, for each WTO Agreement or Decision, the impact of WTO rules and disciplines on the Bahamian legal and regulatory structure. The document should set forth what policy and regulatory reforms would be required in order to bring The Bahamas into compliance with the WTO regime.

  - For the purpose of clarity, the text of the relevant Article or Decision that is discussed will be set forth followed by an analysis. In cases where one Article is dependent on another, the related reference Article will be listed at the end of the analysis. The end document will be a detailed, disaggregated analysis of the legal and regulatory implications for The Bahamas of coming into full compliance with WTO rules.

- Component 3. Review of Investment Policy

  - Significant changes have occurred throughout the world over the past two decades in the area of investment policy. A general trend toward liberalization has been reflected in investment chapters in free trade agreements and bilateral investment treaties. These agreements have tended to restrict the application of many of the traditional instruments used by governments to attract investment, such as specific performance requirements and limitations on the repatriation of profits. The agreements have also established, in many cases, investor-state dispute settlement procedures. Chapter 11 of the North American Free Trade Agreement (NAFTA) has been the model for many of these agreements. The WTO Agreement on Trade-Related Investment Measures (TRIMs) is much more limited in scope than NAFTA Chapter 11 but nevertheless outlaws certain practices.

  - The Bahamas is not currently a member of any international agreement that regulates investment. However, membership in the WTO would imply signing on to the TRIMs Agreement. Participation in a future FTAA or similar regional trade agreement is likely to include, at least to some degree, even broader, NAFTA-like disciplines on investment. The potential scope of application of investment chapters, most notably in the case of NAFTA, has become the focus of significant scrutiny and controversy in recent years. Critics claim that investment chapters like NAFTA weaken the ability of countries to develop policies that are in the public interest, including the ability to proactively protect their natural environments. However, experts in the investment area often find the claims of critics bear no relationship with the texts of the agreements.

  - This component will finance an international consultant to help the government understand the potential implications for The Bahamas associated with the types of international investment disciplines to which The Bahamas may sign on. The consultant will be hired for 10 working days. His/her specific task will be to prepare a report on the possible legal and policy implications of acceding to the WTO TRIMs Agreement. The report will also focus on the legal and policy implications of adopting a NAFTA/CAFTA compatible investment regime. The consultant will explore the investment-related disciplines one-by-one and explicitly highlight options (with pros and cons) and recommendations for the policy and regulatory reforms that compliance with such regimes would imply. Finally, the consultant will suggest possible areas in which it may be prudent to lodge reservations. In doing so, the consultant will explain his/her reasoning and cite examples of where other countries have taken such steps.

- Component 4. Free Trade Zones and Freeport

  - WTO accession and other trade initiatives pursued by The Bahamas could result in significant changes to the rules governing the operation of Freeport, the country’s main free trade zone (FTZ). The WTO, in the Agreement on Subsidies, prohibits the use of certain types of incentives that are used in FTZs. The NAFTA eliminates the use of duty drawback, a common tool used to facilitate assembly in FTZs. While there are different types of FTZs, trade liberalization agreements undoubtedly constrain the flexibility that policymakers have in promoting the use of such zones. Therefore, their future operation and development is likely to be influenced by WTO accession and adherence to regional trade agreements.

  - Given the importance of Freeport, both in terms of employment and as the country’s main center of manufacturing, an international consultant who is an expert on FTZs will be hired for 15 working days. The principal task of the consultant is to help Bahamian policymakers understand how WTO accession and regional trade agreements such as the FTAA and the post-Cotonou Agreement will affect the current operational practices of the Freeport FTZ, the likely constraints that such trade liberalizing agreements are likely to bring, and policy options for ensuring the continued viability and prosperity of Freeport. This will include suggestions on negotiating approaches as well as domestic regulatory reforms. The consultant will also examine the implications of related disciplines such as those pertaining to foreign investment and to monopolies for the current Freeport regime.

  - The output of this consultancy will be a detailed report with options, pros and cons and recommendations constituting, in effect, a roadmap for ensuring the long-term economic viability of Freeport. In completing this task, the consultant will work closely with national policymakers in the capital and with local leaders in Freeport.

  - To support implementation of the project’s four components, the Ministry of Trade and Industry will provide a counterpart contribution in-kind, from existing resources, as per the following: (i) office space and facilities for consultants, as appropriate; (ii) staff time dedicated to providing oversight and direction to the work of consultants; (iii) one junior staff person to work alongside and assist the services consultant; and (iv) one junior staff person to work alongside and assist the investment consultant.

III.	Total Cost of the Project

3.01	The estimated cost of the Project is the equivalent of CAD$165,000, in accordance with the following Budget:

Budget

(in CAD$)

| ## Activities | Bank | Local Contribution | Total |
| --- | --- | --- | --- |
| ### 1. Market Access in Services 1 international consultant x 45 days at $850 per day + 3 roundtrip international air tickets at $1,000 + $1,000 for domestic air tickets + 25 days per diem @ $300. Junior Staff person | 49,750 0 | 0 3,000 | 49,750 3,000 |
| #### 2. WTO Awareness and Compliance 1 international consultant x 30 working days at $850 per day + 3 roundtrip international air tickets at $1,000 + $1,000 for domestic air tickets +30 days per diem @$300. One local consultant 30 days at $500 per day + $4,000 for travel outside of Nassau (tickets and per diem) | 38,500 19,000 | 0 0 | 38,500 19,000 |
| #### 3. Investment Policy Review 1 international consultant x 10 working days at $850 per day + 1 roundtrip international air ticket at $1,000 + $300 for domestic air tickets + 10 days per diem @$300. Junior Staff person | 12,800 0 | 0 1,000 | 12,800 1,000 |
| #### 4. Free Zones/Freeport 1 international consultant x 15 working days at $850 per day + 2 roundtrip international air ticket at $1,000 + $500 for domestic air tickets + 15 days per diem @$300. | 19,750 | 0 | 19,750 |
| #### Office Space and Facilities | 0 | 7,500 | 7,500 |
| #### Staff Time/Oversight | 0 | 3,500 | 3,500 |
| #### Audit | 3,500 | 0 | 3,500 |
| #### Contingencies | 6,700 | 0 | 6,700 |
| ##### Total | 150,000 | 15,000 | 165,000 |

IV.	Execution

  - The Ministry of Trade and Industry will serve as Executing Agency for the Project. In this capacity, the Ministry will appoint a contact person responsible for overseeing the implementation of the Project and ensuring the fulfillment of the Ministry’s responsibilities in this regard.

  - The Executing Agency will select and hire the Project consultants in accordance with the Bank´s procurement procedures.

  - The consultants will work with the counterpart staff in the Ministry in a manner that will ensure a transfer of technology and knowledge and allow Ministry staff to be better able to undertake the relevant functions after project completion.

  - The Executing Agency will submit a written progress report to the Bank, though the Country Office in The Bahamas, twice a year, on June 1 and December 1, explaining the status of the Project, the degree of completion of the aforementioned activities and the progress made in fulfilling the stated objectives. The report will also include a disaggregated account of expenses. Upon completion of all Project activities, the Executing Agency will submit a final Project report to the Bank, in accordance with the general Bank guidelines regarding the structure and content of those reports.

  - Upon completion of the Project, the Executing Agency will hire an independent accounting firm to audit the Project.