LEGIII/BH-639436-05

ANNEX

THE PROJECT

I.	Objective

  - The objectives of this Project are : (a) Stimulate community-based tourism development and local entrepreneurship; (b) Raise awareness levels and stimulating visitor interest in Inagua; (c) Market Sensitization and Transfer of Skills and Technologies; and (d) Product Development and Investment.

(a) 	Stimulate community-based tourism development and local entrepreneurship

  - While the Bahamas is one of the world’s most successful tourism destinations, that success has been achieved primarily through foreign investment.  An important aim of this Project is to promote Bahamian ownership of the industry in Inagua and the Family Islands and investment of Bahamian capital, both human and financial.  This objective would be achieved through targeted technical assistance and enhanced access to financing.

- Raising awareness levels and stimulating visitor interest in Inagua

  - Investment in tourism related services and infrastructure, including accommodations, food and beverage, attractions, and activities must be supported, at the outset, by targeted marketing and promotion. Despite a rich mix of existing and potential attractions, Inagua is literally unknown in primary target markets.

  - One of the best opportunities for travel market development in Inagua is the SAVE market (Scientific, Academic, Volunteer, and Educational travel).  It consists of a wide range of travel market segments ideally suited to Inagua’s existing product mix, including the West Indian Flamingo population, sea turtle nesting grounds, and Inagua National Park.  Voluntourism programs – through Earthwatch and similar environmental travel organizations; university level research programs – such as the Hocking College Training Station in Andros; and college and high school training programs – from two-week environmental education classes to full semesters abroad from the U.S., Europe and Caribbean are all important potential target markets for this Project.  Work is already underway to create the programs and infrastructure required to exploit this potential, but additional support is required in terms of technical assistance and market outreach and development.

(iii)	Market Sensitization and Transfer of Skills and Technologies

  - There are a number of aspiring entrepreneurs in Inagua today, but in addition to a lack of access to capital, most lack an understanding of target markets and the tools and technologies available to develop the island’s tourism industry.  Some are sophisticated business people with a wide range of skills, but know little about the kind of tourism that is best suited to Inagua’s mix of existing and potential products, including the SAVE market, ecotourism, soft adventure, diving, and bird watching.

  - Use of renewable energy technology, both wind and solar, will also be explored in depth, both as a means of establishing the island’s reputation as an eco-friendly destination, and as an economic alternative to the costly import of diesel fuel required to run Inagua’s two generators.

  - Through study tours, workshops, one-on-one counseling, and promotion of joint ventures with successful operators, both foreign and domestic, those interested in pursuing sustainable tourism development will be provided with the skills and market knowledge required for successful Project development.

(iv)	Product Development and Investment

  - Financial and other partners will be recruited to support product development initiatives that will enhance the visitor experience on Inagua.  Examples include bird blinds and watchable wildlife ponds; a Flamingo Research Station (already in progress); renovation of the Salt House and surrounding grounds, and potentially other historic structures, providing food and beverage facilities, a Visitor’s Center, bike rentals, and arts and handicrafts center; signage, visitor information services, etc.  Potential partners include corporations (through corporate social responsibility programs), and environmental organizations (e.g. Birdlife International, Nature Conservancy).

II.	Description

  - The objectives described in Section I above will be ____ through the following activities: (a) Promoting Local Entrepreneurship and Access to Capital; (b) Marketing and Promotion; (c) Market Sensitization and Skills Transfer; (d) Product Development and Investment.

## (a)	Promoting Local Entrepreneurship and Access to Capital

  - Business Planning:  Targeted technical assistance in the preparation of marketing plans and financial analyzes of proposed Projects, including eco-lodges, B&Bs, tour operations, equipment rentals, food and beverage, handicrafts, dive and sport fishing operations, preparation of loan packages, and identifying and working with loan providers – including the Tourism Development Loan Guarantee Fund specifically set up for the Family Islands to promote tourism development (and the commercial banks that provide loans through the Project); a new Venture Capital Fund; and micro-credit facilities available through the Bahamas Development Bank – to promote support of small business development in Inagua.   Joint ventures with successful Bahamian and foreign operators will also be promoted.

  - Tourism Association Development and Capacity Building:  Building upon the successful creation of the Inagua Tourism Steering Committee (as a result of the Bank-funded assessment), an Inagua Tourism Association will be formed to help promote joint and coop marketing (with the Bahamas Ministry of Tourism and other travel trade partners), ongoing training and education programs, and advocacy efforts.

(b)	Marketing and Promotion

  - Website Development – A destination website will be developed for the island, as well as websites for individual businesses.  E-commerce training (web-based reservations systems, excursion bookings, rentals, etc.) and training for website updating and maintenance will also be provided.

  - SAVE Market Development – Through assistance provided by the George Washington University, the proposed Inagua Tourism Association will be provided with training and tools to operate as a SAVE Center – a market outreach and marketing organization for SAVE market segments.

  - Travel Trade Outreach – For other identified market segments, including sport fishing and soft adventure, and in cooperation with travel industry partners such as Bahamas Air, organize and conduct specialized affinity group and tour operator familiarization and travel writer trips.

  - Special Events – Budget permitting, in cooperation with travel trade partners and associations, organize special events that will stimulate awareness of and travel to Inagua, such as bird watching seminars/festivals and bone fishing tournaments.

  - Environmental Certification – The process of certifying Inagua as one of the first islands in the Bahamas designated as a Blue Flag destination will also be initiated.  http://www.blueflag.org/.  Green Globe certification will also be explored.  http://www.greenglobe21.com/. In addition, the recently approved MIF operation “Sustainable Tourism Network for SMEs” (ATN/ME-9466-BH), which will be implemented by the Bahamas Hotel Association will provide the necessary training for tourism oriented SMEs in order to comply with international environmental standards.

- Market Sensitization and Skills Transfer

  - Study Tour – In cooperation with travel trade partners willing to provide in-kind support, to visit successful operations within, and if feasible, outside the Bahamas that serve currently targeted markets.  Sites include Tiamo Resort, the ForFar Research Station and Small Hope Bay Lodge in Andros, Compass Point in Nassau, and Maho Bay Resort in St. John, U.S.V.I.

  - Training and Capacity Workshop – Bringing successful eco-lodge operators, specialized tour operators (dive, bird watching, etc.), BahamaHost representatives, affinity groups with targeted travel programs (BirdLife International, Audubon Society, National Geographic), financial intermediaries (commercial banks providing loans through the Government Loan Guarantee Fund and Bahamas Development Bank) to Inagua to conduct a workshop on successful product development, tourism services operations, marketing, project financing, and enhancing the visitor experience.  This workshop will also provide an opportunity for a first-hand product assessment of Inagua by these experts and to generate additional ideas and support for future product development efforts.  It will also assist in promoting Inagua as a travel destination.

  - Business Training – In accounting, operations management, interpretation (bird watching guides, etc.), website maintenance and e-commerce.

(d)	Product Development and Investment

  - Salt House Renovation – The principal target will be Morton Salt and its parent company, the Rohm and Haas Corporation; a multi-billion dollar diversified chemical company.  A proposal will be prepared and presented to the company for renovation of the Salt House (owned by Morton) through its Corporate Social Responsibility department.  Initial ideas for the Salt House, and the surrounding oceanfront property include a Flamingo and Salt Story Interpretation program, an Arts Center, producing handicrafts and artworks made from recyclable materials (glass, aluminum, plastic, paper), modeled on a program developed at Maho Bay, indoor and outdoor food and beverage facilities, visitor’s information center, equipment rentals, etc.

III.	Total Cost of the Project

  - The estimated cost of the Project is the equivalent of US$181,177, in accordance with the following Table of Costs

#### Project Costs

(in US$)

| Activities | ##### MIF | Contribution | TOTAL |
| --- | --- | --- | --- |
| 1.1 Business Planning/Technical Assistance | 29,250 |  | 29,250 |
| 1.2 Tourism Assoc. Develop. & Capacity Building | 25,950 |  | 25,950 |
| 2.1 Website Development |  | 16,450 | 16,450 |
| 2.2 SAVE Center | 21,175 |  | 21,175 |
| 2.3 Travel Trade Outreach | 12,250 |  | 12,250 |
| 2.4 Initiate Certification Process |  | 12,800 | 12,800 |
| 3.1 Study Tour |  | 7,750 | 7,750 |
| 3.2 Workshop |  | 12,120 | 12,120 |
| 3.3 Business Training |  | 8,850 | 8,850 |
| 4.2 Prep. & Presentation Salt House Renovation | 8,025 |  | 8,025 |
| External Audit | 2,925 |  | 2,925 |
| Administrative and Operating Costs (15%) |  | 23,632 | 23,632 |
| TOTAL | 99,575 | 81,602 | 181,177 |

V.	Execution

  - The executing agency will delegate the day-to-day operations of this Project to a Project Coordination Team (PCT), which will be headed by a staff member from the Ministry of Tourism who will be seconded to the BNT on a part-time basis for the duration of the Project. Terms of Reference for the Project coordinator are included in Annex 2.

  - Operations in Inagua will be coordinated by the Inagua Steering Committee, chaired by the Managing Director of Morton Bahamas Limited.  Support will be provided on an ongoing basis by the Nassau Steering Committee, which is composed of representatives of the Office of the Prime Minister, Ministry of Finance, IDB, BEST Commission, Bahamas National Trust, the Ministry of Tourism, and other representatives from both the public and private sector (as needed).  This committee will meet quarterly, or more frequently as necessary to review progress, provide ongoing guidance for Project implementation, and if needed help to identify additional technical assistance and funding support for the Project.

  - Both international and local consultants will be contracted to conduct various elements of the Project.

  - The execution and disbursement periods will be 12 months and 18 months, respectively, after signing the Letter of Agreement.  The release of Project funds will be contingent upon: (i) Appointment of the Project coordinator; and (ii) receipt of a letter from the Government committing itself to contribute US$ 15,000 in cash for the financing of selected Project activities.

  - The procurement of goods and the selection and contracting of consultants will be governed by the Bank's Policies for the Procurement of Goods and Works and for the Selection and Contracting of Consultants, in Documents GN-2349-4 and GN-2350-4.