| Ref. No. | Description and type of the procurement contract | Estimated Contract Cost ($US) | Procurement method | Review (ex-ante or ex-post) | Source of financing and percentage |  | Pre-qualifi-cation (Yes/No) | Estimated dates |  | Status (pending, in process, awarded, cancelled) | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | IDB % | Local/ Other % |  | Publication of specific procurement notice | Completion of contract |  |  |
|  | - Goods - Good 1 Computers and peripherals associated with establishment of the Trade Information Centre - Good 2 Brief description | $9,000 | 3 Quotes | Ex-ante | 55.56% | 44.44% | No | N/A | January 2009 | Completed |  |
|  | - Consulting services - Consulting services 1 Coordinator SMESU - Consulting services 2 Database Consultant for the Trade Information Centre Consulting services 3 (2) Sector Papers - (i) Impact of the Implementation of the EPA on SME’s in The Bahamas. (ii) Trade Policy Reform options for The Bahamas Audit | $81,000 $10,500 $15,751.04 $3,000 | CCV CCV CCV CCV | Ex-Ante Ex-Ante Ex-Ante | 100% 100% 66.66% | 33.33% 100% | No No | N/A N/A N/A N/A | August 2009 July 2009 August 2010 | Awarded Pending In process Pending |  |

If a number of similar individual contracts were to be executed in different places or at different times, these can be grouped together under a single heading, with an explanation in the comments column indicating the average individual contract amount and the period during which they would be executed. For example, an education project that includes school construction might include an item “school construction” for a total of US$20 million, and an explanation in the comments column such as: “This encompasses some 200 contracts for school construction averaging US$100,000 each, to be awarded individually by participating municipal governments over a three-year period between January 2006 and December 2008.”

Goods and Works: ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through Specialized Agencies; PA: Procurement Agents; IA: Inspection Agents; PLFI: Procurement in Loans to Financial Intermediaries; BOO/BOT/BOOT: Build, Own, Operate/Build, Operate, Transfer/Build, Own, Operate, Transfer; PBP: Performance-Based Procurement; PLGB: Procurement under Loans Guaranteed by the Bank; PCP: Community participation procurement.  Consulting Firms: QCBS: Quality- and Cost-Based Selection QBS: Quality-Based Selection FBS: Selection under a Fixed Budget; LCS: Least-Cost Selection; CQS: Selection based on the Consultants’ Qualifications; SSS: Single-Source Selection.  Individual Consultants: NICQ: National Individual Consultant selection based on Qualifications; IICC: International Individual Consultant selection based on Qualifications

In the case of new Policies it applies only for Goods and Works.  In the case Old Procurement Policies it applies for Goods, Works and Consulting Services.

This column “Status” should be used for retroactive procurement and for procurement plan updates.