## Procurement Plan
SECTION 3
PROCUREMENT PLAN
Project Name : Credit Enhancement Programme for Micro, Small and Medium Enterprises
Project Number: 4115/0C-JA
FROM __JAN/2018______ (month/year) to _JUN/2019_________ (month/year)
Ref. No. 1 | Reference to SEPA code | Comp. No. | Description of and Component of procurement contract | Indicative cost (USD 000) | Procurement Selection method 2 | Review (ex-ante or ex-post) | Source of financing and percentage |  | Prequalification 3 (YES/NO) | Estimated Dates |  | Actual dates |  | Status 4 (pending; in process; awarded; cancelled) | Comments
[7 empty] | IDB % | Local/Other % |  | Publication of specific procurement notice | Completion of Contract | Publication of specific procurement notice | Completion of Contract
1 |  |  | GOODS
Good 1
Brief description
Good 2
Brief description
2 |  |  | WORKS
Work 1
Brief description
Work 2
Brief description
3 |  |  | Non-consulting services
Service 1
Brief description
Service 2
Brief description
4 |  |  | CONSULTING SERVICES
|  | 1 | Finance officer | 27000 | QCNI | ex-post | 50 | 50 |  | 2017-12-01 |  |  |  | in process | Finance officer will be shared with the World Bank Access to Finance Project
|  | 1.1 | Financial Audit | 9000 | CQS | ex-post | 100 |  |  | 2019-02-01
| TBA | 1.1.1 | Monitoring & Evaluation | 24000 | CQS | ex-post | 100 |  |  | 2019-02-01
1.1.1.1
Consulting Services 2
Brief description
1 If there are a number of similar individual contracts to be executed in different places or at different times, these can be grouped together under a single heading, with an explanation in the comments column, indicating the average individual amount and the period during which the contracts would be executed. For example: an education project that includes school construction might include an item labeled “School Construction” for an estimated cost of US$20 million and an explanation under the Comments column such as this: “This item encompasses some 200 contracts for school construction averaging US$100,000 each, to be awarded individually by the participating municipal governments over a three-year period between January 2006 and December 2008.”
2 Goods and Works: ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; Consulting Firms: QCBS: Quality- and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection; Individual Consultants: QCNI: Selection based on comparison of qualifications of national individual consultants; QCII: Selection based on comparison of qualifications of international individual consultants.
3 Applicable only to Goods and Works in case the new Policies apply. In the case of previous Policies, it is applicable to Goods, Works and Consulting Services.
4 Column “Status” will be used for retroactive procurement and when updating the procurement plan.
Codes from SEPA