## RG-T2357 - Procurement Plan
PLAN DE ADQUISICIONES DE COOPERACIONES TECNICAS NO REEMBOLSABLES
Country: Argentina |  |  |  |  | Executing agency: Secretaría de Ambiente y Desarrollo Sustentable de Nación. |  |  |  |  | Public or private sector: Public
Project number: AR-T1120 |  |  |  |  | Title of Project: Apoyo al Proyecto GEF AR-G1002
Period covered by the plan: January 2016 - December 2017
TC Funding: US$1,000,000 |  |  | Local counterpart:
Threshold for ex post review of procurements: N/A |  |  |  | Goods and services (in US$): |  | 127422 |  | Consulting services(in US$): | 872578
Item No. | Ref. AWP | Description (1) | Estimated contract cost (US$) | Procurement Method (2) | Review of procurement (ex-ante or ex-post) (3) | Source of financing and percentage |  | Estimated date of the procurement notice or start of the contract | Technical review by the PTL (4) | Comments
[6 empty] | IDB % | Local/other %
|  | Component 1. Evaluación | 290911 |  |  | 100 |  |  |  | Local counterpart is in-kind contribution, as is counted in AR-G1002
Consulting services
1 |  | Firma para desarrollo de Encuesta de uso final de la energía en el sector residencial | 240911 | QCBS | N/A | 100 |  | 2017-02-01
2 |  | Firma consultora para el diseño de metodología de evaluación multicriterio | 50000 | CQS | N/A | 100 |  | 2017-02-12
|  | Component 2. Tecnología | 254089 |  |  | 100 |  |  |  | Local counterpart is in-kind contribution, as is counted in AR-G1002
Consulting services
3 |  | Estudio de mercado sobre tecnologías de ahorro de agua | 26667 | CQS | N/A | 100 |  | 2014-03-01 | 2017-06-01
4 |  | Estudio para desarrollo de ACV | 50000 | CQS | N/A | 100 |  | 2017-02-01 | 2017-07-01
5 |  | Estudio sobre barreras de conexión a red de ER | 50000 | CQS | N/A | 100 |  | 2018-01-01
Goods and works
6 |  | Adquisición e instalación y monitoreo del desempeño de las tecnologías de ahorro de agua. | 44089 | CB | N/A | 100 |  | 2018-03-01
7 |  | Adquisición, instalación y monitoreo de sistemas fotovoltaicos | 33333 | CB |  | 100 |  | 2018-03-01
8 |  | Adquisición, instalación y monitoreo de sistemas fotovoltaicos y aerogeneradores en prototipos. | 50000 | CB | N/A | 100 |  | 2018-03-01
|  | Componente 3. División | 350000 |  |  | 100 |  |  |  | Local counterpart is in-kind contribution, as is counted in AR-G1002
Consulting services
9 |  | Firma para el montaje de la exposición (show-room) del proyecto | 350000 | QCBS | N/A | 100 |  | 2017-08-01
|  | Component 4. Fortalecimiento institucional | 105000 |  |  | 100 |  |  |  | Local counterpart is in-kind contribution, as is counted in AR-G1002
Individual consultants
10 |  | Consultor individual. Especialista de evaluación y seguimiento | 30000 | SSS | N/A | 100 |  | 2017-01-01 | 2017-12-01
11 |  | Consultor individual. Especialista Técnico | 30000 | SSS | N/A | 100 |  | 2017-01-01 | 2017-12-01
12 |  | Consultor individual. Especialista en contrataciones y adquisiciones | 30000 | SSS | N/A | 100 |  | 2017-01-01 | 2017-12-01
13 |  | Consultor individual. Especialista Técnico Administrativo | 15000 | SSS | N/A | 100 |  | 2017-01-01 | 2017-12-01
Total |  |  | 1000000
(1) Grouping together of similar procurement is recommended, such as computer hardware, publications, travel, etc. If there are a number of similar individual contracts to be executed at different times, they can be grouped together under a single heading, with an explanation in the comments column indicating the average individual amount and the period during which the contract would be executed. For example: an export promotion project that includes travel to participate in fairs would have an item called "airfare for fairs", an estimated total value od US$5,000, and an explanation in the Comments column: "This is for approximately four different airfares to participate in fairs in the region in years X and X1".
(2) Goods and works: CB: Competitive bidding; PC: Price comparison; DC: Direct contracting.
(2) Consulting firms: CQS: Selection Based on the Consultants' Qualifications; QCBS: Quality and cost-based selection; LCS: Least Cost Selection; FBS: Selection nder a Fixed Budget; SSS: Single Source Selection; QBS: Quality Based selection.
(2) Individual consultants: IICQ: International Individual Consultant Selection Based on Qualifications; SSS: Single Source Selection.
(3) Ex ante/ex post review: In general, depending on the institutional capacity and level of risk associated with the procurement, ex post review is the standard modality. Ex ante review can be specified for critical or complex process.
(4) Technical review: The PTL will use this column to define those procurement he/she considers "critical"or "complex"that require ex ante review of the terms of reference, technical specifications, reports, outputs, or other items. |  |  |  |  | ,