LEG/SGO/RG-35123241-10

THE ANNEX

THE PROJECT

Sport as an Instrument for Youth Employment

I.	Objectives

1.01	The goal of the Project is to improve the socioeconomic situation of low income youth in the participating countries.

1.02	Its purpose is to increase job placement opportunities for young people by expanding and improving the “A Ganar” model.

II.	Description

2.01	To achieve the Project objectives described in section I above, financing will be provided for the following components:

### Component 1: Adaptation of the “A Ganar” model

- 2.02	The purpose of this component is to adapt the model that has been used for soccer to other sports, such as rugby, baseball, and field hockey. In addition, the model will be improved taking into account the lessons learned during the past four years of execution. Activities include: (i) selecting partner entities in each country; (ii) developing phase I materials for new sports; (iii) transferring know-how and supervising organizations for effective implementation of the model; (iv) building new elements into the model; and (v) drafting manuals.

- 2.03	The Executing Agency will provide ongoing support to the entities through visits to ensure effective implementation of the model. The entities will be selected based on their experience implementing youth-oriented projects and their ability to contribute funds. Educators or experts will be hired to adapt phase I materials for the new sports. For the transfer of know-how, staff from the new countries will team up with certified facilitators for one week to develop activities on the playing field, so they can internalize the importance and the effect of these sports activities on young people. Service learning modules will be included.

- 2.04	In order to bring the new countries up to speed, the implementation leader of each country will visit the offices of the Executing Agency in Brazil, Ecuador, and/or Uruguay to receive orientation, observe in person the field and classroom training offered to young people as part of phase I, and meet with business leaders and mentors. In addition, staff from these offices will travel to the new countries to hold training workshops for the instructors and certify them as “A Ganar” instructors. The Executing Agency will supervise the adaptation of materials and the model for the new sports to guarantee quality. In addition to the workshops, the Executing Agency will oversee progress in each country, making visits every six months, also to ensure quality.

- 2.05	The expected outcome is an improved “A Ganar” model that is applicable to other team sports. The model should be based on experiences at different levels in the international arena, should target beneficiaries with different profiles (low-income and at-risk youth), and should be executed through entities that have diverse strengths and expertise but focus on youth development.

### Component 2: Youth training

- 2.06	The purpose of this component is to train the instructors and young people in phases I and II of training. Activities include: (i) providing or subcontracting training courses based on labor demand; (ii) providing job skills training for young people; (iii) providing technical skills training for young people; (iv) providing transportation and/or refreshments for young people; (v) identifying mentors in the private sector; and (vi) coordinating the training entities.

- 2.07	During phase I, approximately 50% of the time will be spent on the playing field and 50% will be spent in the classroom, where youth will receive training in math, reading, writing, and computer skills in order to fill in gaps in their education and build their skills. For phase II, the type of vocational training that young people will receive will vary from country to country depending on demand within companies and the realities in each place. Some of the vocations for which courses may be offered are: administrative assistant, restaurant and hotel worker, telemarketer, computer services assistant, mechanic, welder/blacksmith, etc. Companies will be asked to support certain groups of young people by participating in the development of technical materials, supporting internship costs, and also by recruiting their employees to serve as trainers.

- 2.08	An entrepreneurship module will be included during phase II since it will be linked to each vocation. The Executing Agency will improve the existing entrepreneurship manual to help participating youth will learn the basics about: business plans, microcredit, money management, how to open a bank account, etc.

- 2.09	The Executing Agency and the lead organizations in each country will hire facilitators and educators for phase I and II training and/or will subcontract partner training entities by issuing a call for proposals. Some of the criteria for selecting partner training entities will be their experience working with young people, the viability of physical infrastructure for classroom and field activities and technical workshops, and their partnerships with the private sector for arranging internships and/or jobs.

- 2.10	As an expected outcome of this component, technical staff in the new countries in the “A Ganar” Alliance and/or the lead organizations will received adequate training to meet the target of training 5,400 young people, of whom at least 75% are expected to complete all phases of training.

### Component 3: Internships and job placement

- 2.11	The purpose of this component is to form partnerships with the private and public sectors to identify the existing labor demand and arrange for internships (phase III) and follow-up and jobs (phase IV) for participating youth. Activities include: (i) training youth through internships, entrepreneurship practicums, and/or work experience; (ii) implementing a program to follow up with graduates; and (iii) measuring the rates at which young people find jobs, start businesses, and/or return to school.

- 2.12	Partnerships will be established with companies, trade unions, universities, associations, local governments, and other groups to identify: where job opportunities exist, which companies are willing to hire young people, the specific needs of the companies, which companies are willing to host interns, and whether and how they are willing to cofinance youth training for specific trades. A combination of individual and group meetings led by the offices of the Executing Agency and the partner training entities will be held to make these determinations. Direct connections between the partner training entities and the companies are important for ensuring that training actually addresses the needs of the market.

- 2.13	Internships and/or work experience will be supervised by the partner training entities, and if necessary, cofinancing will be provided for transportation and learning materials for the first job. The partner training entities will meet with the companies hosting the young people to evaluate the experience of both the company and the young person. Surveys will be prepared to determine the satisfaction level of both parties.

- 2.14	A system for following up with “A Ganar” graduates will be established in order to provide job placement support and guidance in creating self-employment and finding educational opportunities. A coordinator will be hired to make regular calls or send emails or text messages. Graduates will have access to job counseling, information on educational opportunities, and group activities such as talks with business leaders or sports figures serving as the role models that many young people do not have at home.

- 2.15	This component is expected to produce the following outcomes: 100 partnerships with companies, the public sector, and universities; 70% of companies rate participating youth as “good or excellent”; 70% of participating youth rate their workplace experience as “good or excellent”; at least 52% all participants (70% of program graduates) find work, start their own business, or return to school.

### Component 4: Monitoring and dissemination of outcomes

- 2.16	The purpose of this component is to set up an efficient Project monitoring system at the level of each country and the region and to promote the “A Ganar” model internationally as part of the long-term sustainability strategy. Activities include: (i) conducting outcome evaluations during the Project; (ii) publicizing Project activities and outcomes; and (iii) preparing promotional material. Another lesson learned is that something as simple as jerseys has proven to be a tremendous promotional tool and instills a sense of identity and pride in the youth.

- 2.17	The Executing Agency will develop a system for gathering information to monitor participating youth, based on the Nike Foundation method used to monitor youth participating in the project in Brazil (“Vencedoras”). A software program will be used, and each country will gather information in baseline form, surveys (one at the end of training and another nine months later), and individual and group interviews and will send it to the office of the Executing Agency in Washington, D.C., so it can be compiled and analyzed at the regional level.

- 2.18	A number of events will be held, including a Project launch, visits from sports figures, conferences, and graduations. These events will provide an opportunity for the partner training entities to exchange information and for Project outcomes to be showcased to promote investments in youth-targeted activities. “A Ganar” was invited to present the Project experiences in Brazil, Ecuador, and Uruguay at the Sport for Social Development conference in Beijing, China, in April 2008; the Global Youth Enterprise Conference in Washington in September 2008; and the CEDRO Forum in Rio de Janeiro, Brazil, in November 2009. These types of presentations are expected to continue under the proposed Project.

III.	Total Cost of the Project

### 3.01	The total estimated cost of the Project to be executed by the Executing Agency is US$6,982,757. Following the budget summary table:

### Budget (in US$)

|  | MIF | COUNTERPART RESOURCES | TOTAL | % |
| --- | --- | --- | --- | --- |
| Component I. Adaptation of the model | 227,500 | 299,744 | 527,244 | 7.55 |
| Component II. Youth training | 1,123,500 | 1,664,000 | 2,787,500 | 39.92 |
| Component III. Internships and job placement | 620,500 | 1,114,050 | 1,734,550 | 24.84 |
| Component IV. Monitoring and dissemination of outcomes | 318,800 | 582,250 | 901,050 | 12.90 |
| Execution unit | 248,000 | 289,000 | 537,000 | 7.69 |
| Administration | 207,805 | 0 | 207,805 | 2.98 |
| Contingencies | 114,439 | 0 | 114,439 | 1.64 |
| Evaluations | 81,000 | 0 | 81,000 |  |
| Audits and ex post reviews | 77,000 | 0 | 77,000 |  |
| SUBTOTAL | 3,018,544 | 3,949,044 | 6,967,588 |  |
| Impact evaluation account (for the entire Technical Cooperation) | 15,169 |  | 15,169 |  |
| TOTAL | 3,033,713 | 3,949,044 | 6,982,757 |  |
| Percentages | 44% | 56% | 100% |  |

IV. 	Executing Agency and Mechanism

- 4.01	The executing agency for the Project will be Partners of the Americas Foundation. For the execution of the Technical Cooperation in Argentina, the executing agency will be Virreyes Rugby Club (VRC), who will work under the supervision of the Executing Agency in its capacity as the executing agency for the larger Project. All Argentina related expenditures are the responsibility of VRC.

- 4.02	Execution mechanism. The Bank will sign an agreement with the Executing Agency and an agreement with VRC. The Executing Agency, Partner of the Americas Inc. (the sole partner of the Executing Agency), and VRC will sign an agreement among them describing their respective responsibilities in the execution of the Technical Cooperation. The Executing Agency will supervise VRC to ensure effective adaptation and implementation of the “A Ganar” model, and VRC will carry out the same activities as the entities in the other countries but will be responsible for its counterpart funds. A Program Execution Unit (PEU) will be created in the Washington, D.C., headquarters of the Executing Agency. The PEU will have a director, a coordinator, a financial advisor, and an administrative assistant, who will be responsible for regional administrative, technical, and financial activities. VRC will have a PEU consisting of a project coordinator and a financial administrative specialist in Buenos Aires, Argentina. The entities affiliated with the Executing Agency are as follows: Instituto Companheiros das Américas in Brazil, in Colombia with Colombianos Apoyando Colombianos and the Southwestern Colombia (Cali) Partners of the Americas, Fundación para el Desarrollo de las Américas in Ecuador, and Fundación A Ganar in Uruguay. All have experience with the “A Ganar” model. They will be in charge of transferring their knowledge to new countries in which the Executing Agency has no affiliates. In some of these countries, entities have already been selected for Project execution, such as Fondation Espoir on l’Athlétique d’Haïti in Haiti. L’Athlétique will be a direct implementer of training but may also subcontract with other organizations based on need and opportunity. In Mexico, the Municipality of Juarez, Chihuahua, will sign an agreement with the Fundacion Comunitaria de la Frontera Norte, A.C, who will be responsible for management of Project. The Fundacion will be eligible to directly implement training but is also expected to subcontract training with other organizations in the area. For the Dominican Republic and Jamaica, the Executing Agency is operating with cooperative agreement with the United States Agency for International Development. Under the terms of that agreement, the Executing Agency has chosen a lead organization that will coordinate and supervise activities of the other implementing partners. The two lead organizations have been chosen, Entrena in Dominican Republic and UTech in Jamaica.  Each of these organizations will hire a local program coordinator/monitor and supervise other institutions who will implement training.  The implementing partners are to be chosen via competitive bids.  Those organizations will sign contracts directly with the Executing Agency and not the local lead organizations. In addition, the Exeucting Agency will sign subcontracts with the entities responsible for providing training in each country.

- 4.03	Financial monitoring. The Executing Agency will establish and maintain adequate financial accounts, internal control mechanisms, and record-keeping systems for the operation, in accordance with Bank financial administration policies.