## Detailed Procurement Plan
PROCUREMENT PLAN INITIAL LOAD INFORMATION (ONGOING AND/OR LAST PRESENTED)
GY-L1060 Detailed Proc. Plan
GOODS
Agency | Activity: | Additional Information: | Procurement Method (Select one) | Lots Quantity: | Amount in US$ : |  |  | Associated Component: | Review Method (Select one of the options): | Dates
[5 empty] | Estimated Amount, in US$ : | Estimated Amount, BID %: | Estimated Amount, Counterpart %: |  |  | Specific Procurement notice | Contract Signature
Component 1
MoA | Laptops, Project Management Software and Server | MOA & GBS Staff training | Shopping | Total Sum | 50000 | 100 | 0 | Component 1 | Ex-Ante | Q1 2018 | Q2 2018
Component 2
MoA | Vehicles Region 9&10 | One vehicle per region | Shopping | 2 | 55000 | 100 | 0 | Component 2 | Ex-Ante | Q3 2018 | Q4 2018
MoA | Research tools and equipment (microscope, scale…) | N/A | Shopping | Total Sum | 50000 | 100 | 0 | Component 2 | Ex-Ante | Q1 2018 | Q2 2018
MoA | Subscription to techical journals | Publications & paid subscription services to access specialized journals and purchase publications | DC | Total Sum | 5000 | 100 | 0 | Component 2 | Ex-Ante | Q2 2018 | Q2 2018
MoA | Laboratory equipment (autoclave; soil grinder; incubator; moisture content analyzer) | Region 9 & 10 | ICB | Total Sum | 120000 | 100 | 0 | Component 2 | Ex-Ante | Q2 2018 | Q2 2018
MoA | Materials/agricultural products (seeds, agricultural tools…) | Research Programs | Shopping | Total Sum | 75000 | 100 | 0 | Component 2 | Ex-Ante | Q2 2018 | Q2 2018
MoA | motorcycles/ATV | Research Program | Shopping | 5 | 50000 | 100 | 0 | Component 2 | Ex-Ante | Q3 2017 | Q3 2017
MoA | Fuel and maintenance | Ebini/Letem vehicles & ATVs incl. petrol, tires and wear & tear | NCB | Total Sum | 150000 | 100 | 0 | Component 2 | Ex-Ante | N/A | N/A
Component 3
MoA | Equipment Abattoir R9 | N/A | ICB | Total Sum | 400000 | 100 | 0 | Component 3 | Ex-Ante | N/A | Q3 2018
MoA | Equipment Abattoir R5 | N/A | ICB | Total Sum | 110000 | 100 | 0 | Component 3 | Ex-Ante | N/A | Q3 2018
Consulting Services
CONSULTING FIRMS/ INDIVIDUAL CONSULTANCIES
Agency | Activity: | Additional Information: | Procurement Method (Select one of the options): | Amount in US$ : |  |  | Associated Component: | Review Method (Select one of the options): | Dates
|  |  |  | Estimated Amount, in US$ : | Estimated Amount, BID %: | Estimated Amount, Counterpart %: |  |  | Specific Procurement notice | Contract Signature
Component 1
MoA | Agricultural Census | Consulting firm | SSS | 4000000 | 100 | 0 | Component 1 | Ex-Ante | N/A | Q1 2017
MoA | Update regulations and legal framework of the monitoring and eveluation of the agricultural sector | Individual Consultancy | NICQ | 20000 | 100 | 0 | Component 1 | Ex-Ante | Q2 2017 | Q3 2017
MoA | Support to the Monitoring and Evaluation Unit of MoA | Individual Consultancy | NICQ | 50000 | 100 | 0 | Component 1 | Ex-Ante | Q3 2017 | Q4 2017
MoA | Technical training for designated MoA & GBS staff (abroad) | Non-consulting service | Shopping | 30000 | 100 | 0 | Component 1 | Ex-Ante | Q2 2018 | Q3 2018
MoA | Technical training for designated MoA & GBS staff (in Guyana) | Non-consulting service | Shopping | 20000 | 100 | 0 | Component 1 | Ex-Ante | Q2 2018 | Q3 2018
Component 2
MoA | Design & Supervision Agri. Ctrs. Infrastructure | Consulting firm | QCBS | 680000 | 100 | 0 | Component 2 | Ex-Ante | Q1 2017 | Q2 2017
MoA | Researchers for the research centers | Individual Consultancy | NICQ & IICQ | 150000 | 100 | 0 | Component 2 | Ex-Ante | Q1 2017 | Q2 2017
MoA | Extension officers | Individual Consultancy | NCIS | 150000 | 100 | 0 | Component 2 | Ex-Ante | Q4 2017 | Q1 2018
MoA | Technical support to extension officers | Individual Consultancy | NCIS & ICIS | 225000 | 100 | 0 | Component 2 | Ex-Ante | Q1 2018 | Q2 2018
MoA | Training events | Non-consulting service | Shopping | 120000 | 100 | 0 | Component 2 | Ex-Ante | Q2 2018 | Q3 2018
MoA | Workshop on sustainable practices for farmers | Non-consulting service | Shopping | 75000 | 100 | 0 | Component 2 | Ex-Ante | Q3 2017 | Q4 2017
MoA | Technical training for designated MoA (abroad) | Non-consulting service | Shopping | 198000 | 100 | 0 | Component 2 | Ex-Ante | Q1 2019 | Q2 2019
MoA | Technical training for designated MoA (in Guyana) | Non-consulting service | Shopping | 40000 | 100 | 0 | Component 2 | Ex-Ante | Q3 2018 | Q4 2018
MoA | Support to EPA for compliance audits of environmental standards | Individual Consultancy | NICQ | 150000 | 100 | 0 | Component 2 | Ex-Ante | Q2 2018 | Q3 2018
Component 3
MoA | Design & supervision R9 | Consulting firm | QCBS | 100000 | 100 | 0 | Component 3 | Ex-Ante | Q1 2017 | Q2 2017
MoA | Design & supervision R5 | Consulting firm | QBS | 55000 | 100 | 0 | Component 3 | Ex-Ante | Q1 2017 | Q2 2017
MoA | Strengthening Producers' Assoc. R9 | Individual Consultancy | NICQ | 50000 | 100 | 0 | Component 3 | Ex-Ante | Q1 2018 | Q2 2018
MoA | Strengthening Producers' Assoc. R5 | Individual Consultancy | NICQ | 25000 | 100 | 0 | Component 3 | Ex-Ante | Q1 2018 | Q2 2018
MoA | Training for workers | Individual Consultancy | IICQ | 80000 | 100 | 0 | Component 3 | Ex-Ante | Q3 2018 | Q4 2018
MoA | Training for inspectors | Individual Consultancy | IICQ | 80000 | 100 | 0 | Component 3 | Ex-Ante | Q3 2018 | Q4 2018
MoA | Update and workshops for legal framework and regulations I, II, and III in separate lots | Individual Consultancy | NICQ & IICQ | 180000 | 100 | 0 | Component 3 | Ex-Ante | Q3 2017 | Q4 2017
Works
CONSULTING FIRMS/ INDIVIDUAL CONSULTANCIES
Agency: | Activity: | Additional Information: | Procurement Method (Select one of the options): | Amount in US$ : |  |  | Associated Component: | Review Method (Select one of the options): | Dates
|  |  |  | Estimated Amount, in US$ : | Estimated Amount, BID %: | Estimated Amount, Counterpart %: |  |  | Specific Procurement notice | Contract Signature
Component 1
Component 2
MoA | Buildings, Laboratories, Water Reservoir, and civil works in Region 9 | Works | ICB | 3100000 | 100 | 0 | Component 2 | Ex-Ante | Q3 2017 | Q4 2017
MoA | Buildings, Laboratories, and civil works in Region 10 | Works | NCB | 480000 | 100 | 0 | Component 2 | Ex-Ante | Q3 2017 | Q4 2017
Component 3
MoA | Construction of abattoir and associated waste management facilities in Region 9 | Works | ICB | 1200000 | 100 | 0 | Component 3 | Ex-Ante | Q4 2017 | Q1 2018
MoA | Construction of abattoir and associated waste management facilities in Region 5 | Works | ICB | 520000 | 100 | 0 | Component 3 | Ex-Ante | Q1 2018 | Q2 2018

## PEP Visual
PEP GY-L1060
|  |  |  | 2017/YR 1 | [11 empty] | 2018/YR 2 | [11 empty] | 2019/ YR 3 | [11 empty] | 2020/ YR 4 | [11 empty] | 2021/ YR 5 | [11 empty] | 2022/ YR 6 | [11 empty] | 2023
|  | Indicator | Total | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
| 1 | Component 1: Generating Information for evidence – based policy making and natural resource management | Total: 4170000
| 1.1 | Agricultural census | Total: 4000000
| 1.1.1 | Surveys before and after | Total: 300000
| 1.1.2 | Preparation | Total: 350000
| 1.1.3 | Field work and data collection | Total: 3000000
| 1.1.4 | Data analysis and cleaning | Total: 200000
| 1.1.5 | Analysis and publication | Total: 150000
| 1.2 | Support to the MoA for supervision | Total: 70000
| 1.2.1 | Update of regulations & legal framework | Total: 20000
| 1.2.2 | Support to the MOA for M&E | Total: 50000
| 1.3 | MoA and GSB staff trained | Total: 100000
| 1.3.1 | Training abroad | Total: 30000
| 1.3.2 | Training in Guyana | Total: 20000
| 1.3.3 | Equipement & software | Total: 50000
| 2 | Component 2: Strengthening of the agricultural innovation and extension system | Total: 6398000
| 2.1 | Agriculture centers built and refurbished | Total: 4460000
| 2.1.2 | Design & supervision of infrastructure | Total: 680000
| 2.1.4 | AC Region 10 | Total: 540000
| 2.1.4.1 | Infrastructure | Total: 480000
| 2.1.4.1.1 | Buildings | Total: 350000
| 2.1.4.1.2 | Laboratories | Total: 130000
| 2.1.4.2 | Equipment (laboratory equipment) | Total: 20000
| 2.1.4.3 | Vehicles | Total: 40000
| 2.1.5 | AC Region 9 | Total: 3240000
| 2.1.5.1 | Infrastructure | Total: 3100000
| 2.1.5.1.1 | Buildings | Total: 2500000
| 2.1.5.1.2 | Laboratories | Total: 100000
| 2.1.5.1.3 | Water reservoir | Total: 500000
| 2.1.5.2 | Equipment (laboratory equipment) | Total: 100000
| 2.1.5.3 | Vehicles | Total: 40000
| 2.2 | Research programs implemented | Total: 225000
| 2.2.1 | Consultants for research | Total: 150000
| 2.2.2 | Materials (agricultural products for centers) | Total: 50000
| 2.2.3 | Literature (subscriptions) | Total: 5000
| 2.2.4 | Participation in international events | Total: 20000
| 2.3 | Extension programs implemented | Total: 695000
| 2.3.1 | Consultants for extension | Total: 150000
| 2.3.2 | Technical support (extensionist) | Total: 225000
| 2.3.3 | Motorcycles (ATVs preferably) | Total: 50000
| 2.3.4 | Fuel and maintenance | Total: 150000
| 2.3.5 | Training | Total: 120000
| 2.4 | Farmers trained in the use and benefits of technologies promoted by AC | Total: 650000
| 2.4.1 | Incentives | Total: 500000
| 2.4.2 | Materials (agricultural products for farmers) | Total: 75000
| 2.4.3 | Workshops | Total: 75000
| 2.5 | NAREI and GLDA staff trained | Total: 238000
| 2.5.1 | Training abroad | Total: 198000
| 2.5.2 | Training in Guyana | Total: 40000
| 2.6 | Support to the EPA for supervision (audit comp. w/hygiene ) | Total: 130000
| 2.7.1 | Consultant | Total: 100000
| 2.7.2 | Travel and per diem | Total: 30000
| 3 | Component 3: Support for compliance with sanitary and phytosanitary standards | Total: 2800000
| 3.1 | Pilot facility to process meat in Region 9 implemented | Total: 1750000
| 3.1.1 | Stregthening of producer association | Total: 50000
| 3.1.2 | Design and Supervision of infrastructure | Total: 100000
| 3.1.4 | Infrastructure Works | Total: 1200000
| 3.1.5 | Equipment (abattoir equip.) | Total: 400000
| 3.2 | Pilot facility to process meat in Region 5 implemented | Total: 710000
| 3.1.1 | Stregthening of producer association | Total: 25000
| 3.1.2 | Design and Supervision of infrastructure | Total: 55000
| 3.1.4 | Infrastructure Works | Total: 520000
| 3.1.5 | Equipment | Total: 110000
| 3.3 | Number of people trained in SPS and food safety standards | Total: 160000
| 3.3.1 | Training workers (for example, meat handling practices) | Total: 80000
| 3.3.2 | Training inspectors (for example, inspectional control) | Total: 80000
| 3.4 | Update of legal framework and regulations | Total: 180000
| 3.4.1 | Regulation 1 | Total: 60000
| 3.4.1.1 | Consultants | Total: 40000
| 3.4.1.2 | Workshops | Total: 20000
| 3.4.2 | Regulation 2 | Total: 60000
| 3.4.2.1 | Consultants | Total: 40000
| 3.4.2.2 | Workshops | Total: 20000
| 3.4.3 | Regulation 3 | Total: 60000
| 3.4.3.1 | Consultants | Total: 40000
| 3.4.3.2 | Workshops | Total: 20000
| 0 | Total | Total: 15000000

## Source PEP
| Indicator | Total
1 | Component 1: Generating Information for evidence – based policy making and natural resource management | 4170000
1.1 | Agricultural census | 4000000
1.1.1 | Surveys before and after | 300000
1.1.2 | Preparation | 350000
1.1.3 | Field work and data collection | 3000000
1.1.4 | Data analysis and cleaning | 200000
1.1.5 | Analysis and publication | 150000
1.2 | Support to the MoA for supervision | 70000
1.2.1 | Update of regulations & legal framework | 20000
1.2.2 | Support to the MOA for M&E | 50000
1.3 | MoA and GSB staff trained | 100000
1.3.1 | Training abroad | 30000
1.3.2 | Training in Guyana | 20000
1.3.3 | Equipement & software | 50000
2 | Component 2: Strengthening of the agricultural innovation and extension system | 6398000
2.1 | Agriculture centers built and refurbished | 4460000
2.1.2 | Design & supervision of infrastructure | 680000
2.1.4 | AC Region 10 | 540000
2.1.4.1 | Infrastructure | 480000
2.1.4.1.1 | Buildings | 350000
2.1.4.1.2 | Laboratories | 130000
2.1.4.2 | Equipment (laboratory equipment) | 20000
2.1.4.3 | Vehicles | 40000
2.1.5 | AC Region 9 | 3240000
2.1.5.1 | Infrastructure | 3100000
2.1.5.1.1 | Buildings | 2500000
2.1.5.1.2 | Laboratories | 100000
2.1.5.1.3 | Water reservoir | 500000
2.1.5.2 | Equipment (laboratory equipment) | 100000
2.1.5.3 | Vehicles | 40000
2.2 | Research programs implemented | 225000
2.2.1 | Consultants for research | 150000
2.2.2 | Materials (agricultural products for centers) | 50000
2.2.3 | Literature (subscriptions) | 5000
2.2.4 | Participation in international events | 20000
2.3 | Extension programs implemented | 695000
2.3.1 | Consultants for extension | 150000
2.3.2 | Technical support (extensionist) | 225000
2.3.3 | Motorcycles (ATVs preferably) | 50000
2.3.4 | Fuel and maintenance | 150000
2.3.5 | Training | 120000
2.4 | Farmers trained in the use and benefits of technologies promoted by AC | 650000
2.4.1 | Incentives | 500000
2.4.2 | Materials (agricultural products for farmers) | 75000
2.4.3 | Workshops | 75000
2.5 | NAREI and GLDA staff trained | 238000
2.5.1 | Training abroad | 198000
2.5.2 | Training in Guyana | 40000
2.6 | Support to the EPA for supervision (audit comp. w/hygiene ) | 130000
2.7.1 | Consultant | 100000
2.7.2 | Travel and per diem | 30000
3 | Component 3: Support for compliance with sanitary and phytosanitary standards | 2800000
3.1 | Pilot facility to process meat in Region 9 implemented | 1750000
3.1.1 | Stregthening of producer association | 50000
3.1.2 | Design and Supervision of infrastructure | 100000
3.1.4 | Infrastructure Works | 1200000
3.1.5 | Equipment (abattoir equip.) | 400000
3.2 | Pilot facility to process meat in Region 5 implemented | 710000
3.1.1 | Stregthening of producer association | 25000
3.1.2 | Design and Supervision of infrastructure | 55000
3.1.4 | Infrastructure Works | 520000
3.1.5 | Equipment | 110000
3.3 | Number of people trained in SPS and food safety standards | 160000
3.3.1 | Training workers (for example, meat handling practices) | 80000
3.3.2 | Training inspectors (for example, inspectional control) | 80000
3.4 | Update of legal framework and regulations | 180000
3.4.1 | Regulation 1 | 60000
3.4.1.1 | Consultants | 40000
3.4.1.2 | Workshops | 20000
3.4.2 | Regulation 2 | 60000
3.4.2.1 | Consultants | 40000
3.4.2.2 | Workshops | 20000
3.4.3 | Regulation 3 | 60000
3.4.3.1 | Consultants | 40000
3.4.3.2 | Workshops | 20000