## Sheet1
Inter-American Development Bank
VPC/FMP
PROCUREMENT PLAN FOR NON-REIMBURSABLE TECHNICAL COOPERATIONS
Country: Jamaica |  |  |  |  | Executing agency: IDB (SCL/LMK) |  |  |  |  | Public or private sector: Public
Project number: JA-T1124 |  |  |  |  | Title of Project: Support for the strengthening of Active Labor Market Policies in Jamaica
Period covered by the plan: November 2016 - March 2019
Threshold for ex-post review of procurements: |  |  |  | Goods and services (in US$): |  | 85000 |  | Consulting services(in US$): | 150000
Item Nº | Ref. AWP | Description (1) | Estimated contract cost (US$) | Procurement Method (2) | Review of procurement (ex-ante or ex-post) (3) | Source of financing and percentage |  | Estimated date of the procurement notice or start of the contract | Technical review by the PTL (4) | Comments
[6 empty] | IDB/MIF % | Local/other %
Component 1: Building Effective Employer Engagement |  |  | 183000
Individual Consultants
1 |  | Design of employer-led skills agenda in one sector | 60000 | IICQ | n.a. | 100 |  | Q1 2017 | n/a
2 |  | Support for the revised design of the National Apprenticeship Programme | 45000 | IICQ | n.a. | 100 |  | Q1 2017 | n/a
3 |  | Communication Strategy | 8000 | IICQ | n.a. | 100
Non consulting services
4 |  | Workshops for employer-led skills agenda in one sector | 25000 | n.a. | n.a. | 100 |  | Q1 2017
5 |  | Training activities for National Council on Technical and Vocational Education and Training (NCTVET) and Heart Trust NTA | 25000 | n.a. | n.a. | 100 |  | Q1 2017 | n/a
6 |  | Skills Seminar/ Study tour | 20000 | n.a. | n.a. | 100 |  | Q4 2016 | n/a
Component 2: Capacity Building and Institutional Strengthening |  |  | 52000
Individual consultants
5 |  | Technical assistance to strengthen the ELE team's technical capacity | 37000 | SSS |  | 100 |  | Q1 2017 | n/a
Non consulting services
6 |  | Public employment service study tour | 15000 | n.a. |  | 100 |  | Q1 2017
Other |  |  | 15000
Non consulting services
|  | contingencies | 15000
Total |  |  | 250000 | Prepared by: Fernando Pavon |  |  | Date: October 11, 2016
(1) Grouping together of similar procurement is recommended, such as computer hardware, publications, travel, etc. If there are a number of similar individual contracts to be executed at different times, they can be grouped together under a single heading, with an explanation in the comments column indicating the average individual amount and the period during which the contract would be executed. For example: an export promotion project that includes travel to participate in fairs would have an item called "airfare for fairs", an estimated total value od US$5,000, and an explanation in the Comments column: "This is for approximately four different airfares to participate in fairs in the region in years X and X1".
(2) Goods and works: CB: Competitive bidding; PC: Price comparison; DC: Direct contracting.
(2) Consulting firms: CQS: Selection Based on the Consultants' Qualifications; QCBS: Quality and cost-based selection; LCS: Least Cost Selection; FBS: Selection nder a Fixed Budget; SSS: Single Source Selection; QBS: Quality Based selection.
(2) Individual consultants: IICQ: International Individual Consultant Selection Based on Qualifications; SSS: Single Source Selection.
(3) Ex-ante/ex-post review: In general, depending on the institutional capacity and level of risk associated with the procurement, ex-post review is the standard modality. Ex-ante review can be specified for critical or complex process.
(4) Technical review: The PTL will use this column to define those procurement he/she considers "critical"or "complex"that require ex ante review of the terms of reference, technical specifications, reports, outputs, or other items.

## Sheet2
Actividad/Componente | Descripción | BID | Total | %
Componente I: Fortalecimiento del Sistema de Pensiones |  | 120 | 120 | 60.3%
1.1) Diseño de propuesta de reforma a la política pública actual: factibilidad de un sistema mixto y otras opciones del sistema previsional. | Consultor individual, Viajes, Otros | 60
1.2) Estudio/Análisis de evaluación del proceso de inversión de fondo pensiones | Consultor individual, Viajes, Otros | 35
1.3) Estudio sobre Tablas de Mortalidad. | Consultor individual, Viajes, Otros | 25
Componente I: Actividades de diseminación y difusión |  | 70 | 70 | 35.18%
2) Socialización/Comunicación – Nota Conceptual (1) Comunicación & talleres de diseminación. | Consultores, Talleres, Seminarios, Publicaciones | 70
Imprevistos/Administración |  | 9 | 9 | 4.523%
TOTAL |  | 199 | 199 | 100%