# PROJECT PROCUREMENT PLAN

Update covering the period: January 2010 – June 2011

General information

Country: Bahamas

Borrower:

Executing agency: North Abaco Fishing Cooperative

Project name: Technical Support For North Abaco Society

Project and loan contract numbers: ATN/ME-11668-BH

Brief description of the project’s objectives and components: To equip participating fishermen and NAFCO with the technical and institutional capacity to consolidate their presence in the export market. The project consists of four primary components namely: To provide public education materials and multimedia content. Design a Financial & Risk Management System, Fisherman Training & Skill Development, & Institutional Strengthening of NAFCO. Design of a Feasibility study for a fish processing plant and a Strategic Development plan

Estimated date of project approval by the Board of Executive Directors:

Estimated date of signature of the loan contract: June 27, 2009

Estimated date of the final disbursement: June 27, 2011

- A. Introduction

Procurements for the proposed project will be carried out in accordance with the Policies for the Procurement of Works and Goods Financed by the Inter-American Development Bank (GN-2349-7); and the Policies for the Selection and Contracting of Consultants Financed by the Inter-American Development Bank (GN-2350-7), and with the provisions established in the loan contract and this procurement plan.

- B. Procurement plan

The procurement plan for Enhancing the Technical and Institutional capacity of the North Abaco Fishing Cooperative covering January 2010 to June 2011, 18 months of project execution has been agreed between the Bank and North Abaco Fishing Cooperative. The plan, which is summarized in Appendix 1, indicates the procedure to be used for the procurement of goods, the contracting of works or services, and the method of selecting consultants, for each contract or group of contracts. It also indicates cases requiring prequalification; the estimated cost of each contract or group of contracts; the requirement for prior or post review by the Bank; and estimated dates for the publication of specific procurement notices and completion of the contracts included in this project. The procurement plan will be updated annually or whenever necessary or as required by the Bank. The detailed procurement plan is available at:

the North Abaco Fishing Cooperative, Fox Town, North Abaco P.O. Box N-3903 Abaco, Bahamas.  It will also be published on the IDB website on page Project Procurement Information (www.iadb.org/procurement).

- C. Project procurement

The following is a general description of the procurement planned for the proposed project.

- Works procurement:  Nil

(b) Goods procurement: The goods to be procured for this project include the following: Materials for DVD production and other general materials for production of manuals, training and general office equipment These goods will be procured by local shopping.

There will be no project goods requiring ICB.

(c ) Procurement of consulting services: Consulting services for the project include:

- Rapid Assessment – Report on situation in the field

- Market Intelligence – Seminars & Workshops to address target market needs.

- Preparation of Production guidelines- Production of manuals and News booklet.

- Fisherman Training- STCW & HACCP training.

- Create DVD- Institutional Strengthening in Fishing.

- Cluster Development – Workshops

- Institutional Strengthening- Group strengthening workshop, Capacity Building seminar and Strategic Planning workshop.

These services will all be provided by either IICA experts or individual consultants.

Operating expenses: The following operating expenses will be financed by the Bank:

| Budget Item | MIF Contribution |
| --- | --- |
| Public & Participant Awareness | 12,000 |
| Fishermen Training & Skill Development | 22,500 |
| Project Administration | 17,000 |
| Institutional Strengthening (NAFCO) | 95,500 |
| Audit | 3,000 |
| Total Financed Expenses | 150,000 |

Project operating expenses to be financed by the Bank may be contracted using the executing agency’s procedures that have been previously reviewed by the Bank and classified as satisfactory.

Others: [N/A].

Advance contracting and retroactive financing: [N/A].

- D. Bank review of procurement decisions

Unless the Bank agrees otherwise in writing, the contracts for works and the acquisition of goods and related services shall be subject to ex-ante review, in accordance with Appendix 1 of the policies for the procurement of works and goods and the selection of consultants.

Appendix 1

# Procurement plan

Update covering the period: January 2010 – June 2011

Country: Bahamas

Borrower: North Abaco Cooperative Society Limited (NAFCO)

Executing agency: North Abaco Fishing Cooperative

Project name: Technical Support For North Abaco Cooperative Society Limited

Project and loan contract numbers: ATN/ME-11668-BH

Brief description of the project’s objectives and components: To equip participating fishermen and NAFCO with the technical and institutional capacity to consolidate their presence in the export market. The project consists of four primary components namely: To provide public education materials and multimedia content. Design of Financial & Risk Management System, Fisherman Training & Skill Development, Cluster Development & Institutional Strengthening of NAFCO. Design of a Feasibility study for a fish processing plant and a Strategic Development plan

Estimated date of project approval by the Board of Executive Directors:

Estimated date of signature of the loan contract: June 27, 2009

Estimated date of the final disbursement: June 27, 2011

Address of the executing agency office responsible for the procurement plan: North Abaco Fishing Cooperative POBox Fox Town Abaco Bahamas

| Ref. No. | Description and type of the procurement contract | Estimated Contract Cost (US$000) | Procurement method | Review (ex-ante or ex-post) | Source of financing and percentage |  | Pre-qualifi-cation (Yes/No) | Estimated dates |  | Status (pending, in process, awarded, cancelled) | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | IDB % | Local/ Other % |  | Publication of specific procurement notice | Completion of contract |  |  |
|  | - Goods - Good 1 Desktop Computer/ Office Equipment & Supplies - Good 2 Preparation of Printed Material Banners Brochures Flyers Business Cards - Good 3 Multi-Media Equipment- Video/DVD Camera, Whiteboard / screen - Good 4 Website Domain name/ Hosting Computer Software / Quickbooks - Good 5 Transporatation for Public & Participant Awareness Building Events | $1,500.00 $4,500.00 $1,500.00 $2,500.00 $1,200.00 | PC PC PC PC PC | Ex-ante Ex-ante Ex-ante Ex -ante Ex -ante | 72% 67% 67% 72% 67% | 28% 33% 33% 28% 33% | No No No Yes No | N/A N/A Jan 2010 Mar 2010 Jan 2010 | Jan 30, 2010 Dec 2010 Feb 2010 May 2010 Dec 2010 | Awarded In progress Awarded Awarded In progress |  |
|  | - Distribution & Marketing - Work 1 Radio Spots - Work 2 Television Spots - Work 2 Newspaper / Abaconian - Work 2 Website Marketing Pay Per Click Facebook/Google | $1,000.00 $ 2,800.00 $1,172.00 $500.00 | DC DC DC PC | Ex-ante Ex-ante Ex-ante Ex-post | 75% 75% 75% 75% | 25% 25% 25% 25% | No No No No | N/A N/A N/A Feb 2010 | Dec 2010 Dec 2010 Dec 2010 Dec 2010 | Pending In progress In progress In progress |  |
|  | - Non-consulting services - Service 1 Survey Data Collection - Service 2 Administrative Assistant | $3000 $12,000 | DC PC | Ex-ante Ex-ante | 75% 72% | 25% 28% | No No | N/A August 2009 | Dec 2010 Dec 2010 | In progress In progress |  |
|  | - Consulting services1 - Consulting services Business Management Seminar - Consulting services 2 Food Safety -HACCP Seminar & Workshops - Consulting services 3 Safety at Sea –STCW Certification Seminars & Workshops - Consulting services 6 Divers Safety Workshops - Consulting services 4 Sustainable Fishing Techniques Workshop - Consulting services 5 Cluster Development Workshops - Consulting services 6 Institutional Strengthening Board of Directors Workshops - Services Help Desk establishment Office Rental Utilities Furniture Computer | $1,500.00 $4,000.00 $4,000.00 $4,000.00 $2,800.00 $2,800.00 $2,800.00 $15,000.00 | DC DC DC DC DC DC DC PC | Ex-ante Ex-ante Ex-ante Ex-ante Ex-ante Ex-ante Ex-ante Ex-ante | 54% 54% 54% 54% 54% 54% 54% 54% | 46% 46% 46% 46% 46% 46% 46% 46% | No No No No No No No No | N/A N/A N/A N/A N/A N/A N/A N/A | May 26 2010 July 9, 2010 Jul10 2010 Aug09 2010 Oct10 2010 Nov10 2010 Dec10 2010 Dec10 2010 | Awarded Pending Pending Pending Pending Pending Pending Pending |  |

Appendix 2

Capacity of the executing agency and supervision of procurement by the Bank

Assessment of the executing agency’s capacity to administer procurement

North Abaco Fishing Cooperative (NAFCO) will be responsible for carrying out project procurements. Having assessed the capacity of the executing agency or a representative sample thereof if there are several to carry out the procurement actions, the Bank rates the overall risk to the project arising from the administration of procurement as:  AVERAGE.

| Item | Corrective action | Completion date | Comments |
| --- | --- | --- | --- |
| NAFCO will be expected to play a pivotal role in execution of this project and beyond. | Component 2 – Institutional Strengthening of NAFCO will address and support the capacity issues. | Start: Jan 1/10- Dec 14/10 | The Country Office will monitor the progress of this activity to ensure NAFCO’s strengthening. |
| Improve public awareness of Fisheries issues & the fishing community | Component 1-Public & Participant Awareness by improving the understanding of the fishing industry and its management. Further to enhance and provide basic information on the role of the industry to the community and others | Start: Jan 1/10- Dec 14/10 | Monitored by Country Office, IICA and NAFCO |
| Support the participation of members in the fishing industry, | Component 2 – Developing producer clusters, while helping the fishermen to improve and coordinate market penetration, quality assurance operations and joint learning activities | Start: Feb 1/10 – Dec14/10 | Monitored by Country Office, IICA & NAFCO coordinated with IICA |
| The creation of a strategic framework to guide NAFCO for the design of future programs | Component 2 - The development of a Strategic Plan by the Technical Advisor | Start Feb 1/10 –Nov 31/10 | Monitored by Country Office, IICA & NAFCO |
| The development of a communication system for the value chain of the Abaco lobster industry | Component 2 – Desk manual along with requisite spreadsheets will be produced by TA | Start Feb1/10 – June 30/10 | Monitored by Country Office and IICA |
| Management systems established for financial and risk mitigation | Component 2-NAFCO will be equipped with risk and financial management model by the Technical Advisor | Start: Jan1/10 – Mar 31/10 | Monitored by Country Office and IICA |
| Develop distribution and marketing plan | Component 1 – Model to be enacted by TA | Start Jan 1/10 – Mar 31/10 | Monitored by Country Office and NAFCO |
| Develop coordination strategy based on product lines and location | Component 2- guidelines for monitoring production, collection, analysis and dissemination of information on landings , exports etc. will be provided to NAFCO and the fishing operators. | Start Jan 1/10- June 31/10 | Monitored by Country Office and IICA |
| Training for practical business skills/tools for members (workshops on business planning, food safety and sustainable fishing). | Component 3 – Entrepreneurship Training & Skill Development: Members will be taught how to integrate business management and sustainable fishing techniques into their operations, Training material for future skill development programs for members will be provided | Start: Jan 1/10- Aug 31/10 | Monitored by Country Office and IICA & NAFCO |

Frequency of procurement supervision

In addition to prior reviews, the Bank will conduct post reviews of procurement every [QUARTER]. The frequency of post reviews and the thresholds established for the prior review of contracts are consistent with the assessment made of the executing agency’s capacity. These thresholds and the frequency of post reviews may be adjusted in the process of updating and revising the procurement plan, depending on the performance of the executing agency and the progress made in adopting the corrective measures described above.

The first 18 months of project execution are counted from the date of publication of the general procurement notice, or the first specific procurement notice published following approval of the loan, whichever is earlier.

All project contracts should be included, even if not financed by the Bank, indicating the source of funding in each case.

Goods and Works: ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through Specialized Agencies; PA: Procurement Agents; IA: Inspection Agents; PLFI: Procurement in Loans to Financial Intermediaries; BOO/BOT/BOOT: Build, Own, Operate/Build, Operate, Transfer/Build, Own, Operate, Transfer; PBP: Performance-Based Procurement; PLGB: Procurement under Loans Guaranteed by the Bank; PCP: Community participation procurement.  Consulting Firms: QCBS: Quality- and Cost-Based Selection QBS: Quality-Based Selection FBS: Selection under a Fixed Budget; LCS: Least-Cost Selection; CQS: Selection based on the Consultants’ Qualifications; SSS: Single-Source Selection.  Individual Consultants: NICQ: National Individual Consultant selection based on Qualifications; IICC: International Individual Consultant selection based on Qualifications

In the case of new Policies it applies only for Goods and Works.  In the case Old Procurement Policies it applies for Goods, Works and Consulting Services.

This column “Status” should be used for retroactive procurement and for procurement plan updates.