## Procurement Plan-
Project Name: AGRICULTURAL COMPETITIVENESS PROGRAM SURINAM
Project Number: SU- L1020 |  |  |  |  | Procurement Plan - January 2018 to June 2019
Executing Agency : LVV / PEU
PROCUREMENT PLAN PERIOD:
Ref. # | Component | Description/Contract Name: | Procurement Method | Lots Quantity: | Baseline Document | Contract Type | Estimated Amount, in u$s : | Associated Component:(if applicable) | Review Method (Ex-ante or Ex-post) | Process Status | Dates (If it does not apply, use N/A) | [15 empty] | Bidder | Proposal Price (Currency) | Comments
[11 empty] | Bidding Document |  | No objection to the Documents |  | Publication |  | Opening |  | Evaluation |  | No Objection to the Evaluation |  | Contract Signing |  | End of Contract
[11 empty] | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real
1.1.1.1-2-1 | Health and Food Safety | CONSTRUCTIONS AND IMPROVEMENTS: Upgrade of infrastructure of the plant health diagnostic laboratory (workbenches, cupboards, delivery areas, other) . | NCB |  | Bidding Document for Small Works | Unit Price | 160000 |  | EX-ANTE | Pending | 2018-07-19 |  | 2018-07-31 |  | 2018-08-07 |  | 2018-09-12 |  | 2018-10-15 |  | 2018-10-31 |  | 2018-12-04 |  | 2019-10-15
1.1.1.1-2-2 | Project Admin | PEU OFFICE EQUIPMENT AND UPGRADE : Supply and Installation Air Conditioning for office Program Executing Unit (PEU). | Shopping/PC |  | Request for Quotations | Unit Price | 8504 |  | EX-ANTE | Pending | 2018-02-08 |  | 2018-02-15 |  | n/a |  | n/a |  | 2018-02-28 |  | 2018-03-12 |  | 2018-03-21 |  | 2018-04-02
1.1.1.1-2-3 | Project Admin | PEU OFFICE EQUIPMENT AND IMPROVEMENT : Supply and Installation Works to Improvement Kitchen and other Areas of the PEU Office | Shopping/PC |  | Request for Quotations | Unit Price | 2700 |  | EX-ANTE | Pending | 2018-01-15 |  | 2018-01-21 |  | n/a |  | n/a |  | 2018-01-28 | 2018-01-26 | 2018-02-09 | 2018-02-12 | 2018-02-15 |  | 2018-03-21
1.1.1.1-2-4 | Project Admin | PEU OFFICE EQUIPMENT AND IMPROVEMENT : Supply and Installation Works to General Areas of the PEU Office - Minor Civil Works to Doors and Walls | Shopping/PC |  | Request for Quotations | Unit Price | 1500 |  | EX-ANTE | Pending | 2018-02-08 |  | 2018-02-15 |  | n/a |  | n/a |  | 2018-02-28 |  | 2018-03-12 |  | 2018-03-21 |  | 2018-03-21
1.1.1.1-2-5 | Project Admin | PEU OFFICE EQUIPMENT AND IMPROVEMENT : Supply and Installation Lamellen / Curtains to General Areas of the PEU Office | Shopping/PC |  | Request for Quotations | Unit Price | 2051 |  | EX-ANTE | Pending | 2018-02-08 |  | 2018-02-15 |  | n/a |  | n/a |  | 2018-02-28 |  | 2018-03-12 |  | 2018-03-21 |  | 2018-03-21
1.1.3.1-2-1 | Health and Food Safety | CONSTRUCTIONS AND IMPROVEMENTS: Upgrade/construction of infrastructure and office space at airports, including quarantine facility. | NCB |  | Bidding Document for Small Works | Unit Price | 155000 |  | EX-ANTE | Pending | 2018-10-18 |  | 2018-10-30 |  | 2018-11-06 |  | 2018-12-12 |  | 2019-01-14 |  | 2019-01-30 |  | 2019-03-05 |  | 2019-10-05
1.4.1.1-2-1 | Health and Food Safety | CONSTRUCTIONS AND IMPROVEMENTS: Execution of civil construction works for the Laboratory Complex. | Direct Contracting |  | N/A | Unit Price | 940000 |  | EX-ANTE | Pending | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | 2018-10-08 |  | 2019-10-30 |  |  |  | The Procurement Process used by LVV was reviewed and it was agreed in email dated Feb 17, 2017, that the procedure used to procedure the Civil, Electricaland Outfitting contracts met the IDB regulations and policy
1.4.1.1-2-2 | Health and Food Safety | CONSTRUCTIONS AND IMPROVEMENTS: Execution of Electrical and plumbing installations works for the Laboratory Complex. | Direct Contracting |  | N/A | Unit Price | 160000 |  | EX-ANTE | Pending | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | 2018-10-08 |  | 2019-10-30 |  |  |  | The Procurement Process used by LVV was reviewed and it was agreed in email dated Feb 17, 2017, that the procedure used to procedure the Civil, Electricaland Outfitting contracts met the IDB regulations and policy
2.2.5.2-2-1 | Research and Tech Transfer | CONSTRUCTIONS AND IMPROVEMENTS: Retrofitting of existing pesticide storage facilities or purchase of new pre-fabricated storage buildings/cabinets. | NCB |  | Bidding Document for Small Works | Unit Price | 215000 |  | EX-ANTE | Pending | 2018-04-19 |  | 2018-01-05 |  | 2018-05-08 |  | 2018-06-13 |  | 2018-07-16 |  | 2018-08-01 |  | 2018-09-04 |  | 2019-04-05
2.4.1.1-2-1 | Research and Tech Transfer | CONSTRUCTIONS AND IMPROVEMENTS: Execution of electrical and plumbing installations for the Cluster Laboratory | Direct Contracting |  | N/A | Unit Price | 850000 |  | EX-ANTE | Pending | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | 2018-10-08 |  | 2020-01-30 |  |  |  | The Procurement Process used by LVV was reviewed and it was agreed in email dated Feb 17, 2017, that the procedure used to procedure the Electricaland Outfitting contracts met the IDB regulations and policy
GOODS
Ref. # | Component | Description/Contract Name: | Procurement Method | Lots Quantity: | Baseline Document | Contract Type | Estimated Amount, in u$s : | Associated Component: | Review Method (Ex-ante or Ex-post) | Process Status | Dates (If it does not apply, use N/A) | [15 empty] | Bidder | Proposal Price (Currency) | Comments
[11 empty] | Bidding Document |  | No objection to the Documents |  | Publication |  | Opening |  | Evaluation |  | No Objection to the Evaluation |  | Contract Signing |  | End of Contract
[11 empty] | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real
1.4.1.1-2-3 | Health and Food Safety | Outfitting of Laboratory : Supply and Installation of Laboratory Equipment and Commissioning for the Lab Complex. | ICB | N/A | Standard Bidding Document for Goods | Unit Price | 200000 |  | EX-ANTE | Pending | 2018-08-10 |  | 2018-08-22 |  | 2018-08-28 |  | 2018-10-05 |  | 2018-11-05 |  | 2018-11-20 |  | 2018-12-08 |  | 2020-02-28
2.4.1.1-2-2 | Research and Tech Transfer | Outfitting of Laboratory : Supply and installation of Laboratory equipment for the Cluster Laboratory | ICB | N/A | N/A | Unit Price | 150000 |  | EX-ANTE | Pending | 2018-08-11 |  | 2018-08-23 |  | 2018-08-29 |  | 2018-10-06 |  | 2018-11-06 |  | 2018-11-21 |  | 2018-12-08 |  | 2020-02-28
1.1.5.1-1-1 | Health and Food Safety | COMMUNICATIONS, OTHER EQUIPMENT AND SUPPLIES: Purchase of GPS, mobile devices, tools, and other surveillance equipment. | Shopping/PC | N/A | Request for Quotations | Unit Price | 24805 |  | EX-ANTE | Pending | 2018-07-17 |  | 2018-08-02 |  | n/a |  | 2018-08-23 |  | 2018-09-12 |  | 2018-09-28 |  | 2018-10-12 |  | 2019-04-05
1.1.5.1-1-2 | Health and Food Safety and Project Admin | VEHICLES: Purchase of three (3) vehicles for official use in surveillance activities, LVV media Unit and PEU team | NCB | N/A | Standard Bidding Document for Goods | Unit Price | 130000 |  | EX-ANTE | Pending | 2018-01-18 | 2018-01-25 | 2018-01-30 |  | 2018-02-01 |  | 2018-03-01 |  | 2018-03-21 |  | 2018-04-02 |  | 2018-04-16 |  | 2018-07-15
1.1.5.2-1-1 | Health and Food Safety | SURVEILLANCE SUPPLIES: Purchase of supplies for the surveillance activities including vials, plates, scalpels, gloves and other. | Shopping/PC | N/A | Request for Quotations | Unit Price | 10000 |  | EX-ANTE | Pending | 2018-07-17 |  | 2018-08-02 |  | n/a |  | 2018-08-23 |  | 2018-09-12 |  | 2018-09-28 |  | 2018-10-12 |  | 2019-04-05
1.1.7.1-1-1 | Health and Food Safety | PHYTOSANITARY SUPPLIES: Purchase and installation of traps and lures in citrus plantation. | NCB | N/A | Standard Bidding Document for Goods | Unit Price | 70000 |  | EX-ANTE | Pending | 2018-07-19 |  | 2018-08-06 |  | 2018-08-07 |  | 2018-09-12 |  | 2018-10-15 |  | 2018-10-31 |  | 2019-07-01 |  | 2019-07-05
1.2.3.1-1-1 | Health and Food Safety | HARDWARE AND SOFTWARE: Purchase and installation of hardware (computers, wiring, telephones, printers, other,) and implementation of specific software applications for the animal health integrated information system of LVV. | ICB | N/A | Bidding Document for Goods | Unit Price | 148300 |  | EX-ANTE | Pending | 2018-07-19 |  | 2018-08-06 |  | 2018-08-07 |  | 2018-10-16 |  | 2018-11-16 |  | 2018-12-04 |  | 2019-01-07 |  | 2019-04-07
1.2.9.6-1-1 | Health and Food Safety | JOURNALS AND REFERENCE MATERIALS: Purchase of subscriptions to relevant journals and publications on risk assessment. | Shopping/PC | N/A | Request for Quotations | Unit Price | 4000 |  | EX-ANTE | Pending | 2018-07-17 |  | 2018-08-02 |  | n/a |  | 2018-08-23 |  | 2018-09-12 |  | 2018-09-28 |  | 2018-10-12 |  | 2019-04-05
1.3.6.9-1-1 | Health and Food Safety | IDENTIFICATION SYSTEMS: Purchase of ID card system for farmers including blank PVC cards, as part of the registration and inspection system. | NCB | N/A | Standard Bidding Document for Goods | Unit Price | 28000 |  | EX-ANTE | Pending | 2018-10-18 |  | 2018-11-05 |  | 2018-11-06 |  | 2018-12-12 |  | 2019-01-14 |  | 2019-01-30 |  | 2019-03-05 |  | 2019-05-05
2.2.1.2-1-1 | Research and Tech Transfer | HARDWARE AND SOFTWARE: Purchase of computer equipment and office applications for ODLOAV. | Shopping/PC | N/A | Request for Quotations | Unit Price | 1500 |  | EX-ANTE | Pending | 2018-07-17 |  | 2018-08-02 |  | n/a |  | 2018-08-23 |  | 2018-09-12 |  | 2018-09-28 |  | 2018-10-12 |  | 2019-04-05
2.2.3.3-1-1 | Research and Tech Transfer | FURNITURE: Purchase of office furniture for the media unit of LVV extension services. | Shopping/PC | N/A | Request for Quotations | Unit Price | 2000 |  | EX-ANTE | Pending | 2018-07-17 |  | 2018-08-02 |  | n/a |  | 2018-08-23 |  | 2018-09-12 |  | 2018-09-28 |  | 2018-10-12 |  | 2019-04-05
2.2.3.3-1-2 | Research and Tech Transfer | HARDWARE AND SOFTWARE: Purchase of computer equipment and office applications for the media unit of LVV extension services. | Shopping/PC | N/A | Request for Quotations | Unit Price | 11350 |  | EX-ANTE | Pending | 2018-07-17 |  | 2018-08-02 |  | n/a |  | 2018-08-23 |  | 2018-09-12 |  | 2018-09-28 |  | 2018-10-12 |  | 2019-04-05
2.2.3.6-1-1 | Research and Tech Transfer | MEDIA EQUIPMENT: Purchase of computer displays/data shows and other devices to support the field work of extension officers. | Shopping/PC | N/A | Request for Quotations | Unit Price | 22400 |  | EX-ANTE | Pending | 2018-07-17 |  | 2018-08-02 |  | n/a |  | 2018-08-23 |  | 2018-09-12 |  | 2018-09-28 |  | 2018-10-12 |  | 2019-04-05
2.2.5.1-1-1 | Research and Tech Transfer | PROTECTIVE EQUIPMENT: Purchase of Personal Protective Equipment (PPE) for LVV/ADRON pesticide applicators. | Shopping/PC | N/A | Request for Quotations | Unit Price | 20000 |  | EX-ANTE | Pending | 2018-07-17 |  | 2018-08-02 |  | n/a |  | 2018-08-23 |  | 2018-09-12 |  | 2018-09-28 |  | 2018-10-12 |  | 2019-04-05
II.B.1-1-1 | Health and Food Safety | HARDWARE AND SOFTWARE: Purchase of computer equipment and office applications for the Program Executing Unit (PEU). | Shopping/PC | N/A | Request for Quotations | Unit Price | 37230 |  | EX-ANTE | Pending | 2018-01-08 |  | 2018-01-20 |  | N/A |  | 2018-02-12 |  | 2018-03-14 |  | 2018-03-28 |  | 2018-04-12 |  | 2018-05-22
II.B.1-1-1.2 | Program Admin | HARDWARE AND SOFTWARE: Purchase of one Lap Top Computer for the Program Executing Unit (PEU) to support Quickbooks | Shopping/PC | N/A | Request for Quotations | Unit Price | 1020 |  | EX-ANTE | Completed | 2018-02-08 | n/a | 2018-02-20 |  | n/a |  | 2018-03-12 |  | 2018-04-17 |  | 2018-04-29 | 2018-01-12 | 2018-05-15 |  | 2018-06-30 |  | Computer Harware Services Ltd | 736.3444 | Procurement Process completed during the pre-eligibility phase and LVV subsequently received the non-objection for reimbursement.
II.B.1-1-1.3 | Program Admin | HARDWARE AND SOFTWARE: Purchase of Quickbook for the Program Executing Unit (PEU). | Shopping/PC | N/A | Request for Quotations | Unit Price | 3050 |  | EX-ANTE | Completed | 2018-02-08 |  | 2018-02-20 |  | n/a |  | 2018-03-12 |  | 2018-04-17 |  | 2018-04-28 | 2018-01-12 | 2018-05-15 |  | 2018-06-30 |  | Acfinsol | 2989.6689 | Procurement Process completed during the pre-eligibility phase and LVV subsequently recevied the non-objection for reimbursement.
II.B.2-1-1 | Program Admin | OFFICE EQUIPMENT: Purchase of office supplies , papers etc for Program Executing Unit (PEU). | Shopping/PC | N/A | Request for Quotations | Unit Price | 1800 |  | EX-ANTE | Pending | 2018-01-23 | 2018-02-02 | 2018-02-08 |  | n/a |  | 2018-03-01 |  | 2018-03-21 |  | 2018-04-06 |  | 2018-04-20 |  | 2018-06-20
II.B.2-1-2 | Program Admin | OFFICE EQUIPMENT: Purchase of Kitchen Appliances for Program Executing Unit (PEU). | Shopping/PC | N/A | Request for Quotations | Unit Price | 1300 |  | EX-ANTE | Pending | 2018-02-15 |  | 2018-02-28 |  | n/a |  | 2018-03-09 |  | 2018-03-21 |  | 2018-04-06 |  | 2018-04-20 |  | 2018-06-20
II.B.2-1-3 | Program Admin | OFFICE EQUIPMENT: Purchase of office furniture for Program Executing Unit (PEU). | Shopping/PC | N/A | Request for Quotations | Unit Price | 13000 |  | EX-ANTE | Pending | 2018-01-23 | 2018-02-02 | 2018-02-08 |  | n/a |  | 2018-03-01 |  | 2018-03-21 |  | 2018-04-06 |  | 2018-04-20 |  | 2018-06-20
NON CONSULTING SERVICES
Ref. # | Component | Description/Contract Name: | Procurement Method | Lots Quantity: | Baseline Document | Contract Type | Estimated Amount, in u$s : | Associated Component: | Review Method (Ex-ante or Ex-post) | Process Status | Dates (If it does not apply, use N/A) | [15 empty] | Bidder | Proposal Price (Currency) | Comments
[11 empty] | Bidding Document |  | No objection to the Documents |  | Publication |  | Opening |  | Evaluation |  | No Objection to the Evaluation |  | Contract Signing |  | End of Contract
[11 empty] | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real
1.1.2.4-3-1 | Health and Food Safety | Recurrent/various services in support to the strengthening of the import regulation framework. | Shopping/PC |  | Request for Quotations | Lump Sum | 78400 |  | Ex Ante | Pending | 2018-04-07 |  | 2018-04-17 |  | n/a |  | 2018-05-02 |  | 2018-06-13 |  | 2018-06-29 |  | 2018-07-13 |  | 2022-12-12
1.1.4.3-3-1 | Health and Food Safety | Execution of producer/exporter inspection and registration activities. | Shopping/PC |  | Request for Quotations | Lump Sum | 15000 |  | Ex Ante | Pending | 2018-04-07 |  | 2018-04-17 |  | n/a |  | 2018-05-02 |  | 2018-06-13 |  | 2018-06-29 |  | 2018-07-13 |  | 2022-12-12
1.1.4.4-3-1 | Health and Food Safety | Provision of services by various individuals and local businesses for fumigation, heat treatment, pest identification, applied research and other. | Shopping/PC |  | Request for Quotations | Lump Sum | 40000 |  | Ex Ante | Pending | 2018-04-07 |  | 2018-04-17 |  | n/a |  | 2018-05-02 |  | 2018-06-13 |  | 2018-06-29 |  | 2018-07-13 |  | 2022-12-12
1.1.5.3-3-1 | Health and Food Safety | Execution of priority crop/pest surveillance activities (various services and subcontracts). | Shopping/PC |  | Request for Quotations | Lump Sum | 231195 |  | Ex Ante | Pending | 2018-04-07 |  | 2018-04-17 |  | n/a |  | 2018-05-02 |  | 2018-06-13 |  | 2018-06-29 |  | 2018-07-13 |  | 2022-12-12 |  |  |  | The sum stated is the estimate cost is for the entire five years period. The intention here is to each year a detail programme of surveillence activities will be included in the Annual Operation Plan and an estimated budget of $47,239 will be assigned. This will be done in Phases.
1.1.9.3-3-1 | Health and Food Safety | Support to the establishment of an International Liaison Unit in LVV's Health Plant Service (various cost categories). | Shopping/PC |  | Request for Quotations | Lump Sum | 40000 |  | Ex Ante | Pending | 2018-04-07 |  | 2018-04-17 |  | n/a |  | 2018-05-02 |  | 2018-06-13 |  | 2018-06-29 |  | 2018-07-13 |  | 2022-12-12
1.2.11.1-3-1 | Health and Food Safety | AWARENESS CAMPAIGNS: Execution of awareness workshops aimed at preventing the introduction of exotic diseases, and motivating disease notification. | Shopping/PC |  | Request for Quotations | Lump Sum | 60000 |  | Ex Ante | Pending | 2018-07-17 |  | 2018-07-27 |  | n/a |  | 2018-08-13 |  | 2018-09-12 |  | 2018-09-28 |  | 2018-10-12 |  | 2022-09-30
1.2.11.2-3-1 | Health and Food Safety | PRINTING: Graphic design, printing and distribution of brochures and fact sheets with basic information on animal health and animal welfare. | Shopping/PC |  | Request for Quotations | Lump Sum | 15000 |  | Ex Ante | Pending | 2018-07-17 |  | 2018-07-27 |  | n/a |  | 2018-08-13 |  | 2018-09-12 |  | 2018-09-28 |  | 2018-10-12 |  | 2022-09-30
1.2.11.3-3-1 | Health and Food Safety | AWARENESS CAMPAIGNS: Execution of a workshop with and for the private sector for awareness raising. | Shopping/PC |  | Request for Quotations | Lump Sum | 30000 |  | Ex Ante | Pending | 2018-11-20 |  | 2018-12-02 |  | n/a |  | 2018-12-18 |  | 2019-01-22 |  | 2019-02-07 |  | 2019-02-21 |  | 2019-03-01
1.3.1.2-3-1 | Health and Food Safety | WORKSHOPS: Organization of workshops with stakeholders to discuss the drafted National Food Safety Policy. | Shopping/PC |  | Request for Quotations | Lump Sum | 4000 |  | Ex Ante | Pending | 2018-11-20 |  | 2018-12-02 |  | n/a |  | 2018-12-18 |  | 2019-01-22 |  | 2019-02-07 |  | 2019-02-21 |  | 2019-03-01
1.3.1.3-3-1 | Health and Food Safety | WORKSHOPS: Organization of workshops with stakeholders to discuss the implementation plans, budgets and operational manual of the National Food Safety Policy. | Shopping/PC |  | Request for Quotations | Lump Sum | 5000 |  | Ex Ante | Pending | 2018-11-20 |  | 2018-12-02 |  | n/a |  | 2018-12-18 |  | 2019-01-22 |  | 2019-02-07 |  | 2019-02-21 |  | 2019-03-01
1.3.2.1-3-1 | Health and Food Safety | SALARY SUPPORT: Appointment and payment of members of the Inter-Ministerial National Food Safety Committee and monitoring of implementation plan. | Shopping/PC |  | Request for Quotations | Lump Sum | 30000 |  | Ex Ante | Pending | 2018-11-20 |  | 2018-12-02 |  | n/a |  | 2018-12-18 |  | 2019-01-22 |  | 2019-02-07 |  | 2019-02-21 |  | 2019-03-01
1.3.2.2-3-1 | Health and Food Safety | WORKSHOPS: Organization of workshop to introduce and promote the Inter-Ministerial National Food safety Committee as coordinating mechanism. | Shopping/PC |  | Request for Quotations | Lump Sum | 1000 |  | Ex Ante | Pending | 2018-11-20 |  | 2018-12-02 |  | n/a |  | 2018-12-18 |  | 2019-01-22 |  | 2019-02-07 |  | 2019-02-21 |  | 2019-03-01
1.3.5.2-3-1 | Health and Food Safety | WORKSHOPS: Organization of workshops to discuss updated and final GAP standards for crops and pigs. | Shopping/PC |  | Request for Quotations | Lump Sum | 8000 |  | Ex Ante | Pending | 2018-11-20 |  | 2018-12-02 |  | n/a |  | 2018-12-18 |  | 2019-01-22 |  | 2019-02-07 |  | 2019-02-21 |  | 2019-03-01
1.3.5.4-3-1 | Health and Food Safety | WORKSHOPS: Organization of workshops to discuss draft and final GAP standards for livestock and aquaculture. | Shopping/PC |  | Request for Quotations | Lump Sum | 8000 |  | Ex Ante | Pending | 2018-07-17 |  | 2018-08-02 |  | n/a |  | 2018-08-23 |  | 2018-09-12 |  | 2018-09-28 |  | 2018-10-12 |  | 2018-11-30
1.3.5.6-3-1 | Health and Food Safety | WORKSHOPS: Organization of workshops to discuss the draft and final standards for fruits and vegetables, meat and fish. | Shopping/PC |  | Request for Quotations | Lump Sum | 12000 |  | Ex Ante | Pending | 2018-07-17 |  | 2018-08-02 |  | n/a |  | 2018-08-23 |  | 2018-09-12 |  | 2018-09-28 |  | 2018-10-12 |  | 2018-11-30
1.3.8.2-3-1 | Health and Food Safety | WORKSHOPS: Organization of workshops to discuss the scope of surveillance plan on food safety hazards. | Shopping/PC |  | Request for Quotations | Lump Sum | 2000 |  | Ex Ante | Pending | 2018-07-17 |  | 2018-08-02 |  | n/a |  | 2018-08-23 |  | 2018-09-12 |  | 2018-09-28 |  | 2018-10-12 |  | 2018-11-30
2.2.2.2-3-1 | Research and Tech Transfer | Workshops: Organization of bi-annual sub-sector consultations with the private sector as part of the activities of the National Agricultural Innovation Board. | Shopping/PC |  | Request for Quotations | Lump Sum | 9000 |  | Ex Ante | Pending | 2018-11-20 |  | 2018-12-02 |  | n/a |  | 2018-12-18 |  | 2019-01-22 |  | 2019-02-07 |  | 2019-02-21 |  | 2019-03-01
2.2.3.4-3-1 | Research and Tech Transfer | OTHER SERVICES: Design, development and maintenance of agricultural extension services Web site. | Shopping/PC |  | Request for Quotations | Lump Sum | 7250 |  | Ex Ante | Pending | 2018-11-20 |  | 2018-12-02 |  | n/a |  | 2018-12-18 |  | 2019-01-22 |  | 2019-02-07 |  | 2019-02-21 |  | 2019-03-01
2.2.3.5-3-1 | Research and Tech Transfer | OTHER SERVICES: Provision of Internet connectivity to LVV extension offices. | Shopping/PC |  | Request for Quotations | Lump Sum | 84000 |  | Ex Ante | Pending | 2018-11-20 |  | 2018-12-02 |  | n/a |  | 2018-12-18 |  | 2019-01-22 |  | 2019-02-07 |  | 2019-02-21 |  | 2019-03-01
CONSULTING FIRMS
Ref. # | Component | Description/Contract Name: | Procurement Method | Process Number: | Contract Type | Estimated Amount, in u$s : | Associated Component: | Review Method (Ex-ante or Ex-post) | Process Status | Dates (If it does not apply, use N/A) | [21 empty] | Short List Members | Technical Score Assigned | Evaluated Price Proposal (Currency ####) | Combined Score | Comments
[10 empty] | Expression of Interest Notice |  | RFP and Short List |  | No Objection to RFP and Short List |  | RFP Submission |  | Opening |  | Technical Evaluation |  | No Objection to the Technical Evaluation |  | Final Evaluation and Negotiation |  | No Objection to the Contract |  | Contract Signing |  | End of Contract
[10 empty] | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real
1.1.1.1-2-1.1 and 1.4.1.2.4.1 | Health and Food Safety | CONSULTING FIRM: National or international consultancy to Conduct a Civil, electrical and plumbing assesssment to ascertain the Scope Of Works required to Rehab the Plant Health diagnostic laboratory, Airport Quarantine Facility and the Residual Laboratory, and subsquent Supervision of the Construction Works. | QCBS |  | Lump Sum | 235000 |  | Ex Ante | Pending | 2018-01-08 | 2018-01-30 | 2018-01-19 |  | 2018-02-02 |  | 2018-02-23 |  | n/a |  | n/a |  | n/a |  | 2018-03-09 |  | 2018-03-19 |  | 2018-04-03 |  | 2019-09-29
2.4.1.2-4-1 | Research and Tech Transfer | CONSULTING FIRM: National or international consultancy to execute an assessment of the works done under the current contract and the supervision of the installation of electrical and plumbing works and outfitting of the Cluster Laboratory. | CQS |  | Lump Sum | 135000 |  | Ex Ante | Pending | 2018-01-08 |  | 2018-01-19 |  | 2018-02-02 |  | 2018-02-23 |  | n/a |  | n/a |  | n/a |  | 2018-03-09 |  | 2018-03-19 |  | 2018-03-30 |  | 2020-03-02
III.A-4-1 | External Audit | CONSULTING FIRM: National consultancy - independent accounting firm to conduct and prepare the annual external audits of the Program. | CQS |  | Lump Sum | 250000 |  | Ex Ante | Pending | 2018-10-19 |  | 2018-11-08 |  | 2018-11-19 |  | 2018-12-02 |  | n/a |  | n/a |  | n/a |  | 2019-01-10 |  | 2019-01-20 |  | 2019-02-02 |  | 2022-12-30
INDIVIDUAL CONSULTANTS
Ref. # | Component | Description/Contract Name: | Procurement Method | Process Number: | Estimated Amount, in u$s : | Estimated Number of Consultants: | Associated Component: | Review Method (Ex-ante or Ex-post) | Process Status | Dates (If it does not apply, use N/A) | [5 empty] | Consultant's Name | Period |  | Title | Comments
[10 empty] | No Objection to the TORs |  | Hiring Deadline |  | End of Activity |  |  | From | Until
[10 empty] | Estimated | Real | Estimated | Real | Estimated | Real
1.1.2.1-4-1 | Health and Food Safety | INDIVIDUAL CONSULTANT: International consultancy (plant health specialist) to design and prepare the training activities in Sanitary and Phytosanitary Measures (SPS) with respect to international standards. | IICQ |  | 17250 | 1 |  | EX-ANTE | Pending | 2018-10-15 |  | 2019-01-05 |  | 2019-03-30
1.1.2.1-4-1 | Health and Food Safety | INDIVIDUAL CONSULTANT: National Consultancy for a Legal Expert to review the existing contract for the Cluster Laboratory Complex and determine a way forward. | NICQ |  | 9000 | 1 |  | EX-ANTE | Pending | 2018-01-08 | 2018-01-16 | 2018-03-05 |  | 2018-04-30
1.1.2.1-4-2 | Health and Food Safety | INDIVIDUAL CONSULTANT: National consultancy (plant health specialist) to administer training activities in Sanitary and Phytosanitary Measures (SPS) with respect to international standards. | NICQ |  | 4500 | 1 |  | EX-ANTE | Pending | 2018-09-30 |  | 2019-01-05 |  | 2019-03-15
1.1.2.1-4-3 | Health and Food Safety | INDIVIDUAL CONSULTANT: National consultancy (animal health specialist) to administer training activities in Sanitary and Phytosanitary Measures (SPS) with respect to international standards. | NICQ |  | 4500 | 1 |  | EX-ANTE | Pending | 2018-09-30 |  | 2019-01-05 |  | 2019-03-15
1.1.2.1-4-4 | Health and Food Safety | INDIVIDUAL CONSULTANT: National consultancy (food safety specialist) to administer training activities in Sanitary and Phytosanitary Measures (SPS) with respect to international standards. | NICQ |  | 4500 | 1 |  | EX-ANTE | Pending | 2018-09-30 |  | 2019-01-05 |  | 2019-03-15
1.1.2.2-4-1 | Health and Food Safety | INDIVIDUAL CONSULTANT: International consultancy (plant health specialist) to prepare and update the pest lists and import requirements. | IICQ |  | 69750 | 1 |  | EX-ANTE | Pending | 2018-10-15 |  | 2019-01-10 |  | 2021-01-10
1.1.5.3-4-1 | Health and Food Safety | INDIVIDUAL CONSULTANT: National consultancy for the preparation of protocols and the execution of priority crop/pest surveillance activities. | NICQ |  | 42000 | 1 |  | EX-ANTE | Pending | 2018-04-15 |  | 2018-07-18 |  | 2022-11-30
1.1.7.2-4-1 | Health and Food Safety | INDIVIDUAL CONSULTANT: National consultancy for ALPP strategy development, planning for the intervention, and personnel training. | NICQ |  | 11200 | 1 |  | EX-ANTE | Pending | 2018-09-30 |  | 2018-12-07 |  | 2018-12-07
1.1.7.3-4-1 | Health and Food Safety | INDIVIDUAL CONSULTANT: National consultancy for the development of protocols on ALPP, and provision of training. | NICQ |  | 16800 | 1 |  | EX-ANTE | Pending | 2018-10-25 |  | 2018-11-07 |  | 2019-04-12
1.3.1.1-4-1 | Health and Food Safety | INDIVIDUAL CONSULTANT: International consultancy to prepare the draft national food safety policy including implementation plan, budget, and operational manual. | IICQ |  | 22500 | 1 |  | EX-ANTE | Pending | 2018-10-15 |  | 2018-11-20 |  | 2019-01-15
1.3.4.1-4-1 | Health and Food Safety | INDIVIDUAL CONSULTANT: National consultancy to update the regulations on meat inspection, and preparation of regulations for farm registration. | NICQ |  | 5600 | 1 |  | EX-ANTE | Pending | 2018-04-15 |  | 2018-07-05 |  | 2018-12-30
1.3.5.1-4-1 | Health and Food Safety | INDIVIDUAL CONSULTANT: National consultancy to review and update of national Good Agricultural Practices (GAP) standards for crops and pigs. | NICQ |  | 4000 | 1 |  | EX-ANTE | Pending | 2018-09-30 |  | 2018-11-30 |  | 2019-03-15
1.3.5.3-4-1 | Health and Food Safety | INDIVIDUAL CONSULTANT: National consultancy to prepare national GAP standards for livestock and aquaculture. | NICQ |  | 17000 | 1 |  | EX-ANTE | Pending | 2018-09-30 |  | 2018-11-30 |  | 2019-02-15
1.3.5.5-4-1 | Health and Food Safety | INDIVIDUAL CONSULTANT: National consultancy to prepare national code of practices and standards for fruits and vegetables, meat and fish. | NICQ |  | 21000 | 1 |  | EX-ANTE | Pending | 2018-04-15 |  | 2018-06-18 |  | 2019-02-15
1.3.5.11-4-1 | Health and Food Safety | INDIVIDUAL CONSULTANT: National consultancy for the design and execution of a food safety educational program for producers, and coordination with other institutions and stakeholders. | NICQ |  | 16000 | 1 |  | EX-ANTE | Pending | 2018-09-30 |  | 2018-11-30 |  | 2022-08-07
1.3.6.4-4-1 | Health and Food Safety | INDIVIDUAL CONSULTANT: National consultancy for the preparation of draft GAP inspection procedures manuals for crop, livestock and aquaculture. | NICQ |  | 22000 | 1 |  | EX-ANTE | Pending | 2018-04-15 |  | 2018-06-30 |  | 2018-12-30
1.3.7.6-4-1 | Health and Food Safety | INDIVIDUAL CONSULTANT: National consultancy for the preparation of laboratory quality assurance manual, and standard operating procedures manual, including registration forms for ISO17025. | NICQ |  | 16000 | 1 |  | EX-ANTE | Pending | 2018-10-25 |  | 2019-01-05 |  | 2019-05-12
1.3.12.2-4-1 | Health and Food Safety | INDIVIDUAL CONSULTANT: National consultancy to design, organize and execute laboratory services awareness campaigns. | NICQ |  | 20000 | 1 |  | EX-ANTE | Pending | 2018-10-25 |  | 2019-01-25 |  | 2021-12-12
2.2.1.1-4-1 | Research and Tech Transfer | INDIVIDUAL CONSULTANT: National consultancy for the preparation of project implementation protocols, including monitoring and evaluation guidelines. | NICQ |  | 6000 | 1 |  | EX-ANTE | Pending | 2018-04-15 |  | 2018-06-15 |  | 2018-11-30
2.2.1.3-4-1 | Research and Tech Transfer | INDIVIDUAL CONSULTANT: National consultancy to provide training in project management and implementation for project managers and senior project staff of ODLOAV, ODL and ADRON. Includes logistics. | NICQ |  | 5200 | 1 |  | EX-ANTE | Pending | 2018-07-30 |  | 2018-09-30 |  | 2018-11-30
2.3.1.1-4-1 | Research and Tech Transfer | INDIVIDUAL CONSULTANT: National consultancy to prepare the final design of project selection, monitoring and evaluation procedures (new and updates) | NICQ |  | 30000 | 1 |  | EX-ANTE | Pending | 2018-09-30 |  | 2018-11-30 |  | 2022-03-07
2.3.1.2-4-1 | Research and Tech Transfer | INDIVIDUAL CONSULTANT: National consultancy to provide specialized technical support for project assessment and evaluation (selection committee and secretariat). | NICQ |  | 25000 | 1 |  | EX-ANTE | Pending | 2018-09-30 |  | 2018-11-30 |  | 2022-03-07
2.3.1.3-4-1 | Research and Tech Transfer | INDIVIDUAL CONSULTANT: National consultancy to provide specialized technical support for project design and the preparation of project documents. | NICQ |  | 50000 | 1 |  | EX-ANTE | Pending | 2018-10-25 |  | 2019-01-30 |  | 2022-03-12
II.A.1.A-4-1 | Program Admin - PEU Staff Salaries | Programme Coordinator | NICQ |  | 48000 | 1 |  | EX-ANTE | Contracted | n/a |  | n/a |  | n/a
II.A.3.A-4-1 | Program Admin - PEU Staff Salaries | Financial Specialist | NICQ |  | 28800 | 1 |  | EX-ANTE | Contracted | n/a |  | n/a |  | n/a
II.A.4.A-4-1 | Program Admin - PEU Staff Salaries | Procurement Specialist | IICQ |  | 20800 | 1 |  | EX-ANTE | Contracted | n/a |  | n/a |  | n/a
II.A.4.B-4-1 | Program Admin - PEU Staff Salaries | Procurement Assistant | Seconded Ministry Staff |  | 4950 | 1 |  | EX-ANTE | Contracted | n/a |  | n/a |  | n/a
II.A.5.A-4-1 | Program Admin - PEU Staff Salaries | Social and Environmental Specialist | Seconded Ministry Staff |  | 4800 | 1 |  | EX-ANTE | Contracted | n/a |  | n/a |  | n/a
II.A.1.B-4-1 | Program Admin - PEU Staff Salaries | Technical Coordinator of Plant Health | Seconded Ministry Staff |  | 7200 | 1 |  | EX-ANTE | Contracted | n/a |  | n/a |  | n/a
II.A.1.C-4-1 | Program Admin - PEU Staff Salaries | Technical Coordinator of Animal Health | Seconded Ministry Staff |  | 7200 | 1 |  | EX-ANTE | Contracted | n/a |  | n/a |  | n/a
II.A.1.D-4-1 | Program Admin - PEU Staff Salaries | Technical Coordinator of Food Safety | Seconded Ministry Staff |  | 7200 | 1 |  | EX-ANTE | Contracted | n/a |  | n/a |  | n/a
II.A.1.E-4-1 | Program Admin - PEU Staff Salaries | Technical Coordinator of Agricultural Innovation | Seconded Ministry Staff |  | 7200 | 1 |  | EX-ANTE | Contracted | n/a |  | n/a |  | n/a
II.A.2.A-4-1 | Program Admin - PEU Staff Salaries | INDIVIDUAL CONSULTANT: Contracting of the Planning, Monitoring and Evaluation Specialist of the Program Executing Unit (PEU). | NICQ |  | 15360 | 1 |  | EX-ANTE | Pending | 2018-01-08 |  | 2018-03-08 |  | 2019-03-08
II.A.3.B-4-1 | Program Admin - PEU Staff Salaries | INDIVIDUAL CONSULTANT: Contracting of the Accountant of the Program Executing Unit (PEU). | NICQ |  | 2400 | 1 |  | EX-ANTE | Pending | 2018-01-08 |  | 2018-03-08 |  | 2019-03-08
II.A.6.A-4-1 | Program Admin - PEU Staff Salaries | INDIVIDUAL CONSULTANT: Contracting of the Administrative Assistant of the Program Executing Unit (PEU). | NICQ |  | 5000 | 1 |  | EX-ANTE | Pending | 2018-01-08 | 2018-02-01 | 2018-03-08 |  | 2019-03-08
TRAINING
Ref. # | Component | Description/Contract Name: | Procurement Method | Process Number: | Contract Type | Estimated Amount, in u$s : | Associated Component: | Review Method (Ex-ante or Ex-post) | Process Status | Dates (If it does not apply, use N/A) | [5 empty] | Detail | Amount (Currency ) | Comments
[10 empty] | Annual Training Plan (ATP) |  | No Objection to the ATP |  | End of Activity
[10 empty] | Estimated | Real | Estimated | Real | Estimated | Real
1.1.6.1-3-1 | Health and Food Safety | POST GRADUATE EDUCATION: Masters Degree-level studies in Crop Protection for three LVV staff members. | N/A |  | Lump Sum | 80000 |  | Ex Ante | Pending | 2018-02-02 |  | 2018-02-16 |  | 2020-06-30 |  |  |  | An International accredited University will be identified and the programme offered will be analysed to ensure it meets the objectives.
1.1.6.5-3-1 | Health and Food Safety | TECHNICAL TRAINING: Participation of laboratory technicians in specialized course in plant health laboratory procedures. | Shopping / PC |  | Lump Sum | 14000 |  | Ex Ante | Pending | 2019-03-02 |  | 2019-03-16 |  | 2019-06-16 |  |  |  | Given the limited number of companies that offer these types of specialized training it may be difficult to identify three companies. Shopping is therefore recommended for the planning phase.
1.1.6.6-3-1 | Health and Food Safety | TECHNICAL TRAINING: Participation by the Head of National Plant Protection Organization (NPPO) in a specialized management course for plant health service. | Shopping / PC |  | Lump Sum | 15000 |  | Ex Ante | Pending | 2019-03-02 |  | 2019-03-16 |  | 2019-06-16 |  |  |  | Given the limited number of companies that offer these types of specialized training it may be difficult to identify three companies. Shopping is therefore recommended for the planning phase.
1.1.6.7-3-1 | Health and Food Safety | TECHNICAL TRAINING: Participation of selected LVV personnel in external training/course in SPS standards and their application. | Shopping / PC |  | Lump Sum | 35000 |  | Ex Ante | Pending | 2018-02-02 |  | 2018-02-16 |  | 2018-08-16 |  |  |  | Given the limited number of companies that offer these types of specialized training it may be difficult to identify three companies. Shopping is therefore recommended for the planning phase.
1.1.6.8-3-1 | Health and Food Safety | TECHNICAL TRAINING: Participation of selected LVV personnel in Pest Risk Analysis (PRA) theory and practice course. | Shopping / PC |  | Lump Sum | 22000 |  | Ex Ante | Pending | 2019-03-02 |  | 2019-03-16 |  | 2019-06-16 |  |  |  | Given the limited number of companies that offer these types of specialized training it may be difficult to identify three companies. Shopping is therefore recommended for the planning phase.
1.1.6.10-3-1 | Health and Food Safety | TECHNICAL TRAINING: Participation of selected LVV personnel in awareness training on biosecurity in the national economy and promoting national support. | Shopping / PC |  | Lump Sum | 20000 |  | Ex Ante | Pending | 2018-04-04 |  | 2018-04-20 |  | 2018-07-20 |  |  |  | Given the limited number of companies that offer these types of specialized training it may be difficult to identify three companies. Shopping is therefore recommended for the planning phase.
1.1.6.11-3-1 | Health and Food Safety | TECHNICAL TRAINING: Participation of LVV laboratory staff and inspectors in occupational health and safety training sessions/courses. | Shopping / PC |  | Lump Sum | 8000 |  | Ex Ante | Pending | 2018-04-04 |  | 2018-04-20 |  | 2018-07-20 |  |  |  | Given the limited number of companies that offer these types of specialized training it may be difficult to identify three companies. Shopping is therefore recommended for the planning phase.
1.1.8.3-3-1 | Health and Food Safety | TRAINING: Organization of training workshops for the Pesticide Control Board (Shopping/PCB) and other stakeholders (producers, managers, inspectors, retailers, other) | Shopping / PC |  | Lump Sum | 80000 |  | Ex Ante | Pending | 2019-03-02 |  | 2019-03-16 |  | 2019-10-16 |  |  |  | Given the limited number of companies that offer these types of specialized training it may be difficult to identify three companies. Shopping is therefore recommended for the planning phase.
1.1.4.1-3-1 | Health and Food Safety | TRAINING: Organization of training sessions on pest detection for inspectors. | Shopping / PC |  | Lump Sum | 20600 |  | Ex Ante | Pending | 2018-04-04 |  | 2018-04-20 |  | 2018-07-20 |  |  |  | Given the limited number of companies that offer these types of specialized training it may be difficult to identify three companies. Shopping is therefore recommended for the planning phase.
1.1.4.3-3-2 | Health and Food Safety | TRAINING: Organization of training and awareness sessions for producers/exporters on registration and compliance. | Shopping / PC |  | Lump Sum | 24000 |  | Ex Ante | Pending | 2018-06-06 |  | 2018-06-20 |  | 2018-12-20 |  |  |  | Given the limited number of companies that offer these types of specialized training it may be difficult to identify three companies. Shopping is therefore recommended for the planning phase.
1.2.5.1-3-1 | Health and Food Safety | TRAINING: Training sessions for LVV's Veterinary Services staff on emerging diseases, notifications and inspections. | Shopping / PC |  | Lump Sum | 45000 |  | Ex Ante | Pending | 2018-06-06 |  | 2018-06-21 |  | 2018-12-21 |  |  |  | Given the limited number of companies that offer these types of specialized training it may be difficult to identify three companies. Shopping is therefore recommended for the planning phase.
1.2.6.1-3-1 | Health and Food Safety | POST GRADUATE EDUCATION: Masters Degree-level studies in Veterinary Public Health Management for the Chief Veterinary Officer (CVO) of LVV. | N/A |  | Lump Sum | 51250 |  | Ex Ante | Pending | 2018-06-07 |  | 2018-06-22 |  | 2018-12-21 |  |  |  | An International accredited University will be identified and the programme offered will be analysed to ensure it meets the objectives.
1.3.6.1-3-1 | Health and Food Safety | TECHNICAL TRAINING: Organization and execution of training/courses and coaching plan on Quality Assurance for inspection units. | Shopping / PC |  | Lump Sum | 45500 |  | Ex Ante | Pending | 2018-08-08 |  | 2018-08-20 |  | 2018-10-20 |  |  |  | Given the limited number of companies that offer these types of specialized training it may be difficult to identify three companies. Shopping is therefore recommended for the planning phase.
1.3.7.10-3-1 | Health and Food Safety | TECHNICAL TRAINING: Implementation of a training and coaching program plan on Laboratory Quality Assurance. | Shopping / PC |  | Lump Sum | 22750 |  | Ex Ante | Pending | 2018-08-08 |  | 2018-08-21 |  | 2018-10-21 |  |  |  | Given the limited number of companies that offer these types of specialized training it may be difficult to identify three companies. Shopping is therefore recommended for the planning phase.
2.2.1.2-3-1 | Research and Tech Transfer | TRAINING: Provision of training to ODLOAV project bureau in budgetary aspects. | Shopping / PC |  | Lump Sum | 5000 |  | Ex Ante | Pending | 2018-08-08 |  | 2018-08-22 |  | 2018-09-22 |  |  |  | Given the limited number of companies that offer these types of specialized training it may be difficult to identify three companies. Shopping is therefore recommended for the planning phase.
2.2.2.3-3-1 | Research and Tech Transfer | TRAINING: Provision of technical training to build the capacity of the National Agricultural Innovation Board. | Shopping / PC |  | Lump Sum | 5000 |  | Ex Ante | Pending | 2018-08-09 |  | 2018-08-23 |  | 2018-09-23 |  |  |  | Given the limited number of companies that offer these types of specialized training it may be difficult to identify three companies. Shopping is therefore recommended for the planning phase.
2.2.3.2-3-1 | Research and Tech Transfer | TECHNICAL TRAINING: Provision of staff training in modern media technology and methods for the LVV extension service through UNASAT. | Shopping / PC |  | Lump Sum | 4000 |  | Ex Ante | Pending | 2018-10-10 |  | 2018-10-24 |  | 2018-12-15 |  |  |  | Given the limited number of companies that offer these types of specialized training it may be difficult to identify three companies. Shopping is therefore recommended for the planning phase.
2.2.4.1-3-1 | Research and Tech Transfer | PROFESSIONAL TRAINING: Participation of LVV researchers in university level courses to upgrade their Bachelor of Science and Master of Science levels. | N/A |  | Lump Sum | 30000 |  | Ex Ante | Pending | 2018-10-11 |  | 2018-10-25 |  | 2018-12-16 |  |  |  | An International accredited University will be identified and the programme offered will be analysed to ensure it meets the objectives.
2.2.4.2-3-1 | Research and Tech Transfer | ACADEMIC TRAINING: Participation of LVV research technicians in courses to upgrade to the HAVO/HBO level . | N/A |  | Lump Sum | 25000 |  | Ex Ante | Pending | 2018-10-12 |  | 2018-10-26 |  | 2018-12-17 |  |  |  | An International accredited University will be identified and the programme offered will be analysed to ensure it meets the objectives.
2.2.4.3-3-1 | Research and Tech Transfer | ACADEMIC TRAINING: Participation of LVV extension staff in courses to upgrade to the HAVO/HBO level . | N/A |  | Lump Sum | 50000 |  | Ex Ante | Pending | 2019-01-05 |  | 2019-01-19 |  | 2019-03-20 |  |  |  | An International accredited University will be identified and the programme offered will be analysed to ensure it meets the objectives.
2.2.4.4-4-1 | Research and Tech Transfer | TECHNICAL TRAINING: Participation by LVV research staff in specialized courses and training (green technologies, economic analysis, entomology, mycology, water management, other). | Shopping / PC |  | Lump Sum | 61000 |  | Ex Ante | Pending | 2019-01-05 |  | 2019-01-20 |  | 2019-03-21 |  |  |  | Given the limited number of companies that offer these types of specialized training it may be difficult to identify three companies. Shopping is therefore recommended for the planning phase.
2.2.4.5-4-1 | Research and Tech Transfer | TECHNICAL TRAINING: Participation by LVV research and/or extension staff in-house courses and training (statistical analysis, extension and communication, pesticides spraying, other). | Shopping / PC |  | Lump Sum | 35000 |  | Ex Ante | Pending | 2019-01-05 |  | 2019-01-21 |  | 2019-03-22 |  |  |  | Given the limited number of companies that offer these types of specialized training it may be difficult to identify three companies. Shopping is therefore recommended for the planning phase.
1.3.10.7-3-1 | Health and Food Safety | POST GRADUATE EDUCATION: Masters Degree-level studies in Agri-Food Safety and Quality Assurance for two LVV personnel. | n/a |  | Lump Sum | 30000 |  | Ex Ante | Pending | 2019-01-06 |  | 2019-01-22 |  | 2022-03-22 |  |  |  | An International accredited University will be identified and the programme offered will be analysed to ensure it meets the objectives.
1.2.8.1-3-1 | Health and Food Safety | TECHNICAL TRAINING: Participation of the Chief Veterinary Officer (CVO) in meetings of the World Organization for Animal Health (OIE). | N/A |  | Lump Sum | 10750 |  | Ex Ante | Pending | 2019-01-06 |  | 2019-01-22 |  | 2022-03-22 |  |  |  | This represents the cost associated with attending a specific accredited meeting.
1.2.9.7-3-1 | Health and Food Safety | TECHNICAL TRAINING: Participation of LVV personnel in annual meetings of the OIE. | N/A |  | Lump Sum | 17000 |  | Ex Ante | Pending | 2019-01-06 |  | 2019-01-22 |  | 2022-03-22 |  |  |  | This represents the cost associated with attending a specific accredited meeting.
Goods and Works: ICB: International Competitive Bidding; LIB: Limited International Bidding; NCB: National Competitive Bidding; Shopping/PC: Price Comparison; DC: Direct Contracting; FA: Force Account; PSA: Procurement through Specialized Agencies; PA: Procurement Agents; IA: Inspection Agents; PLFI: Procurement in Loans to Financial Intermediaries; BOO/BOT/BOOT: Build, Own, Operate/Build, Operate, Transfer/Build, Own, Operate, Transfer; PBP: Performance-Based Procurement;
PLGB: Procurement under Loans Guaranteed by the Bank; CPP: Community participation procurement.
Consulting Firms: QCBS: Quality-and Cost-Based Selection QBS: Quality-Based Selection FBS: Selection under a Fixed Budget; LCS: Least-Cost Selection; CQS: Selection based on the Consultants’ Qualifications; SSS: Single-Source Selection.
Individual Consultants: NICQ: National Individual Consultant selection based on Qualifications; IICQ: International Individual Consultant selection based on Qualifications.
Formulas:
No objection to the Documents = [Dates (If it does not apply, use N/A)]+12
Publication = [No objection to the Documents]+2
Opening = [Publication]+28
Evaluation = [Opening]+20
No Objection to the Evaluation = [Evaluation]+12
Contract Signing = [No Objection to the Evaluation]+14
End of Contract = [Contract Signing]+90
Proposal Price (Currency) = [Real]+15