## Sheet1
PROCUREMENT PLAN FOR NON-REIMBURSABLE TECHNICAL COOPERATIONS
Country: REGIONAL |  |  |  |  | Executing agency: INT/TIN |  |  |  |  | Public or private sector: Public
Project number: RG-T3048 |  |  |  |  | Title of Project: Enhancing Korea-LAC Partnership in Trade and Investment
Period covered by the plan: 24 Months
Threshold for ex post review of procurements: |  |  |  | Goods and services (in US$):____________ |  | 400000 |  | Consulting services(in US$):____________ | 270000
Item No. | Ref. AWP | Description (1) | Estimated contract cost (US$) | Procurement Method (2) | Review of procurement (ex-ante or ex-post) (3) | Source of financing and percentage |  | Estimated date of the procurement notice or start of the contract | Technical review by the PTL (4) | Comments
[6 empty] | IDB/MIF % | Local/other %
Individual Consultants
1 |  | Individual consultants to provide technical asistance for the preparation, coordination and execution of the Korea-LAC Business Summit | 60000 | IICQ | Ex-Post | 100% | 0% | 2017-06-01 | N/A | Individual consultants will support Component I, II and TC execution and monitoring.
Consulting firms
2 |  | Consulting firm to provide technical assistance as well as integrated logistic support for the Korea-LAC Business Summit 2017 in Seoul, Republic of Korea (all relevant and technical tasks for the Business Matchmaking and Korea-LAC Business Forum): Participation of panelists, venue, promotional materials, exhibition booths, intepretation services, local transportation and OA equipments. | 210000 | SSS | Ex-Post | 100% | 0% | 2017-07-01 | N/A | The donor has made a strong suggestion of a consulting firm that has supported previous versions of the Korea-LAC Business Summit. For this contract, the Bank's Corporate Procurement Procedures will apply.
Non Consulting Services
3 |  | Travel Arrangements for speakers, moderators and Investment Promotion Agencies (IPAs) from the region | 180000 | SSS | Ex-Post | 100% | 0% | 2017-07-01 | N/A | Ultramar does not possess the capability of handling this event, where more than 50 participants from the region will be travelling to Korea in seperate itineraries. The International firm considered for this task has broad experience dealing with large groups and has previously worked with the bank, performing with excellency and is familiar to the bank's payment process.
4 |  | Venue for the Korea-LAC Forum and Business Matchmaking, catering, accomodation of participants and networking events | 220000 | DC | Ex-Post | 100% | 0% | 2017-08-01 | N/A | The donor has made a venue suggestion, considering the accesibility, facility and previous experiences of having hosted international conferences there.
Total |  |  | 670000 | Prepared by: Sunghee Ahn |  |  | Date: May 19, 2017
(1) Grouping together of similar procurement is recommended, such as computer hardware, publications, travel, etc. If there are a number of similar individual contracts to be executed at different times, they can be grouped together under a single heading, with an explanation in the comments column indicating the average individual amount and the period during which the contract would be executed. For example: an export promotion project that includes travel to participate in fairs would have an item called "airfare for fairs", an estimated total value od US$5,000, and an explanation in the Comments column: "This is for approximately four different airfares to participate in fairs in the region in years X and X1".
(2) Goods and works: CB: Competitive bidding; PC: Price comparison; DC: Direct contracting.
(2) Consulting firms: CQS: Selection Based on the Consultants' Qualifications; QCBS: Quality and cost-based selection; LCS: Least Cost Selection; FBS: Selection nder a Fixed Budget; SSS: Single Source Selection; QBS: Quality Based selection.
(2) Individual consultants: IICQ: International Individual Consultant Selection Based on Qualifications; SSS: Single Source Selection.
(3) Ex ante/ex post review: In general, depending on the institutional capacity and level of risk associated with the procurement, ex post review is the standard modality. Ex ante review can be specified for critical or complex process.
(4) Technical review: The PTL will use this column to define those procurement he/she considers "critical"or "complex"that require ex ante review of the terms of reference, technical specifications, reports, outputs, or other items.