## Slide 1: FINAL DRAFT Report visit May 9-13 Operations / Project Management Support
BA-L1002 Barbados Housing and Neighborhood Upgrading Program Phase 1
16 May 2011

## Slide 2: Agenda
Objectives, Scope and Schedule
Diagnosis / observations
Recommendations
Deliverables
Action Plan

## Slide 3: Objective & Scope
The objective was to provide specific operational and technical support to the PCMU and Bank’s Operations Analyst and increase their managerial capacity.
Scope
Coaching PCMU and Bank on overall Project Management processes, including Project Scope Management, Project Time Management and Project Results Management (Communications)
Deliverables: Disbursement Project Tables, Project Management Plan and Annual Operating Plan (AOP)

## Slide 4: Schedule / Work Plan
Planned
Monday May 9th
  Meeting with PS
  WS 1 – Big Picture / Overview
Tuesday May 10th
  WS 2 – Manage Scope
Wednesday May 11th
  WS 3 – Manage Time
Thursday May 12th
  WS 4 – Manage Results & Communication
Friday May 13th
  Update deliverables: Disbursement Projection Tables, Annual Operations Plan, Project Management Plan
  Close out / wrap up meeting
Actual
Monday May 9th
Meeting with PS
WS 1 – Overview with C1 (NU)
Tuesday May 10th
am WS 1&2 (scope) C2 (AH)
pm WS 2 (manage scope) with C3 (IS) & C4 (Admin/Fin)
Wednesday May 11th
am WS manage scope with C1
pm update IDB Ops Analyst
Thursday May 12th
am Sr. Acct on budget & disb
am/pm WS time (AOP) w C1
pm WS time (AOP) with C2
Friday May 13th
WS time (AOP) with C3
Deliverables: DPT, AOP, PMP
Close out / wrap up meetings
Notes: Due to several other commitments by the project team during the week of May 9-13th, it was decided to change the work plan from sessions for the whole team to sessions per component.

## Slide 5: Diagnosis
May 9-13, 2011

## Slide 6: Observations / 1
Very good project facilities
Team is helping out each other
AOP sufficiently detailed
Notes: Very good project facilities
  Team is co-located and located within the Ministry of Housing
  Team has access to computers, printers, copier and plotter
  Team has access to meeting room, projector and flipchart
Team is helping out each other
For example Marketing promotions on three Saturdays in May
AOP sufficiently detailed
A good part of the scope elements that are included in the AOP are sufficiently detailed. However, AOP are not covering all scope / activities (e.g. project management activities, community participation committees, Land Info System, issue resolution activities)

## Slide 7: Triple Constraint Start of Project
Start: 8 April 2008 Finish: 8 April 2013
Time
Scope / Results
Neighborhood Upgrading (12 Periurban neighborhood + 2 inner-city neighborhood improvement projects + 4 Community Participation Comm)
Affordable Housing (320 housing units, (400 subsidies for new houses and 600 subsidies for incremental home construction)
Institutional Strengthening (BSS, SSS, LIS)
Cost
IDB: USD 30,000,000
+
GOB: USD 10,000,000
Note: Scope / Results based on Disbursement Projection Tables April 2011
Notes: Triggers for phase 2 according to the loan document (Triggers for the Second Phase of the Program, p15, Barbados Proposal for a loan for a housing and neighborhood upgrading program Phase I)
Neighborhood Upgrading (> 400 lots developed)
Affordable Housing (> 100 subsidies for new houses and > 200 subsidies for incremental home construction)
Institutional Strengthening (efficient and transparent beneficiary selection system and new information and financial systems in operation)

## Slide 8: Triple Constraint Status April 2011
Start: 8 April 2008 Finish: 8 April 2013
Time
Scope
Neighborhood Upgrading
Production of Affordable Housing
Institutional Strengthening
Others
Cost
Budget IDB: USD 30,000,000
Note: Actual cost taken from Executive Financial Summary For 1953/OC-BA As of 2011-05-04
60%
0.8%
Actual IDB: USD 247,214
?%
Notes: 60% of time has passed since project start, but hardly anything of the scope and cost have been realized.

## Slide 9: Triple Constraint to go
Start: May 2011 Finish: 8 April 2013
Time
Cost
USD 29,752,786
Time is running out!
Scope / Results
Neighborhood Upgrading (12 Periurban neighborhood + 2 inner-city neighborhood improvement projects + 4 Community Participation Comm)
Affordable Housing (320 housing units, (400 subsidies for new houses and 600 subsidies for incremental home construction)
Institutional Strengthening (BSS, SSS, LIS)
Notes: Almost all of the scope and budget is still to be realized, but there is only two more years to go. Time is running out. Given the magnitude of scope, complexity of the project and weak track record of achieving results in a timely manner, the triple constraint to go is not considered achievable.

## Slide 10: Observations / 2
Issues resolution, decisions and approvals take too long
Not all elements of scope appear to be clear / defined
Insufficient Project Management practices
  Manage project constraints: Scope, Time, Cost, Resources, Risks and Quality
  Manage Schedule (AOP)
  Manage Issues
  Manage Communication
Imbalance between Scope-Cost and Resources-Time
Human Resources constraints impacting project progress
Notes: Issues resolution, decisions and approvals take too long
  Probably also due to the fact that information is not well prepared by the Project Team.
  Example includes the issue Eckstein village (see issues log). PS was supposed to discuss and resolve this issue in a special government committee meeting on Friday May 13th, but due to other topics this item was not discussed. It is unclear when it will be discussed and resolved. Other items in the issue log are also examples related to this observation.
Not all scope elements are clear and/or defined
  e.g. Construction Fund (Eckstein village, alternative solution is not defined), Allen View (fracture in Cave, no back-up solution defined), Quality Surveyor (unclear what is in the scope of this contract and what the payment schedule will be), Supervisor (same as Quality Surveyor)
Insufficient Project Management Practices
Manage project constraints (see Triple Constraint). Project Management Team (PS, PM and PO’s) is not managing the triple constraint.
Manage Schedule: AOP is not regularly updated. Activities are not completed in the AOP, resources are not assigned, activities are not proactively monitored, activities are not completed on time.
Example: Geotechnical Survey (confirmed April 11-12. May 11-12 ToR still to be written)
Manage Communication: No regular project team meetings, no regular Steering Committee meetings. Information is not communicated well. Visit if Operations Support Contractor was not communicated to every team members, visit of IDB counselors (May 12th) came as a surprise to PM and PO’s and took a lot of (unscheduled) time.
Imbalance between Scope-Cost and Resources-Time (see Triple Constraint)
Human Resources constraints impacting project progress
Insufficient sponsorship from PS. PS does not resolve major issues (see issues log) and changes.
Project Management Team members (PS, PM, PO’s) appear to have limited Project Management capabilities and experience in this type of project among.
Due to resource constraints in component 2, other team members have to help out which causes other activities to be delayed.
Social Investigator still not hired to support Component 2 subsidies

## Slide 11: Recommendations
May 2011

## Slide 12: Recommendations
Project Management Practices
Align Scope and Cost within Time and Resources constraints
Implement sound project management practices
  Schedule/Time management: Proactively manage the schedule, ensure work is assigned and completed on time and within budget. Check at the start of each week who needs to do what, give assigned resources a heads up and ask when the task will be completed. Check-in halfway through the scheduled duration.
  Issue management: Proactively identify, track, manage and resolve project issues. Use issues log.
  (scope) change management: Proactively manage scope to ensure that only what was agreed to is delivered, unless changes are approved through a scope management process.
  Communication management: Proactively communicate project information to all stakeholders. Hold weekly Project Team meetings and monthly Steering Committee meetings.
Notes: Align Scope and Cost within Time and Resources constraints
Given the project environmental factors (e.g. government policies and procedures) it is unlikely resources constraints can be resolved and significantly increased. Therefore the only option is to significantly reduce the scope of the project. Reduced scope and cost should be brought in line within resource and time constraints. See suggestion for triple constraint Phase 1a and Phase 1b.

## Slide 13: Recommendations
Project Organisation & Roles
Define decision making authority / tolerance level PM.
  Define what decisions PM can make and for which PM has to go to PS.
  Define and clarify role PS, PM and Component Project Officers
Consider assigning dedicated PO to component 3 so that PM can focus on overall coordination and issue resolution and have component project officers managing their respective components.
Appoint Social Investigator and Marketing Consultant to start immediately.
Notes: Project Organisation & Roles
Table of authorities and decision making level should be established similar to for example the one that exists within the IDB. This should clarify what level of authorization the PM has versus the PO’s and PS.
PM is currently distracted in many different directions trying to resolve issues. As a result Component 3 progress is not sufficiently monitored and managed. A dedicated PO who will proactively manage schedule, issues, scope and communication for component 3 would benefit progress.
Social Investigator and Marketing Consultant should be appointed immediately to ensure further progress in Component 2 subsidies.

## Slide 14: Recommendations
Financial Management / Procurement
ToR’s / Contracts should include payment details
Include contract (values) in finance / disbursement plan
Align finance / disbursement plan with Procurement Plan and AOP
Monthly update of the finance / disbursement plan
Procurement Plan should only include clearly defined activities
Notes: In order to ensure project finances are properly monitored and controlled the following measures should be taken:
Each ToR / Contract should include total value and payment details (% of payment and timing)
Include contracts (total values and payments) as a separate new line in Finance / Disbursement Plan / Forecast Tables
Finance / Disbursement Plan should be aligned with Procurement Plan and AOP. Each contract / procurement item should have a unique code and this code should be applied in all relevant document (e.g. Procurement Plan, Finance/Disbursement Plan and AOP)
Sr. Acct, PM, PO’s and Procurement Specialist to meet (at least) monthly to update the Finance / Disbursement / Procurement plans and AOP’s

## Slide 15: Align Scope and Cost within Time and Resources constraints to go Phase 1a
Start: May 2011 Finish: 8 April 2013
Time
Cost
IDB USD 13,600,000
GOB 1,800,000
Scope / Results
Neighborhood Upgrading (Garden Land, Phase 1 additional sites?)
Affordable Housing (400 subsidies for new houses and 800 subsidies for incremental home construction)
Institutional Strengthening (BSS, SSS, LIS?)
Project Management Support
Notes: Suggested Scope (to be verified and agreed)
NU (4.6 mio)
Garden Land (2.6 mio)
  Phase 1 additional sites (2,000,000)
AH (5 mio)
2.2 New Homes (2 mio)
2.3 IHC (3+1 mio)
IS (1.5 mio)
Prep, Supervision, Design (1.5 mio)
Program Admin (1.8 mio)
Total: 13.6 mio IDB, 1.8 mio GOB

## Slide 16: Align Scope and Cost within Time and Resources constraints to go Phase 1b
Start: 2013 Finish: 2015-16
Time
Cost
IDB USD 16,400,000
GOB 8,200,000
Scope / Results
Neighborhood Upgrading (Allen View, Phase 2 additional sites, Cats Castle, Greenfield)
Affordable Housing (Construction Fund)
Institutional Strengthening (Project Management Practices)
Notes: To be verified

## Slide 17: Deliverables
Disbursement Projection Tables
Codes introduced and assigned
Actuals updated
GL (1.1.1), Subsidies (2.2 & 2.3) and some Institutional Strengthening further specified and planned.
Not all scope elements could be realistically planned because the scope of work and/or approach is not clear in all cases
  1.1.2 AV, 1.1.3 & 4 10 add. sites
  1.2.1 CC, 1.2.2 Gf, 1.3 CPC
  2.1 Construction Fund / EV
  3.3 Land Information System
  4.3.3 Quality Surveyor
  4.3.4 Supervision Services
  4.3.5 Land Surveying Services
Annual Operations Plan
Codes introduced and assigned
Subcomponents and activities aligned with Disbursement Projection Tables and Procurement Plan
% complete introduced and updated
Resource names introduced and assigned
Resource View and Reports introduced

## Slide 18: Action Plan

## Slide 19: Action Plan, Activities and Visits
Action plan to follow
  List, document and resolve issues
  Review and update AOP on a weekly basis
  Weekly team meetings to agree and set priorities for the week
  Align scope and cost with time and resources
  Further alignment between Procurement Plan and Financial Plan (Disbursement Plan) and Disbursement Projection Tables
  All contracts (values) to be reflected in Disbursement Projection Tables and AOP’s
  Monthly updates on Financial Plan 4b Cash Flow projections
  Clarify roles PS, PM, PO’s
Calendar of activities
  Weekly (virtual) coaching session 1 hour, topics to be determined by Project Team
Subsequent visits
  Jun 6–10 or 13–17
  Aug 29–Sept 2 or Sept 5–9
  Oct 3–7 or 10–14
  Nov 7–11 or 14–18
  Dec 5–9 or 12–16

## Slide 20: Sample Week
Monday: 9-10am Project Team Meeting
  Focus on activities / priorities this week
    PO’s should have updated their schedules (AOP)
  Update on issues
  What to communicate to who this week
Wednesday: Update Finance Plan / Disbursement Forecast (Sr. Acct, PM, PO’s, Proc. Specialist)
Thursday (once a month): Steering Committee meeting