## Introduction
Impact Evaluation Work Calendar Model
This Excel file presents two examples of work calendars or Gantt charts for an impact evaluation. Both calendars have the same duration of activities but in the summarized version some activities have been combined.
The activities list brings together the essential activities for performing an impact evaluation, and in any case, depending on the particular evaluation, other activities should be added or removed from the existing list.
Similarly, the times assigned to each activity should be adjusted. Special care has been taken in these models with respect to the duration and order of the activities, such that each component is in agreement with the best practices for performing these surveys. Surely for some users some of the activities might seem to be excessively long, but we recommend that you conduct a detailed analysis before making any modifications so as not to underestimate the duration of any activity, which can be especially problematic when the work calendar represents contractual commitments.
It is recommended that the work calendars be detailed, ideally containing tangible product checkpoints, for example, "Databases verified"; "Baseline report"; "Evaluation report"; etc.
Finally, evaluating the possible risks that could prevent the activities from developing as stipulated in the calendar is suggested in order to improve the estimations and/or take actions to mitigate these risks.

## Guide
Note for Adapting the Material
The activities list in these examples is common to all impact evaluations and surveys of this type, however, the need to add new activities or eliminate existing activities if they are not relevant should be considered. Note that greater detail about the activities and the inclusion of verifiable outputs facilitates follow up and monitoring of activity implementation.
These examples are presented in Excel, but the Gantt chart can evidently be developed with other tools such as MS Project. One important aspect that should be respected, independent of the tool used, is the order of activities. In the example, these are given by formulas that take the completion date of the activity that proceeds the event being scheduled into account. For example, the questionnaire must be finalized before carrying out the training.
The duration of the activities presented is only a guide, however, these examples use the minimum amount of time reasonably needed to develop impact evaluations that use survey instruments like those included in this portal.
The total duration of surveying in the field is conditional on the total number of sampling points, the number of surveys to be performed at each sampling point, and the average estimated time to perform the surveys at each sampling point, in addition to the number of field teams deemed necessary. Keep in mind that the general recommendation suggests spending more time in the field with fewer teams than the contrary of less time and more teams. The former allows for better control of aspects of survey quality. However, keep in mind that these times should be consistent with the project's activities. Do not forget that, as the example impact evaluation Gantt chart shows, the baseline survey must be performed before the start of the project's interventions, which may make it necessary to shorten time in the field and thus increase the number of teams.
If you want to use Excel to construct your Gantt chart you can modify the examples presented, keeping in mind that you must manually modify the graphic representation of the activities calendar.

## Detailed_model
1 | MANAGEMENT, FINANCE, LOGISTICS, AND INSTITUTIONAL AGREEMENTS |  |  | Days | 2015 |  |  | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019
[5 empty] | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB
[5 empty] | 8 | 5 | 3 | 7 | 4 | 4 | 1 | 6 | 3 | 1 | 5 | 2 | 7 | 4 | 2 | 6 | 3 | 3 | 7 | 5 | 2 | 7 | 4 | 1 | 6 | 3 | 1 | 5 | 2 | 2 | 6 | 4 | 1 | 6 | 3 | 7 | 5 | 2 | 7 | 4 | 1
1.01 | Start of the impact evaluation project | 2015-10-08 | 2015-10-12 | 5
1.02 | Establishment of the technical evaluation team | 2015-10-08 | 2015-10-11 | 4
1.03 | Establishment of institutional agreements | 2015-10-15 | 2015-11-14 | 31
1.04 | Define technical assistance needs and opportunities | 2015-10-15 | 2015-10-26 | 12
1.05 | Contract consultants for the evaluation (companies/people/institutions) | 2015-10-15 | 2015-10-26 | 12
2 | DESIGN |  |  | Days | 2015 |  |  | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019
[5 empty] | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB
[5 empty] | 8 | 5 | 3 | 7 | 4 | 4 | 1 | 6 | 3 | 1 | 5 | 2 | 7 | 4 | 2 | 6 | 3 | 3 | 7 | 5 | 2 | 7 | 4 | 1 | 6 | 3 | 1 | 5 | 2 | 2 | 6 | 4 | 1 | 6 | 3 | 7 | 5 | 2 | 7 | 4 | 1
2.01 | Design of the impact evaluation | 2015-10-29 | 2015-11-23 | 26
2.02 | Determine the sample size | 2015-11-26 | 2015-11-30 | 5
2.03 | Establish the evaluation budget | 2015-12-03 | 2015-12-07 | 5
2.04 | Identify funding sources | 2015-12-10 | 2016-01-11 | 33
2.05 | Evaluation design report | 2015-12-10 | 2016-01-11 | 33
3 | BASELINE |  |  | Days | 2015 |  |  | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019
[5 empty] | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB
[5 empty] | 8 | 5 | 3 | 7 | 4 | 4 | 1 | 6 | 3 | 1 | 5 | 2 | 7 | 4 | 2 | 6 | 3 | 3 | 7 | 5 | 2 | 7 | 4 | 1 | 6 | 3 | 1 | 5 | 2 | 2 | 6 | 4 | 1 | 6 | 3 | 7 | 5 | 2 | 7 | 4 | 1
3.01 | Preparation for baseline data collection (questionnaires, strategies, etc.) | 2015-11-26 | 2016-01-25 | 61
3.02 | Develop ToR for baseline data collection firm | 2015-11-26 | 2016-01-25 | 61
3.03 | Contract data collection firm (the entire process) | 2016-01-14 | 2016-04-13 | 91
3.04 | Preparation of the survey | 2016-04-14 | 2016-09-14 | 154
3.05 | Field baseline survey | 2016-09-15 | 2017-02-12 | 151
3.06 | Analysis of baseline information | 2017-01-06 | 2017-03-21 | 75
3.07 | Baseline report | 2017-03-24 | 2017-04-04 | 12
3.08 | Release of baseline results | 2017-04-07 | 2017-04-18 | 12
3.09 | Confirmation of BL database to disseminate | 2017-01-06 | 2017-04-04 | 89
4 | INTERVENTION |  |  | Days | 2015 |  |  | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019
[5 empty] | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB
[5 empty] | 8 | 5 | 3 | 7 | 4 | 4 | 1 | 6 | 3 | 1 | 5 | 2 | 7 | 4 | 2 | 6 | 3 | 3 | 7 | 5 | 2 | 7 | 4 | 1 | 6 | 3 | 1 | 5 | 2 | 2 | 6 | 4 | 1 | 6 | 3 | 7 | 5 | 2 | 7 | 4 | 1
4.01 | Execution of the intervention program | 2017-03-24 | 2018-03-19 | 361
5 | IMPACT EVALUATION (IE) |  |  | Days | 2015 |  |  | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019
[5 empty] | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB
[5 empty] | 8 | 5 | 3 | 7 | 4 | 4 | 1 | 6 | 3 | 1 | 5 | 2 | 7 | 4 | 2 | 6 | 3 | 3 | 7 | 5 | 2 | 7 | 4 | 1 | 6 | 3 | 1 | 5 | 2 | 2 | 6 | 4 | 1 | 6 | 3 | 7 | 5 | 2 | 7 | 4 | 1
5.01 | Preparation of IE data collection | 2017-11-19 | 2017-12-21 | 33
5.02 | Contract IE survey data collection firm | 2018-01-04 | 2018-03-31 | 87
5.03 | IE survey | 2018-04-03 | 2018-11-11 | 223
5.04 | Impact analysis | 2018-10-12 | 2018-12-21 | 71
5.05 | Release workshop | 2019-01-11 | 2019-01-19 | 9
5.06 | Development of IE report | 2018-12-24 | 2019-02-22 | 61
5.07 | Confirmation of IE database to disseminate | 2018-12-24 | 2019-02-22 | 61
6 | QUALITY ASSURANCE |  |  | Days | 2015 |  |  | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019
[5 empty] | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB
[5 empty] | 8 | 5 | 3 | 7 | 4 | 4 | 1 | 6 | 3 | 1 | 5 | 2 | 7 | 4 | 2 | 6 | 3 | 3 | 7 | 5 | 2 | 7 | 4 | 1 | 6 | 3 | 1 | 5 | 2 | 2 | 6 | 4 | 1 | 6 | 3 | 7 | 5 | 2 | 7 | 4 | 1
6.01 | Review of baseline ToR | 2015-01-03 | 2015-01-17 | 15
6.02 | Review of baseline (BL) materials | 2016-04-14 | 2016-09-14 | 154
6.03 | Supervision, training, and selection of BL staff | 2016-07-14 | 2016-08-29 | 47
6.04 | BL field supervision | 2016-09-15 | 2017-02-12 | 151
6.05 | Remote supervision of the quality of BL data collected | 2016-09-15 | 2017-02-12 | 151
6.06 | Quality control of the BL consolidated database | 2017-02-05 | 2017-02-19 | 15
6.07 | Review of evaluation survey (ES) ToR | 2017-11-19 | 2017-12-21 | 33
6.08 | Review of EE materials | 2018-04-03 | 2018-07-02 | 91
6.09 | Supervision, training, and selection of EE staff | 2018-06-02 | 2018-07-17 | 46
6.1 | EE field supervision | 2018-07-20 | 2018-11-11 | 115
6.11 | Remote supervision of the quality of EE data collected | 2018-07-20 | 2018-11-11 | 115
6.12 | Quality control of the EE consolidated database | 2018-11-14 | 2018-11-21 | 8

## Summarized_model
1 | MANAGEMENT, FINANCE, LOGISTICS, AND INSTITUTIONAL AGREEMENTS |  |  | Days | 2015 |  |  | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019
[5 empty] | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB
[5 empty] | 8 | 5 | 3 | 7 | 4 | 4 | 1 | 6 | 3 | 1 | 5 | 2 | 7 | 4 | 2 | 6 | 3 | 3 | 7 | 5 | 2 | 7 | 4 | 1 | 6 | 3 | 1 | 5 | 2 | 2 | 6 | 4 | 1 | 6 | 3 | 7 | 5 | 2 | 7 | 4 | 1
1.01 | Start of the impact evaluation project | 2015-10-08 | 2015-10-12 | 5
1.02 | Establishment of the technical evaluation team | 2015-10-08 | 2015-10-11 | 4
1.03 | Establishment of institutional agreements | 2015-10-15 | 2015-11-14 | 31
1.04 | Define technical assistance needs and opportunities | 2015-10-15 | 2015-10-26 | 12
2 | DESIGN |  |  | Days | 2015 |  |  | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019
[5 empty] | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | OCT
[5 empty] | 8 | 5 | 3 | 7 | 4 | 4 | 1 | 6 | 3 | 1 | 5 | 2 | 7 | 4 | 2 | 6 | 3 | 3 | 7 | 5 | 2 | 7 | 4 | 1 | 6 | 3 | 1 | 5 | 2 | 2 | 6 | 4 | 1 | 6 | 3 | 7 | 5 | 2 | 7 | 4 | 1
2.01 | Design of the impact evaluation | 2015-10-29 | 2015-11-23 | 26
2.02 | Determine the sample size | 2015-11-26 | 2015-11-30 | 5
2.03 | Establish the evaluation budget | 2015-12-03 | 2015-12-07 | 5
2.04 | Identify funding sources | 2015-12-10 | 2016-01-11 | 33
3 | BASELINE |  |  | Days | 2015 |  |  | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019
[5 empty] | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | OCT
[5 empty] | 8 | 5 | 3 | 7 | 4 | 4 | 1 | 6 | 3 | 1 | 5 | 2 | 7 | 4 | 2 | 6 | 3 | 3 | 7 | 5 | 2 | 7 | 4 | 1 | 6 | 3 | 1 | 5 | 2 | 2 | 6 | 4 | 1 | 6 | 3 | 7 | 5 | 2 | 7 | 4 | 1
3.01 | Preparation for baseline data collection (questionnaires, strategies, etc.) | 2015-11-26 | 2016-01-25 | 61
3.02 | Contract data collection firm (the entire process) | 2016-01-14 | 2016-04-13 | 91
3.03 | Preparation of the survey | 2016-04-14 | 2016-09-14 | 154
3.04 | Baseline survey | 2016-09-15 | 2017-02-12 | 151
3.05 | Analysis of baseline information | 2017-01-06 | 2017-03-21 | 75
3.06 | Baseline report | 2017-03-24 | 2017-04-04 | 12
3.07 | Release of baseline results | 2017-04-07 | 2017-04-18 | 12
4 | INTERVENTION |  |  | Days | 2015 |  |  | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019
[5 empty] | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | OCT
[5 empty] | 8 | 5 | 3 | 7 | 4 | 4 | 1 | 6 | 3 | 1 | 5 | 2 | 7 | 4 | 2 | 6 | 3 | 3 | 7 | 5 | 2 | 7 | 4 | 1 | 6 | 3 | 1 | 5 | 2 | 2 | 6 | 4 | 1 | 6 | 3 | 7 | 5 | 2 | 7 | 4 | 1
4.01 | Execution of the intervention program | 2017-03-24 | 2018-03-19 | 361
5 | IMPACT EVALUATION |  |  | Days | 2015 |  |  | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019
[5 empty] | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | OCT
[5 empty] | 8 | 5 | 3 | 7 | 4 | 4 | 1 | 6 | 3 | 1 | 5 | 2 | 7 | 4 | 2 | 6 | 3 | 3 | 7 | 5 | 2 | 7 | 4 | 1 | 6 | 3 | 1 | 5 | 2 | 2 | 6 | 4 | 1 | 6 | 3 | 7 | 5 | 2 | 7 | 4 | 1
5.01 | Prepare for follow up data collection | 2017-11-19 | 2017-12-21 | 33
5.02 | Contract follow up data collection firm | 2018-01-04 | 2018-03-31 | 87
5.03 | Follow up survey | 2018-04-03 | 2018-11-11 | 223
5.04 | Impact analysis | 2018-10-19 | 2019-01-02 | 76
5.05 | Release workshop | 2019-01-05 | 2019-01-13 | 9
5.06 | Development of reports | 2019-01-05 | 2019-03-06 | 61
6 | QUALITY ASSURANCE |  |  | Days | 2015 |  |  | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019
[5 empty] | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | OCT
[5 empty] | 8 | 5 | 3 | 7 | 4 | 4 | 1 | 6 | 3 | 1 | 5 | 2 | 7 | 4 | 2 | 6 | 3 | 3 | 7 | 5 | 2 | 7 | 4 | 1 | 6 | 3 | 1 | 5 | 2 | 2 | 6 | 4 | 1 | 6 | 3 | 7 | 5 | 2 | 7 | 4 | 1
6.01 | Baseline quality assurance | 2016-01-02 | 2017-02-19 | 415
6.02 | Evaluation survey quality assurance | 2017-11-19 | 2018-11-18 | 365