## Sheet1
SECTION 3
PROCUREMENT PLAN
FROM October/2014 to September/2015
Ref. No. 1 | Reference to SEPA code | Comp. No. | Description of and Component of procurement contract | Indicative cost (USD 000) | Procurement Selection method 2 | Review (ex-ante or ex-post) | Source of financing and percentage |  | Prequalification (YES/NO) | Estimated Dates |  | Actual dates |  | Status 4 (pending; in process; awarded; cancelled) | Comments
[7 empty] | IDB % | Local/ Other % |  | Publication of specific procurement notice | Completion of Contract | Publication of specific procurement notice | Completion of Contract
1 |  | 1 | GOODS
| E-GOV-40-LPI-S | 1.1 | Ministry of Legal Affairs - Shelving for the Vault of the Registrar General's Department | 3312 | ICB | ex-ante | 100 |  | No | 2013-01-21 | 2015-01-30 | 2013-08-29 |  | Awarded
| E-GOV-51-AD-B | 1.2 | Upgraded to Hansard reporting for Parliament - Software | 195 | SSS | ex-ante | 100 |  | No | 2013-05-20 | 2015-01-30 |  |  | Awarded
| E-GOV-45-LPI-S | 1.3 | Ministry of Housing Land and Marine Affairs - Procurement of Unmanned Aerial Vehicles Mapping Systems for Lands and Surveys Division | 1714 | ICB | ex-ante | 100 |  | No | 2013-05-20 | 2015-05-01 | 2013-08-26 |  | Awarded
| E-GOV-58-LPI-S | 1.4 | Ministry of National Security - Development and Installation of an Enterprise Geographic Information System - Broadband Solution / Metro ethernet | 523 | ICB | ex-ante | 100 |  | No | 2013-05-20 | 2015-06-18 | 2013-07-29 |  | Awarded
| E-GOV-59-LPI-S | 1.5 | Ministry of National Security - Development and Installation of an Enterprise Geographic Information System - Networking | 1086 | ICB | ex-ante | 100 |  | No | 2013-05-20 | 2015-02-28 | 2013-08-06 |  | Awarded
3 |  | 3 | NON-CONSULTING SERVICES
| E-GOV-36-CD-CF | 3.1 | MOF- Gentax Upgrade And Electronic Services For The Inland Revenue Division, Ministry Of Finance | 4498 | SSS | ex-ante | 100 |  | No | 2012-10-01 | 2015-09-01 | 2012-10-01 |  | Awarded
| E-GOV-49-SBCC-CF | 3.2 | Ministry of Housing, Land and Marine Affairs - Conduct of Aerial and Lidar Survey for Trinidad and Toabgo | 1033 | QCBS | ex-ante | 100 |  | Yes | 2013-06-15 | 2015-04-13 | 2013-09-12 |  | Awarded
| E-GOV-60-LPI-S | 3.3 | Ministry of National Security - Development and Installation of an Enterprise Geographic Information System - Geospacial Datasets | 924 | ICB | ex-ante | 100 |  | No | 2013-05-20 | 2015-02-28 | 2013-08-30 |  | Awarded
| E-GOV-57-LPI-S | 3.4 | Ministry of National Security - Development and Installation of an Enterprise Geographic Information System - GIS Software | 1028 | ICB | ex-ante | 100 | 0 | No | 2013-05-20 | 2015-06-30 | 2013-07-15 |  | In process
| E-GOV-48-SBCC-CF | 3.5 | Ministry of Housing Land and Marine Affairs -Upgrade of Cadastral Management Information System for Lands and Surveys Division | 3559 | ICB | ex-ante | 100 |  | No | 2013-05-20 | 2016-03-12 | 2013-08-23 |  | Awarded
| E-GOV-19-SBCC-CF | 3.6 | Procurement of Consultancy Services to Assist with the Design of an Electronic Document Management System for the Service Commission Department | 264 | QBS | ex-ante | 0 | 100 | Yes | 2011-08-01 | 2014-02-01 | 2011-08-30 |  | Awarded
|  | 4 | CONSULTING SERVICES
4 |  |  | Programme Management
| E-GOV-24-SCC-CI | 4.1 | Financial Specialist | 96 | QCNI | ex-ante | 100 |  | No | n/a | 2014-12-11 | 2012-10-01 |  | Awarded
Knowledge Brokering
| E-GOV-27-SBC-CF | 4.2 | Elimination of the Congestion of A Backlog of Records at the National Archives Records Center at Chaguaramas. | 435 | QBS | ex-ante | 100 |  | Yes |  | 2014-12-15 | 2012-08-15 |  | Awarded
| E-GOV-55-SBCC-CF | 4.3 | MPA SHRM - Human Resource System Modernization | 2523 | QCBS | ex-ante | 100 |  | No | 2012-11-01 | 2016-03-31 | 2012-11-13 |  | Awarded
| E-GOV-17-SBCC-CF | 4.4 | MPA - Provision Of Business Process Management Support In The Public Service | 462 | QBS | ex-ante | 100 |  | No | 2012-12-10 | 2012-07-01 | 2013-02-13 |  | Awarded
| E-GOV-29-SBCC-CF | 4.5 | MFE - Change Management and Project Management for Electronic Services Project, Board of Inland Revenue | 406 | QCBS | ex-ante | 0 | 100 | No | 2013-05-20 | 2015-12-30 | 2013-05-27 |  | In process
| E-GOV-30-SBCC-CF | 4.6 | Ministry of Health - Master Plans for POSGH , SFGH and EWMSC | 2619 | QCBS | ex-ante | 100 | 0 | No | 2012-12-01 | 2015-01-02 | 2013-05-02 |  | Awarded
| E-GOV-32-SBCC-CF | 4.7 | MPA -Institutional Strengthening of the Public Service Academy | 1023 | QCBS | ex-ante | 100 |  | No | 2013-06-03 | 2015-03-24 | 2013-07-15 |  | Awarded
| E-GOV-33-SBCC-CF | 4.8 | MPA - Envisioning and Planning for Enterprise wide Records and Information Management (RIM) System | 184 | QCBS | ex-ante | 0 | 100 | No | 2013-06-24 | 2014-06-10 | 2013-08-02 |  | In process
| E-GOV-61-CD-CI | 4.9 | MFE - Financial management Reform Coordinator | 195 | QCII | ex-ante | 100 |  | No. | 2013-09-20 | 2015-01-12 | 2013-07-26 |  | Awarded
| E-GOV-62-SCC-CI | 4.1 | MPSD - Updating of the Sample design and Sample Frame of the Continuous Sample Survey of Population (CSSP) | 67 | QCNI | ex-ante | 0 | 100 | No. | 2013-09-20 | 2015-02-20 | 2013-07-24 |  | Awarded
|  |  | Ministry of Planning and Sustainable Development - Eurotrace Programmer | 51 | QCNI | ex-ante | 100 | 0 | No |  |  |  |  | Awarded
|  | 5 | Audit
| E-GOV-53-SBMC-CF | 5.1 | MPA - Consulting Firm to audit eGKBF for 2 yrs | 48 | QCBS | ex-ante | 100 |  | No |  | 2014-01-31 | 2013-10-29 |  | Awarded
1 If there are a number of similar individual contracts to be executed in different places or at different times, these can be grouped together under a single heading, with an explanation in the comments column, indicating the average individual amount and the period during which the contracts would be executed. For example: an education project that includes school construction might include an item labeled “School Construction” for an estimated cost of US$20 million and an explanation under the Comments column such as this: “This item encompasses some 200 contracts for school construction averaging US$100,000 each, to be awarded individually by the participating municipal governments over a three-year period between January 2006 and December 2008.”
2 Goods and Works: ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; Consulting Firms: QCBS: Quality- and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection; Individual Consultants: QCNI: Selection based on comparison of qualifications of national individual consultants; QCII: Selection based on comparison of qualifications of international individual consultants.
3 Applicable only to Goods and Works in case the new Policies apply. In the case of previous Policies, it is applicable to Goods, Works and Consulting Services.
4 Column “Status” will be used for retroactive procurement and when updating the procurement plan.
Codes from SEPA
Formulas:
Actual dates = [Estimated Dates]
Note on F64: Test: QCBS