ANEXO ÚNICO

Social Effects of Conflict in Colombia on Indigenous, Afroecuadorian and Campesino Populations in Ecuador

TC -Plan of Operations

- Basic Project Data

| Project name: | Social Effects of Conflict in Colombia on Indigenous, Afroecuadorian and Campesino Populations in Ecuador |  |  |
| --- | --- | --- | --- |
| Project number: | EC- T1002 |  |  |
| Project team: | Kristyna Bishop (RE3/SO3), team leader; Amanda Glassman (RE3/SO3); Baudoin Duquesne (COF/CEC); Kevin McTigue (LEG) and Alexandra Ortega (RE3/SO3) who assisted in the preparation of this document. |  |  |
| Executing agency: | Programa Andino de Derechos Humanos (PADH) – Universidad Andina Simon Bolivar. |  |  |
| Beneficiaries: | Ministry of Foreign Relations, Social Sector Ministries and civil society institutions working with displaced populations in Ecuador. |  |  |
| Financing plan: | IDB (FSO): Local: Total: | US$ US$ US$ | 149, 950 15,000 164, 950 |

- Background and Problem Statement

  - The effects of the armed conflict in Colombia on the civilian population in Colombia and neighboring countries are substantial.  According to a Colombian NGO, Consultancy for Human Rights and Displacement (CODHES), 2.9 million Colombians have been internally displaced since 1985 by the conflict and the UNHCR has stated that Colombia can be listed just behind Angola, Burundi and Sudan in terms of the magnitude of the refugee situation.

  - Many displaced Colombians are fleeing over the borders into Panama, Venezuela and Ecuador. At present, Ecuador receives the highest number of Colombian asylum seekers and refugees at the regional level. Between January 2000 and March 2004, the total number of asylum seekers was estimated to be 23,584. However, these are official numbers; many asylum seekers and refugees do not register with the Ecuadorian authorities so the actual numbers could be much higher.

  - While the Government of Ecuador has attempted to increase security along Ecuador’s 370 mile (600 kilometer) border with Colombia, historic trading and kinship relationships have made it relatively easy for many asylum seekers and refugees from Colombia to find places to live and assistance in establishing a permanent life in Ecuador. The increasing number of asylum seekers and refugees from Colombia is changing the demographic composition of the border areas and straining the provision of already scarce social services which has long term consequences and implications for the health, culture and education of the Indigenous, Afroecuadorian and campesino communities that live in northeastern Ecuador.

  - Small cities and rural communities in northeastern Ecuador are being affected by the flow of asylum seekers and refugees as a result of the conflict in Colombia.  Some have been transformed from quiet rural towns to large urban centers. One example is Lago Agrio which has the country’s highest population growth, at 7.5%, and which is located only 14 miles (22 kilometers) from the Colombian border.  Lago Agrio now has several cantinas, bordellos and health facilities that cater almost exclusively to Colombian guerillas and paramilitary fighters who cross the border posing as refugees.  Heavy commercial activity in the otherwise poverty-stricken town has resulted in allegations that Lago Agrio is an important source of essential supplies for the various factions in the conflict.  In the last few years, murder rates and the rates of kidnappings, extortion, and carjackings, previously unknown in these areas, have all increased. Evidence is emerging from residents of these areas that some local residents have been forced to move to other areas or have voluntarily relocated their families in order to escape the violence.

  - Much attention has been given to the situation of the Colombian asylum seekers and refugees by international and multilateral organizations, but very little information is currently available regarding how the influx of Colombians and the transformation of rural communities is impacting the Indigenous, Afroecuadorian and campesino communities in northeastern Ecuador. This information is essential for future social and development planning in these regions and in Ecuador in general.

- Project Objectives and Description

  - The main goal of this project is to assist the Social Sector Ministries within the Government of Ecuador to respond to the social and economic impacts of changes in demographic composition, increasing violence and lack of social services for the Indigenous, Afroecuadorian and campesino communities in northeastern Ecuador as a result of the conflict in Colombia.

  - In order to achieve this goal, this technical cooperation has the following specific objectives:  (i) to gather information and analyze the social effects of internal population displacement in northeastern Ecuador and the State’s efforts to respond to these effects; (ii) to increase public awareness by disseminating this information to relevant agencies, government ministries and donors; and (iii) to prepare an action plan based on these assessments which will serve as an input for future Bank operations.

  - The purpose of Component (1) is to provide a comprehensive analysis of the current situation in northeastern Ecuador, including an assessment of the magnitude of internal displacement, reasons for displacement and settlement patterns of Indigenous, Afroecuadorian and campesino communities and the effect of internal displacement on the health, culture and education of the affected local communities.  The development of an information gathering methodology and training in its use as well as the convening of several focus groups in the affected areas will be financed in order to provide accurate, up-to-date information and to establish a baseline for social indicators which will be important intermediate results of this operation.  A combination of local community facilitators, community members, Indigenous organizations and human rights practitioners associated with PADH and the Universidad Andina Simon Bolivar will use the methodology developed as part of this project to gather information pertaining to social and economic statistics, poverty indicators and gender issues.

  - Component (2) activities include the dissemination of the results of Component (1) to communities, government ministries and collaborating institutions through:  (i) two published academic and occasional papers (separate topics); (ii) a final report that provides an analysis of the situation and includes the methodology for information gathering and highlights obstacles or issues that arose during investigation; (iii) a public symposium to be held at the Universidad Andina Simon Bolivar in Quito; and (iv) an action plan that includes recommendations for future projects.

- Cost and Financing

| Budget (in US$) |  |  |
| --- | --- | --- |
| Activity | Cost |  |
|  | IDB | LOCAL |
| Component (1) :Investigation and Analysis | 125,000 | 0 |
| Component (2): Dissemination of results | 19,950 | 0 |
| Project administration |  | 15,000 |
| Independent audit | 5,000 |  |
| Total | 149,950 | 15,000 |

  - The total cost of the operation is estimated to be $164,950 of which $149,950 will be drawn from the net income of the Bank’s Fund for Special Operations and the remaining $15,000 will be provided by the Universidad Andina Simon Bolivar in kind.

- Executing Agency and Execution Structure

  - This project will be executed by the Programa Andino de Derechos Humanos (PADH) at the Universidad Andina Simón Bolivar in Quito in collaboration with the Ministry of Foreign Relations.  The Universidad Andina Simón Bolívar – Programa Andino de Derechos Humanos is particularly well placed to carry out this study.  It is a graduate study program focused on promoting and protecting human rights and democracy in the Andean region and has a long history of participatory analysis and research on related issues. In the last two years, the Programa Andino has included the impact of human migration and internal displacement on the security and protection of fundamental human rights among their priority issues for research and has held several international conferences on the subject.

  - The Executing Agency will be responsible for all technical and administrative project execution, including but not limited to: a) preparing and submitting disbursement requests to the Bank, as well as the corresponding justification of expenditures; b) maintaining adequate financial, accounting and internal control systems that allow for the identification of the sources and uses of project funds, provides documentation to verify transactions, and permits the timely preparation of financial statements and other financial reports; c) preparing and submitting periodic financial and accounting reports to the Bank; and d) maintaining an adequate disbursement and contracting supporting documentation filing system for eligible expenditures. The executing agency will prepare and submit to the Bank the project’s final financial statements, within ninety (90) days after the date of last disbursement of the project.

  - The execution period will be 12 months, with 18 months allowed for disbursement.  Technical supervision for this project will rest with RE3/SO3. Administrative and disbursement supervision will rest with COF/CEC.

- Major Issues

  - Given the characteristics of the displaced population, high response rates and accurate responses will be a challenge for the executing agency.  Increasing militarization and cross border incursions by Colombian paramilitary groups represent additional safety and security risks for the executing agency.  These risks will be mitigated by the involvement of local communities through their representative organizations that have experience working in these areas and a strong presence on the ground.

- Action Plan

  - The Universidad Andino Simón Bolívar – Programa Andino de Derechos Humanos is ready to begin execution immediately. The Director of the Program, Sr. Roque Espinosa, will supervise the development of the methodology and project administration.

- Environmental and Social Strategy

  - This project will be undertaken in an area that is already somewhat unstable (see Section V) so issues regarding the safety and security of both the interviewers and the informants will be extremely important. As discussed above, these issues will be mitigated by the involvement of local Indigenous, campesino and Afroecuadorian organizations in both the design and execution of the survey and focus groups that will form the basis of the field work to be carried out under this project. In addition to avoiding negative social impact, this partnership will also ensure that the information gathered under the project will treated with respect and that essential dialogue among the key players is encouraged. No negative environmental impacts are anticipated.

http://www.usip.org/pubs/specialreports/sr114.html.

Source: United Nations High Commission for Refugees (2004).