## Sheet1
MINISTRY OF EDUCATION
PROGRAMME AND PROJECTS PLANNING AND MANAGEMENT UNIT
SEAMLESS EDUCATION SYSTEM (SES) PROGRAMME - PROCUREMENT PLAN
FOR THE PERIOD JANUARY 2015 TO 17TH AUGUST, 2015
IDB LOAN FUNDING WILL BE USED TO FINANCE PROJECTS UP TO 17TH AUGUST, 2015
THEREAFTER, COUNTERPART FUNDING WILL BE UTILIZED UNTIL PROJECT COMPLETION
Ref. No. 1 | Reference to SEPA code | Comp. No. |  | Description of and Component of procurement contract | Indicative cost (USD) | Procurement Selection method 2 | Review (ex-ante or ex-post) | Source of financing and percentage |  | Prequalification 3 (YES/NO) | Estimated Dates |  | Actual dates |  | Status 4 (pending; in process; awarded; cancelled)
|  |  | Procurement Categories |  |  |  |  | IDB % | Local/Other % |  | Publication of specific procurement notice | Completion of Contract | Publication of specific procurement notice | Completion of Contract
1 | SES-62-SBCC-CF | 5 | Consulting Services | Technical Assistance for the conduct of a Final Evaluation of the Programme | 300000 | IICQ | ex-ante | 100% |  | EOI | 2015-02-15 | 2015-08-15 |  |  | In process
3 |  | 1 |  | Construction of 24 ECCE Centres | 21985226.88 | NCB | ex-ante | 100% |  |  |  |  | 2012-02-01 | 2014-12-01 | Awarded
4 |  | 1 |  | Supervision of 24 ECCE Centres | 2559885.265 | QCBS | ex-ante | 100% |  |  |  |  | 2011-07-01 | 2014-12-01 | Awarded
5 |  | 1 |  | Furniture & Outfitting of 24 ECCE Centres | 1456546.19 | NCB | ex-ante | 100% |  |  |  |  | 2012-05-01 | 2014-12-01 | Awarded
6 |  | 1 |  | ECCE Business Process | 309440.46 | ICB | ex-ante | 100% |  |  |  |  | 2013-06-01 | 2015-07-01 | Awarded
7 |  | 1 |  | Children Understanding | 2709860 | ICB | ex-ante | 100% |  |  |  |  | 2012-07-01 | 2015-01-01 | Awarded
8 |  | 1 |  | Upgrades of 16 Demo Schools- (ICAN Rooms) | 24923.19 | Direct Contracting BONDED Items | Ex-post | 100% |  |  |  |  | N/A | 2013-12-01 | Awarded
9 |  | 2 |  | The supply & delviery of 25 steel pan ensembles to primary shcools for the MOE | 473713.75 | NCB | ex-ante | 100% |  |  |  |  | 2013-05-01 | 2014-07-01 | Awarded
10 |  | 2 |  | Editing of the Teaching Guides, Curriculum guides and instructional toolkits for the Revised Primary School Curriculum | 16662.5 | NICQ | ex-ante | 100% |  |  |  |  | 2013-06-01 | 2013-08-01 | Awarded
11 |  | 2 |  | Printing and Distributing of Curriculum, Teachers Guides and Instructional Toolkits in print and CD formats to 589 Primary Schools and to Administrative offices of the MOE | 460132.92 | NCB | ex-ante | 100% |  |  |  |  | 2013-07-01 | 2014-01-01 | Awarded
12 |  | 2 |  | Curriculum writers stipend | 275400 |  |  | 100% |  |  |  |  | N/A | 2014-12-01 | Awarded
13 |  | 2 |  | Supply of a 5 year Maintenance Agreement for the servicing of 118 Schools for the Ministry of Education | 1015324.83 | NCB | ex-ante | 20% | 80% |  |  |  | 2013-05-01 | 2019-08-30 | Awarded
14 |  | 2 |  | Literacy and Numeracy Coaches | 920000 | Direct Contracting | ex-ante | 100% |  | No |  | 2014-12-31 | N/A | 2015-08-01 | Awarded
15 |  | 2 |  | Recruitment of 147 Monitors for the MOE Pupils | 2499000 | Direct Contracting | ex-ante | 100% |  | No |  | 2014-12-31 | N/A | 2015-08-01 | Awarded
16 |  | 2 |  | 65 iPad cases for use in Baseline consultancy survey | 3336.67 | Local Shopping | Ex-post | 100% |  |  |  |  | N/A | 2012-09-01 | Awarded
17 |  | 2 |  | Technical consultancy to evaluate the current system of examination, testing and assessment with a view to improving the reliability of results in line with the curriculum and the value outcomes identified. | 538446.8833 | ICB | ex-ante | 100% |  |  |  |  | 2013-01-01 | 2015-05-01 | Awarded
18 |  | 2 |  | Curriculum Implementation Materials | 4132372.96 | ICB | ex-ante | 100% |  | No |  | 2014-12-31 | N/A | 2015-04-01 | Awarded
19 |  | 2 |  | Various services, supplies etc for Impl. Revised Primary School Curriculum | 167068.57 | Local Shopping | Ex-post | 100% |  |  |  |  | N/A | 2014-09-01 | Awarded
20 |  | 3 |  | ICT Adviser to the MOE | 133333 | IICQ | ex-ante | 60% | 40% |  |  |  | 2013-06-01 | 2015-01-01 | Awarded
| SES-75-SBC-CF | 3 |  | Consultancy to Provide Organisation Development Consultancy | 26185.56 | Direct Contracting | ex-ante | 100% |  |  |  |  | N/A | 2013-06-01 | Awarded
21 |  | 3 |  | Consultancy to Provide Technical Advisory Support | 47966 | Direct Contracting | ex-ante | 100% |  |  |  |  | N/A | 2013-02-01 | Awarded
22 |  | 3 |  | Supply/Printing and delivery of 39,678 survey questionnaires | 62688 | Local Shopping | ex-ante | 100% |  |  |  |  | N/A | 2013-09-01 | Awarded
23 |  | 3 |  | Physical Security and Assessment | 293008 | QBS | ex-ante | 66% | 33% | No |  | 2014-12-31 | 2013-06-01 | 2015-01-01 | Awarded
24 |  | 3 |  | Recruitment of a 3-man team for Consolidation of Circulars | 42255 | Direct Contracting | Ex-ante | 100% |  |  |  |  | N/A | 2013-06-01 | Awarded
25 |  | 3 |  | Recruitment of a 3-man team for Training in the Implementation of Circulars | 65000 | Direct Contracting | Ex-ante | 100% |  |  |  |  | N/A | 2014-09-01 | Awarded
26 |  | 3 |  | Resources for the administration of the Circulars Implementation Consultancy | 14137.58 | Local Shopping | ex-ante | 100% |  |  |  |  | N/A | 2014-09-01 | Awarded
27 |  | 3 |  | ECCE Construction and Partnering Development Consultancy | 60000 | Direct Contracting | ex-ante | 100% |  |  |  |  | N/A | 2014-11-01 | Awarded
28 |  | 3 |  | Staffing | 422510 | QCNI | ex-ante | 100% |  | No | 2014-01-14 | 2014-12-31 | N/A | 2015-03-13 | Awarded
29 |  | 3 |  | Various services for Consolidation of Circulars Consultancy Training | 10595.51 | Local Shopping | Ex-ante | 100% |  |  |  |  | N/A | 2014-09-01 | Awarded
30 | SES-63-SSF-CF | 5 |  | Annual Audit of SES Oct 2012 to Sept 2013 | 22836.73 | QBS | ex-ante | 100% |  | No |  | 2014-12-31 | 2012-11-01 | 2014-01-01 | Awarded
31 |  | 5 |  | Peachtree Consultancy | 2300 | Direct Contracting | Ex-ante | 100% |  |  |  |  | N/A | 2014-02-01 | Awarded
41050156.4483
-40892770.49
157385.9583
1 If there are a number of similar individual contracts to be executed in different places or at different times, these can be grouped together under a single heading, with an explanation in the comments column, indicating the average individual amount and the period during which the contracts would be executed. For example: an education project that includes school construction might include an item labelled “School Construction” for an estimated cost of US$20 million and an explanation under the Comments column such as this: “This item encompasses some 200 contracts for school construction averaging US$100,000 each, to be awarded individually by the participating municipal governments over a three-year period between January 2006 and December 2008.”
2 Goods and Works: ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; Consulting Firms: QCBS: Quality- and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection; Individual Consultants: QCNI: Selection based on comparison of qualifications of national individual consultants; QCII: Selection based on comparison of qualifications of international individual consultants.
3 Applicable only to Goods and Works in case the new Policies apply. In the case of previous Policies, it is applicable to Goods, Works and Consulting Services.
4 Column “Status” will be used for retroactive procurement and when updating the procurement plan.
Codes from SEPA

## Sheet2
1 | SES-71-LPI-O | 1 |  | Assessment and technical upgrade of 8 ECCE Centres and 8 Primary Schools into Demonstration Inclusive Centres and Schools. | 2231150 | NCB | ex-ante | 100% | No | 2014-11-01 | 2014-12-31 | 2014-11-30
2 |  | 2 |  | Recruitment of a firm to print numeracy/literacy manuals | 31000 | NCB | ex-ante | 100% | No | 2014-04-01 | 2014-12-31
3 |  | 2 |  | Independent Review of Curriculum Project | 200000 | QCBS | ex-ante | 100% | No | 2014-04-14 | 2014-12-31 | 2014-09-30
4 |  | 2 |  | Numeracy/Literacy Training | 280000 | QCNI | ex-ante | 100% | No | 2014-03-14 | 2014-12-31
7 |  | 2 |  | Purchase of teaching materials for Numeracy and Literacy project for all 477 Primary School | 800000 | NCB | ex-ante | 100% | No |  | 2014-12-31 | Feb 2014
9 |  | 2 |  | Purchase of camcorders for 477 primary schools | 300000 | NCB | ex-ante | 100% | No | 2014-04-14 | 2014-12-31
10 |  | 2 |  | Acquisition of a Classroom Collaborative Learning System for installation in 20 schools and 5 sites | 2000000 | ICB | ex-ante | 100% | No |  | 2014-12-31
12 |  | 3 |  | Design of a System of Standardization and Simplification which meets the requirements of Total Quality Management (TQM) | 100000 | QCBS | ex-ante | 1 | No | 2014-04-15 | 2014-12-31
13 |  | 3 |  | Strategic Integrated Information system plan SIISP | 323000 | QCBS | ex-ante | 1 | No | 2014-05-14 | 2014-12-31
14 | SES-53-SBCC-CF |  |  | School Supervision and School-based Management. | 400000 | QCBS | ex-ante | 100% | No | 2014-04-14 | 2014-12-31
15 | SES-57-SBCC-CF | 3 |  | ECCE Division Business Process Strengthening | 250000 | QBS | ex-ante | 100% | No |  | 2014-12-31 | Jun 2013
17 |  | 3 |  | Recruitment of an Individual Map-Based ECCE Demographic consultant. | 40000 | QCNI | ex-ante | 100% | No |  | 2014-12-31 | Mar 2014
18 |  | 3 |  | Programme and projects planning and management, leadership, governance and training | 532000 | QCBS | ex-ante | 100% | No | 2014-05-14 | 2014-12-31
19 |  | 3 |  | Longitudinal tracer study on child development | 250000 | QCBS | ex-ante | 100% | No | 2014-05-14 | 2014-12-31
20 |  | 3 |  | Recruitment of 6 Technical Assistants for component Divisions / Units. | 170000 | QCNI | ex-ante | 100% | No | 2014-04-14 | 2014-12-31
22 | SES-62-SBCC-CF | 5 | Consulting Services | Technical Assistance for the conduct of a Final Evaluation of the Programme | 500000 | QBS | ex-ante | 100% | EOI |  | 2014-12-31
24 |  |  |  | Project Administration
|  |  |  | Stationery / Materials/ Office Equipment | 100000 | Shopping | ex-ante | 100% | No | 2014-01-14 | 2014-12-31