LEGIII/JA-731781-06

## ANNEX

THE PROGRAM

Program to Strengthen Government of Jamaica’s Capacity to Manage for Results

I.	Objective

1.01	The Program seeks to strengthen results-based management in Jamaica by supporting the preparation of a medium term action plan to improve the performance, management, monitoring and evaluation capacity of the public sector. It will also include critical capacity building activities to disseminate Management for Results (MfR) concepts within the public sector and civil society, and to facilitate future implementation of the action plan.

II.	Description

2.01	In order to achieve the above aforementioned objectives, the Project will finance the following components:

Component 1: Preparation of the strategy and medium term action plan for

improving government’s management for results

  - The component will consist of activities directed to developing the strategy and medium term action plan to promote MfR in the Government of Jamaica (GOJ), and to facilitate consensus building around this. The main actions will include:

a.	Revision of the Ministry Paper 56 Public Sector Modernization Vision and

Strategy for 2002-2012. The review will focus on the preparation of a detailed action plan for three of its core thematic areas for MfR: (i) Resources management and accountability; (ii) performance management; and (iii) technology. The review will follow a participatory process to include relevant stakeholders, and will take into consideration the GOJ’s fiscal constraints for financing implementation of the reforms.

- Completion of the institutional and operational diagnostic work of Public Financial Management (PFM) and other systems related to MfR, including the analysis of the country’s capacity for ex-ante and ex-post evaluation of projects, and the quality and capacity of the statistical system as a whole. The diagnostic work will cover the analysis of the regulatory framework and applicable institutional arrangements, as well as the assessment of the technical and operational capacity of the public entities responsible for leading the systems. With regard to project evaluation capacity, the assessment should also include an analysis of current practices and the extent to which the conclusions of project appraisals are taken into consideration for the preparation of the government’s annual capital budget.

c.	Review and streamlining of the Government’s planning, prioritization and results monitoring mechanisms, including the Medium Term Social and Economic Policy Framework, the Capital Projects and Policy Prioritization System and the current Corporate Planning process. The review will focus on: (i) tools to strengthen the process in which priorities are set and decisions are made; (ii) the improvement of linkages between corporate planning and budgeting.

d. 	Preparation of technical proposals to support the action plan that will include the following: (i) the provision of guidance and analytical capacity to enhance parliamentary oversight; (ii) improving methodologies and instruments for implementation of results-based budgeting; (iii) completing the design of the strategy for the improvement of the public financial management systems (including procurement and oversight) following the recommendations of the joint Country Financial Accountability Assessment and Country Procurement Assessment Report (CFAA/CPAR); the design should include improved linkages between the financial management system, the procurement process and corporate planning; and (iv) the design of a strategy to enhance the institutional capacity of the leading public entities in the areas of planning, financial management, procurement and fiscal oversight.

e. 	Organization of consultations within the GOJ to discuss the content and the structure of the draft Action Plan, as well as workshops and seminars with other stakeholders, including parliament and civil society representatives.

# Component 2: Capacity building for management for results: institutional and

technical settings

2.03 	Under this component the program will support work in critical areas of public sector modernization and public financial management that will facilitate the implementation of the action plan once it is approved. The selected activities correspond to ongoing GOJ modernization efforts and are compatible with the recommendation of sector work studies performed by international organizations and bilateral donors. Some of these activities will be related to pilot experiences as a way of deriving lessons for implementation before the experiences are rolled out to other public entities.

2.04 	In order to facilitate project implementation and monitoring, activities will be organized into discrete modules with clearly identified units responsible for implementation. Core modules are: (i) completion of Public Financial Management Information System (FINMAN) pilots; (ii) Performance Management System in the Ministry of Transport and Works (MOTW); (iii) public audit; and (iv) procurement policy and procedures. Specific training activities for each of these modules will also be included in this component. In general, the activities of this component will include:

- Support the pilot program for the implementation of the financial management information system in the Ministry of Finance and Planning, and the Ministry of Transport and Works. At the conclusion of the pilots, the program will finance a technical evaluation.

- Support the completion of the pilot experience of MfR in the MOTW. This will include: (i) the establishment of a system to perform investment project monitoring and evaluation in the MOTW; and (ii) tools for monitoring and evaluating the overall performance of Executive Agencies in the sector.

- Support to the Auditor General’s Department in the preparation of a needs assessment for upgrading information technology (IT) and the design and initial implementation of a training program in IT audit and value for money auditing. It is expected that the training activities will benefit the Auditor General’s Department, the Internal Audit Directorate of the Ministry of Finance and Planning (MOFP) and the Internal Audit Unit of the MOTW.

d.	Revision of the regulatory framework and existing Procurement Handbook and development of Standard Bidding Documents in accordance with the recommendations of the joint CFAA/CPAR.

# Component 3: Training and dissemination in MfR

2.05 	Activities under this component will comprise of the following:

- A flexible training program in MfR organized in modules and focused on training for technical staff; individualized seminars for groups such as public sector executives, parliamentarians and civil society; internships; workshops on selected topics and cross cutting management systems. Training modules will consist of: (i) Basic training for GOJ official covering general concepts and core methods of MfR; (ii) specialized training in MfR for the staff of the leading entities (MOFP, Planning Institute of Jamaica –PIOJ-, Cabinet Office, MOTW, Auditor General’s Department –AGD-), and initial technical training in public procurement; and (iii) training for public sector executives, parliamentarians and civil society.

- Preparation of a training strategy for MfR to support the implementation of the Medium Term Action Plan. This strategy should identify opportunities to introduce MfR concepts to a broader audience, and explore the need for the inclusion or strengthening of specific courses in the University curriculum.

- Preparation of the strategy for dissemination of the action plan and GOJ’s results on plan implementation. The strategy will put emphasis on improving communications with and information to the public.

d.	Institutionalization and further expansion of the MfR training efforts by transferring the delivery of large-scale training courses and web-based training to the Management Institute for National Development (MIND).

III.	Total Cost of the Program

3.01	The estimated cost of the Program is the equivalent of five hundred thousand dollars (US$500,000), in accordance with the following Budget:

Budget

(in US$)

| ACTIVITIES | BANK | GOJ | TOTAL |
| --- | --- | --- | --- |
| - Action Plan and Strategy Revision of the Public Sector Modernization Vision and Strategy Completion of diagnostic work of PFM and other systems Review of GOJ’s planning, prioritization and results monitoring mechanisms Preparation of technical proposals to support the action plan for MfR Consultations (workshops and seminars) 2. Capacity Building Activities Ministry of Planning and Finance Financial Management: Pilots, Asset Mang., Training program design Procurement Ministry of Transport and Works Auditor General Department 3. Training in MfR Design and development of Basic training module Specialized training and internships Development of Training Strategy to support the MTAP Training for executives Strategy for dissemination of the Action Plan 4. Administration and Contingencies Task Manager Audit and Evaluation Other Administrative costs Contingencies | 128,000 16,000 24,000 36,000 32,000 20,000 176,000 134,000 100,000 34,000 42,000 0 78,000 30,000 20,000 10,000 10,000 8,000 68,000 45,000 13,000 5,000 5,000 | 4,000 4,000 36,000 4,000 4,000 32,000 0 10,000 10,000 | 132,000 16,000 24,000 40,000 32,000 20,000 212,000 138,000 104,000 34,000 42,000 32,000 78,000 30,000 20,000 10,000 10,000 8,000 78,000 45,000 13,000 5,000 15,000 |
| TOTAL | 450,000 | 50,000 | 500,000 |

##### IV.	Execution

  - The program execution period will be 18 months and the disbursement period will be 24 months. The program will be governed by a Steering Committee (SC) that will be responsible for overall project guidance and oversight, as well as for the approval and supervision of the work plans. The SC will review the progress reports and will interface with other institutional actors in order to facilitate the orderly implementation of the program. The SC will be comprised of the Deputy Financial Secretary of the MOFP (Public Expenditure Policy Coordination), the Director of External Cooperation of PIOJ, the Director of Planning of the MOTW, the Deputy Auditor General and the Head of the Public Sector Reform Unit of Cabinet Office (PSRU), who will act as chair of the SC. The SC will meet at least twice a year.

  - The program’s general coordination will be conducted by the PSRU, while the technical execution of the different activities will be undertaken by the GOJ’s leading entities in the MfR process as presented in the following table:

GOJ entities responsible for program execution

| Activity/ Area of Intervention | Entity Responsible |
| --- | --- |
| - Component 1 - Medium Term Action Plan for MfR - Component 2 o Module 1: FINMAN pilot implementation o Module 2: Performance Mgmt. Syst. MOTW o Module 3: Procurement o Module 4: Auditing - Component 3 o Training Program o Workshops and Seminars | - PSRU - MOFP - MOTW - MOFP - AGD - MOFP - PSRU - PSRU |

  - The technical work related to planning, preparation of terms of reference and/or specifications, selection of consultants and quality control of their work, and monitoring of the progress on implementation will be carried out by the respective responsible entity. The administrative support related to the preparation of bidding documents, contracting, purchasing and payments will be carried out by the PSRU.

4.04	As part of the general coordination activities, the PSRU will be responsible for: (i) coordinating program execution; (ii) revising and presenting the work plans, semiannual and final progress reports to the SC for approval and later submission to the Bank, in addition to other reports requested by the Bank during the program execution period; (iii) monitoring execution performance, and collecting the information needed for the indicators specified in the logical framework; (iv) conducting the procurement and processing the contracts required for program implementation; (v) providing technical advice to the agencies in charge of the execution of the program; (vi) preparing and presenting disbursements requests and justification of the use of funds to the Bank’s satisfaction, and the semiannual reports on the use of the revolving fund; (vii) maintaining the financial and accounting records related to the use of program resources, demonstrating at any time that the funds are used for the purpose intended; (viii) keeping adequate documentation to support the disbursements received; this information shall be made available for review by Bank personnel and/or external auditors; and (ix) preparing and presenting the financial statements of the program to the Bank, duly certified by eligible external auditors. The PSRU will appoint a technical coordinator for the program.

  - The program will be executed according to a detailed work plan containing: (i) the activities to be carried out and the targets to be achieved every six months; (ii) the expenditures to be made and the sources of financing; and (iii) the units responsible for compliance.

### MONITORING AND EVALUATION

5.01	The PSRU will submit to COF/CJA semiannual progress financial reports. The semiannual reports should discuss progress toward the achievement of the Semiannual Progress Indicators, which have been agreed between the GOJ authorities and the Bank’s team.

  - The GOJ and the Bank will hold semiannual meetings in order to review the progress achieved in implementing the Program. For this purpose, PSRU will furnish, prior to each meeting, information and documentation requested by the Bank regarding the advancement of the program.

5.03	A final evaluation financed with TC funds will also be conducted for project supervision and monitoring, based on the indicators and goals established in the logical framework. This evaluation will focus on: (i) verifying the degree of compliance with the indicators for the program and the different components; (ii) taking stock of the successes and shortcomings of program design and execution and its effectiveness in working toward the country’s development objectives; and (iii) recommending corrective or monitoring measures for future programs of this kind.