LEGIII/GY-511889-05

ANNEX

THE PROJECT

# Justice Modernization Project

I.	Objective

1.01	The overall objective of the Project is to provide technical assistance to the Government of Guyana in formulating a comprehensive program for the modernization of the justice administration system.

1.02	The specific objectives of the Project are: (a) to design a roadmap that would identify, classify and prioritize activities that could be financed by the Bank; and (b) to set up an office within the justice administration system capable of ensuring an orderly design and timely execution of the Justice Modernization Program.

II.	Description

2.01	In order to achieve the objectives mentioned in Section I above, the Project has the following components:

1. Design and approval of a roadmap for future action

2.02	International consulting services will provide technical assistance to relevant decision makers in order to help them design a roadmap that will guide the future justice modernization program. This will be carried out through a strategic planning exercise that will require permanent consultations with involved parties and the organization of several one-day workshops, as well as additional seminars to review -and later disseminate- the resulting strategies and action plans.

2.03	The strategic planning exercise will concentrate on the whole justice administration system; therefore, it will focus attention on organizing collective thought and action within an inter-organizational network in which no one person or institution is fully in charge. Time will need to be invested in organizing forums for discussions, involving diverse constituencies, negotiating agreements in existing or new arenas, and coordinating the activities and actions of numerous relatively independent people, groups, organizations and institutions.

2.04	The design of the roadmap will follow an orderly process in two main successive stages that are detailed in the Terms of Reference agreed between the Executing Agency and the Bank, and summarized as follows: during a first assessment stage, the consulting team will review and analyze all relevant information and enter into negotiation with all relevant parties in order to design a strategy addressing the most pressing issues faced by the justice administration system. Among the tasks implied in this stage are: (a) a review of all significant study reports of recent or ongoing international assistance already accumulated, as well as all relevant legislation; (b) broad yet effective information gathering in order to develop and explore strategic alternatives including: (i) a rapid review of the functions, organizational structure, staffing, management, relationships, and perceived strengths and weaknesses of each participating entity; (ii) an assessment of the system’s environment, identifying its strengths and weaknesses (including an analysis of available statistical information), as well as its opportunities and threats; and (iii) an analysis of stakeholders, considering persons, groups or organizations that can place a claim in the justice system’s attention, resources, or output; (c) technical guidance in negotiations among key internal decision makers in order to agree on the overall strategic planning effort and the key planning steps. This implies a previous identification of the key decision makers, and soon thereafter, the persons, groups, units or organizations that should be involved in the process. The agreement should cover: (i) the purpose of the effort; (ii) the preferred steps for the process; (iii) the role and functions of any participating group; and (iv) the commitment of resources necessary to proceed with the effort; and (d) identification of the strategic issues facing the justice system. The strategic issues will be fundamental policy questions or critical challenges that affect the system’s mission and values (as could be, for example, legal training, judicial selection, judicial independence, administrative capacity, and access to justice). The exercise, which should include workshops with key stakeholders, will aim at reaching consensus about: (i) a succinct description of the issues; (ii) a list of the factors that make them fundamental; and (iii) a statement of the consequences of failing to address them.

2.05	It is expected that, by the end of this first stage, the consultancy will be able to provide the Government of Guyana and the Bank with a reasoned and documented analysis of the key issues facing the justice administration system of Guyana, as well as a roadmap to guide future policy and institutional changes. This analysis will serve as input for the drafting of the Project Concept Document for the Justice Modernization Program, and should detail the main issues that need to be addressed by that possible loan operation.

2.06	During the second and final action plan stage, the consulting team will develop improvement plans (action plans) for priority entities to be implemented during the execution of the Justice Modernization Program. This implies: (a) activities aimed at building a basic level of consensus among stakeholders regarding the steps that need to be taken to implement the strategic plan identified during the previous stage. Various short workshops will need to be organized by the consultancy in order to inform, dialogue with, and generate consensus among all (as far as is practicable) staff in each agency, concerning the aims and anticipated outputs of the Project. This process will also require the commitment of key decision makers to adopt the resulting strategy and, therefore, ensure a reasonable expectation for its implementation; (b) the action plans resulting from this part of the exercise will detail at least the following aspects: (i) implementation roles and responsibilities of oversight bodies, organizational teams and individuals; (ii) specific objectives and expected results; (iii) specific action steps and relevant details; (iv) time schedules; (v) required resources (costs); (vi) review and monitoring mechanisms; (vii) milestones for implementation; (viii) accountability procedures; and (ix) associated benefits and risks.

2.07	At the end of this stage the consultancy should be able to provide the Government of Guyana and the Bank with improvement plans that will serve as main inputs for the drafting of a Project Proposal Document for the Justice Modernization Program.

2. Setting up executing capabilities in the justice administration system

2.08	The Project will allocate resources of the Contribution to hire a project execution team that will function as the main liaison between the Bank and its counterparts in the judicial sector. It is expected that such a team will provide technical support and ensure continuity in the preparation and execution of the Justice Modernization Program. The project team will report to the Office of the Chief Justice of the High Court. In this preparation phase the team will include a project manager, a financial specialist and one administrative assistant.

2.09	Resources from this component will be used to fund the project team’s remuneration, per diem and travel expenses, as well as the procurement of equipment (computers, software and related expenses) for a period of approximately eight months.

III.	Total Cost of the Project

3.01	The estimated cost of the Project is the equivalent of three hundred and thirty thousand dollars (US$330,000), in accordance with the following Budget:

Budget

(in US$)

| Activities | Bank | Beneficiary | Total |
| --- | --- | --- | --- |
| I. Design and approval of roadmap | 199,000 |  | 199,560 |
| 1.1. International consultant services | 144,000 |  | 135,000 |
| 1.2. Seminars and workshops | 13,000 |  | 10,000 |
| II. Setting up execution unit | 60,800 |  | 60,800 |
| 1.1. Remunerations | 50,000 |  | 50,000 |
| 1.2. Equipment | 10,800 |  | 10,800 |
| ### III. Administrative support |  | 30,000 | 30,000 |
| IV. Evaluation | 15,000 |  | 15,000 |
| V. Audits | 3,000 |  | 3,000 |
| V. Contingencies | 21,640 |  | 21,640 |
| TOTAL | 300,000 | 30,000 | 330,000 |

## IV.	Execution

4.01	The Office of the Chief Justice of the High Court will be in charge of executing the Project. Therefore, it will have a direct participation in the successful completion of the Project through supervision of the work and overall functioning of the professional team that will participate in the design and execution of the Justice Modernization Program.

4.02	The Executing Agency and the Bank will closely supervise the work carried out by the consultant teams, which will produce advance reports for approval, as outlined in their terms of reference. The unit with administrative responsibility will be COF/CGY. Responsibility for the coordination of the work of the consultants will be shared by COF/CGY and RE3/SC3.

4.03	A final evaluation, carried out by independent consultants, will be financed with Project resources when ninety-five (95%) percent of the Contribution has been disbursed. The evaluation will assess the implementation of the Project and will document the achieved outcomes. This evaluation will determine: (a) the degree to which the Project achieved its objectives; (b) the efficiency of means used to address these objectives; (c) the factors that, in general, influenced Project outcomes; (d) the sustainability of the Project results; and (e) the lessons learned. The “Logical Framework” for the Project will be the primary tool used in this evaluation.