LEGIIII/GY-562900-05

ANNEX

THE PROJECT

Increasing Net Usable Yields in the Fisheries Sector

I.	Objective

  - The general objectives of the Project are to reduce the waste stream generated by processors in the wild caught shrimp sub-sector of the fisheries sector and to improve the operations of the fisheries sector in Guyana.

  - The specific objectives of the Project are: (i) to increase the net useable yields emanating from the wild caught shrimp sub-sector, (ii) to identify new products and markets for current waste streams produced by the trawler sub-sector, and (iii) to enhance the existing capacity within the Guyana Trawlers and Seafood Processors Association (GTSPA) to assist its membership in the pursuit of best practices.

II.	Description

The Project will consist of the following two components:

I. Developing New Products from current Waste Stream.

  - This component includes (i) Technical analysis and advise on the extraction procedure of chitins from the shell; (ii) a market analysis to determine inter alia: a)demand for the various products, b) location of markets, c) timing of markets (whether seasonal or year round), d) prices paid, e) potential costs and, f) conditions/standards for exporting; (iii) conduct sensitization workshops, and; (iv) assistance in cluster formation. To carry out this component the Executing Agency will engage the services of technical experts in the areas of food technology, with specialization in the fisheries sector and marketing.

II. Conducting a Feasibility Study.

  - This component will concentrate in conducting a feasibility study to utilize broken and emulsifying these into larger whole shrimp that can be exported.

  - This component would involve the hiring of consulting services to: (i) conduct visits to trawler processing plants; (ii) review of existing technology in the industry to determine what may be required; (iii) review equipment/procedure compatibility with the processors’ existing operations; (iv) assess availability of raw materials; (v) explore markets that exist for emulsified products; (vi) analyze skills availability in the industry and specific training requirements; (vii) determine quality standards/assurance, and; (viii) determine the ease of implementation.

  - The consulting services will be provided by an expert in Food Technology/Chemistry with practical experience in the industry, and some knowledge of marketing.

III.	Total Cost of the Project

3.01	The estimated cost of the Project is the equivalent of US$ 130,275 in accordance with the following Budget:

Budget in US Dollars

|  | BANK | LOCAL | TOTAL |
| --- | --- | --- | --- |
| I. Developing new products from current waste Streams | 50,125 | 6,000 | 56,125 |
| Food Technologist fees (20 days @$850) | 17,000 |  | 17,000 |
| Consultant travel and per diem (1 round trip) | 5,500 |  | 5,500 |
| 1 Demonstration workshop (travel and logistics) |  | 2,000 | 2,000 |
| Marketing Specialist (25 days @$850) | 21,250 |  | 21,250 |
| Consultant travel and per diem (1 round trip) | 6,375 |  | 6,375 |
| Cluster formation workshops (travel and logistics) |  | 4,000 | 4,000 |
| II. Conducting a Feasibility Study | 32,850 | 8,000 | 40,850 |
| Consultant fees (20 days @$850) | 25,500 |  | 25,500 |
| Consultant travel and per diem (1 round trip) | 7,350 |  | 7,350 |
| Local travel and support |  | 8,000 | 8,000 |
| III. Administration | 13,500 | 16,000 | 29,500 |
| Project coordination (3 months @ $3,500/mth) | 10,500 |  | 10500 |
| Auditing | 3,000 |  | 3000 |
| Communications |  | 8,000 | 8000 |
| Document reproduction, materials |  | 3,000 | 3000 |
| Office space |  | 5,000 | 5000 |
| IV. Contingencies (3%) | 2,900 | 900 | 3,800 |
| TOTAL (US$) | 99,375 | 30,900 | 130,275 |

IV.	Execution and Monitoring.

4.01. 	The Guyana Trawlers and Seafood Processors Association (GTSPA) will be the Executing agency. Its Project execution responsibilities will include, among other things, the selection, contracting and supervision of consultants, providing the Project consultants with the necessary background briefing, documents, information and logistical support to assist in their desk research and field trips; reproduction and submission of the consultants reports to the relevant national authorities; liaison with players in the sub-sector to ensure adequate participation in the Project’s implementation and organization of technical meetings and workshops/seminars.