LEGIII/GY-431666-05

THE ANNEX

THE PROJECT

Public Management Modernization Program (PMMP)

I.	Objective

  - The objective of the Project is to improve public management efficiency, transparency and accountability in the Government of Guyana, including its Semi-Autonomous Agencies (“SAA”). The specific objectives of this operation are to: (i) strengthen public service management and the Public Service Ministry (“PSM”) institutional capacity; (ii) improve accountability mechanisms for statutory bodies; and (iii) identify the long-term challenges for the State reform process in Guyana and promote consensus building for the related strategies.

II.	Description

  - The Project includes three (3) components: (i) Public service management strengthening; (ii) Agencies and statutory bodies accountability and efficiency improvement; (iii) Coordination of the State reform process.

Component 1 - Public service management strengthening

  - The objective of this component is to strengthen public service management and the PSM institutional capacity. In particular, this component will seek to: (i) improve the capacity of the PSM in order to enhance its competence to regulate and manage the public service system; (ii) review the public service rules and regulations to ensure normative consistency and management flexibility; (iii) enhance the existing Human Resource Management Information System (“HRMIS”) and connect the remainder of central public entities; (iv) strengthen management capacity of personnel offices; (v) train Permanent Secretaries (“PS”) and Heads of Department (“HD”); and (vi) design and implement a performance appraisal system for the PS and HD, including a revision of their responsibilities and authority.

  - Improving the capacity of the PSM. This activity will enhance the PSM’s capacity to regulate and manage the civil service system to facilitate greater efficiency and effectiveness in the public service. It will include the development of a Human Resource (“HR”) Strategy in conjunction with all relevant stakeholders and the enhancement of the HR structure for the public service. This activity will support the capacity of the PSM to define the structure and functioning of public organizations; reclassify positions and prepare the corresponding job-descriptions; and systematically plan the evolution of the workforce. The Project will finance the training of a number of HR officials to act as instructors to provide the actual training on an ongoing basis, and to rationalize, simplify and update the structure and functioning of public organizations and corresponding job descriptions. All training activities included in the Project will establish rules and specific commitments to promote public servants trained will remain in Guyana Public Service, minimizing the possibility of emigration.

  - Review of public service rules and regulations. This activity will seek to improve the normative consistency and management flexibility in the public service to increase the efficiency, effectiveness and transparency of the HR function. This will be accomplished by reviewing and updating the current rules and regulations and by training all relevant HR staff in the revised guidelines. In particular, this activity will provide the necessary technical assistance to review and validate the public service rules and the Public Service Commission (“PSC”) rules. In order to ensure the efficacy and sustainability of the process to update the regulations, coordination and participation with all entities involved in the HR management shall be attained. To this end, the Project will also provide: (i) technical assistance to the Guyana Public Service Union (“GPSU”) to support its participation in all necessary discussions; and (ii) a number of opportunities (i.e., workshops and seminars) to facilitate the attainment of consensus. The Project will also finance a dissemination campaign to ensure that all employees become familiarized with the new regulations. In order to promote equal opportunities for both women and men in the public service, gender issues will be specifically addressed by this revision of the rules and regulations. The Bank’s Program for the Support of Women’s Leadership and Representation (PROLEAD) plans to finance a study, a survey and the design of a training course to promote gender equity in the public service.

  - Enhancement of the HRMIS. This activity will expand and fine-tune the HRMIS, complete the interconnection between the Ministry of Finance (“MOF”) and the regions and provide local area network (“LAN”) connectivity to a total of thirty five (35) agencies twenty (20) ministries, ten (10) regions and five (5) Constitutional agencies. In addition, the Project will complete the wide area network (“WAN”) connectivity to the remainder of public agencies, while making the necessary improvements and adjustments. This activity will finance technical assistance and training of personnel, and the acquisition of equipment. The HRMIS will include in its management reports the information necessary to support the monitoring of public service management indicators, defined in the Project’s logical framework.

  - Strengthening of Personnel Offices (“PO”). This activity will enhance the management capacity of the PO of all twenty-two (22) ministries, the ten (10) regions and five (5) Constitutional agencies. It will finance technical assistance to update the structure and functioning of PO; train their personnel on the application of the new policies and rules, work planning, drafting of job descriptions, use of the new HRMIS.

  - Training of PS and HD. This activity will increase the effectiveness and efficiency of approximately eighty (80) PS and HD by updating their management skills. Technical assistance will be provided to identify the management training needs and to develop a training curriculum. It will also finance courses and training material.

  - Performance Appraisal System (“PAS”) for PS and HD.  This activity will enhance the institutional and personnel performance in the Executive Branch by increasing the accountability of PS and HD, including a revision of their responsibilities and authority. It will finance technical assistance to design and implement a PAS, including the validation and consensus-building workshops as well as the necessary training. During the Logical Framework Seminar held in Georgetown in August 2004, the majority of the PS, deputies and other authorities of the Central Government were consulted about the scope and modality of the future PAS. Their preliminary recommendations were: (i) goals must be realistic, measurable and time bound; (ii) managers must have sufficient institutional resources, incentives and autonomy to achieve the goals and results proposed; (iii) flexibility in the system to fit different situations and institutions; (iv) include institutional actors other than ministries, such as the Director of Budget (MOF), PSM, Auditor General and State Planning; and (v) clearly define who appraises and how. The PAS will include specific accountability arrangements (i.e. a performance contract) between each HD and each PS with their Minister and the Head of Government on the basis of performance benchmarks.

# Component 2: Agencies and statutory bodies accountability and efficiency improvement

  - This component will develop mechanisms to support SAA and Statutory Bodies (“SB”) by financing: (i) development and implementation of a general institutional framework to classify SAA and SB; (ii) revision and reclassification of SAA and SB from a sector perspective; (iii) support the strengthening of management and accountability capabilities in at least six pilot SAA and/or SB; and (iv) design and implementation of a monitoring and evaluation system for SAA and SB.

  - The institutional framework to classify SAA and SB will include general policy guidelines and standardization of the definition of the different types of agencies to categorize these entities and the development of corresponding operation procedures for each type. The revision and reclassification will be carried out prior to the implementation of the pilots and will include specific sector studies to address institutional fragmentation and function overlaps; and will be performed taking into consideration the recommendations of the “Report of the Committee to Review and Classify Statutory Bodies” prepared by the MOF in 2004. It is expected that these activities will reduce the total number of SAA and SB, including mergers and eliminations, with the aim of disbanding or restructuring those which have outlived their mandates, and incorporate their functions into regular line agencies, as proposed in the National Development Strategy.

  - Under the pilot projects to support the strengthening of management and accountability capabilities in at least six SAA and/or SB, the Project will finance: restructuring, workforce planning, self-generated revenues strategy, and performance monitoring and evaluation. Restructuring will include: the implementation of new organizational structures and their relationship with the sector and the related ministry (activities to strengthen a given agency or statutory body may be extended to the ministerial level where there is a need for improved oversight); the strengthening of strategic formulation capacities; the revision of selected work processes; the outsourcing of support services; and other activities. Workforce planning will include: a critical review of the number of positions; the matching of job descriptions and establishments to mission statements and services provided, and of individual employees to job descriptions and required qualifications; agreement upon a new personnel structure; and capacity building through training. Self-generated revenues strategy will include financial sustainability analysis to promote ways in which the agency can generate revenue through and for its activities. Performance monitoring and evaluation will include the building of the structures and capacities necessary to monitor Project performance and a mapping of current performance.

  - The criteria to identify the list of pilot agencies and to modify or to include other entities, will be: (i) prior reclassification and sectoral arrangements realized under activities mentioned in paragraph 2.10; (ii) high potential to increase self-generated revenues or decrease subventions; (iii) political commitment; (iv) relevant size; and (iv) significant service to the public. A specific final report for each pilot will be prepared, including efficiency, efficacy and transparency indicators, and an impact evaluation analysis. The experience of these pilots will be evaluated before being replicated in other agencies.

  - The objective of a monitoring and evaluation system for agencies will be to encourage results-based decision-making processes, transparency, accountability, and competition for budget resources. It is expected the implementation of this system will contribute to increase self-generated revenues or decrease subventions for SAA and SB as proposed in the National Development Strategy. Design of the system will involve definition of the type and nature of financial information required for effective decision making, and capacity-building for the development, monitoring and evaluation of service agreements between the ministries and the agencies, related to Project outcomes, impacts and benefits. In addition, the Project will provide resources to support capacity building in the analysis and use of information generated by the system.

  - The design and operation of this system will be coordinated with the Fiscal and Financial Management Program (Loan 1551/SF-GY) and will include the linkage with the “Project Performance Statements” mentioned in the Fiscal and Management and Accountability Act (“FMAA”). The system will include in its management reports the information necessary to assist with the monitoring of the indicators of SAA and SB defined in the Project’s logical framework.

# Component 3: Coordination of aspects of the State reform process

  - The objective of this component is to identify the long-term challenges for the State reform process in Guyana and promote consensus building for the related strategies. In particular, this component will finance: (i) institutional and governance assessment to identify potential areas for improvement and the long-term challenges for the State reform process, including consensus building activities around specific actions identified in the assessment; (ii) design of specific guidelines to improve transparency and integrity in the public sector; (iii) development of an Information Technology (“IT”) Plan for the Government; and (iv) formulation of strategies and policies for local government institutional development.

  - The institutional and governance assessment will support the preparation of the White Paper for State Reform in Guyana, including the conceptual definitions and institutional models for the main functions of policy-making, regulation, and service delivery in the public sector. Also, the assessment will identify potential areas for improvement and the long-term challenges for State reform, including the Legislative and the Judicial Branches, taking into account the analysis of potential environment and social impacts of the course of action.  It is expected that the White Paper for State Reform will create a supportive environment and increase the internal ownership for the reform that will be reflected in legislative and regulatory changes at an appropriate time.

  - The Project will promote consensus building among stakeholders around specific actions identified in the assessment, with a view toward managing expectations and developing an agreed upon approach to the State reform process. To this end, a Modernization of the State Board (“MSB”) should be established with the participation of relevant stakeholders. Activities will be undertaken to promote studies and debates about important issues and the costs and sequencing of reform, including monitoring and evaluation indicators and the analysis of potential environmental and social impacts, as well as the issue about gender and ethnic diversity in the Guyanese public sector.  It is expected that this approach will promote political feasibility and sustainability throughout the whole process.

  - For the purpose of supporting component 3, the MSB will be established as a high-level consultative body and, among other functions, will review the White Paper and make the recommendations it may deem appropriate. It is recommended that this board be comprised of the main stakeholders related to the State reform process, including representatives of, at least: the Executive branch, the Legislative, the Judiciary, the PSC, the GPSU, the Private Sector Commission, and one civil society organization. The board will be established within the first six months of the signature of the Loan Contract and will meet at least once a quarter. The Prime Minister of Guyana will chair the MSB.

  - The Project will finance an assessment of the Integrity Commission (“IC”), including an evaluation of its effectiveness and a review of existing legislation and recommendations.

  - The design of the IT Plan will include: (i) an assessment of the management of information systems and technology investment in the Government of Guyana (“GOG”); (ii) the development of a strategic information systems plan; (iii) the establishment of the IT standards program; and (iv) the design of the protocol for the sharing of information as well as for the access to public management data.

  - For the formulation and implementation of strategies and policies for local government institutional development, to support a new approach to their work and their relations with the people they serve as citizens and clients and to promote increasing of local revenues and service delivery, the Project will finance: (i) a diagnosis and design of proposals for institutional strengthening of Neighborhood Democratic Councils (“NDC”), including a training plan to build the necessary skills to effectively manage the councils and the design of instruments and mechanisms to promote public accountability; (ii) design and implementation of an information system for local development in the Ministry of Local Government and Regional Development (MLGRD); (iii) design of a policy framework to improve coordination between public utilities and NDC regarding investment plans and service delivery; and (iv) design a policy and institutional framework for the updating of property values in NDC areas and training to develop property appraisal capacity.  Activities of this subcomponent are subject to the outcome of the constitutional reform process.

III.	Total Cost of the Project and Financing Plan

3.01	The estimated cost of the Project is the equivalent of five million five hundred and sixty thousand dollars (US$5,560,000), in accordance with the following investment categories and sources of financing:

Cost and Financing

(in thousands of US$)

| Investment Categories | Bank | Local Contribution | Total | % |
| --- | --- | --- | --- | --- |
| ## Project Administration | 405 | 90 | 495 | 8.9 |
| Individual Local Consultants | 360 | - | 360 | 6.5 |
| Purchases, Maintenance & Administrative Assistants | 45 | 90 | 135 | 2.4 |
| DIRECT COSTS | 4,135 | 360 | 4,495 | 80.8 |
| 1. Public service management strengthening | 1,720 | 180 | 1,900 | 34.1 |
| 1. Strengthening of PSM | 190 | 30 | 220 | 4.0 |
| 2. Review of PS rules and regulations | 200 | 30 | 230 | 4.1 |
| 3. Enhancing of HR management IT (system/database) | 700 | 45 | 745 | 13.4 |
| 4. Strengthening of Personnel Offices | 110 | 30 | 140 | 2.5 |
| 5. Training of PS & HD | 125 | 15 | 140 | 2.5 |
| 6. Performance appraisal for PS & HD | 395 | 30 | 425 | 7.6 |
| 2. Agencies and SB accountability and efficiency improvement | 1,495 | 105 | 1,600 | 28.8 |
| 1. Institutional Framework | 90 | 30 | 120 | 2.2 |
| 2. Reclassification & Revision | 245 | 30 | 275 | 4.9 |
| 3. Pilots Restructuring & Strengthening | 870 | 22 | 892 | 16.0 |
| 4. Monitoring & Evaluation System | 290 | 23 | 313 | 5.7 |
| 3. Coordination of State reform process | 920 | 75 | 995 | 17.9 |
| 1. Institutional & Governance Assessment & Consensus Building | 245 | 30 | 275 | 4.9 |
| 2. Transparency & Integrity Guidelines | 65 | 15 | 80 | 1.4 |
| 3. IT Strategy Plan | 220 | - | 220 | 4.0 |
| 4. Institutional Development for Local Governments | 390 | 30 | 420 | 7.6 |
| 4. Concurrent Costs | 90 | - | 90 | 1.6 |
| 4.1 External Audit | 50 | - | 50 | 0.9 |
| 4.2 Evaluation (initial framework and baseline + final evaluation) | 40 | - | 40 | 0.7 |
| 5. No Specific Assignation (contingencies) | 320 | - | 320 | 5.8 |
| 6. Financing Costs | 50 | 110 | 160 | 2.9 |
| 6.1 Interest |  | 75 | 75 | 1.4 |
| 6.2 FIV (1%) | 50 | - | 50 | 0.9 |
| 6.3 Credit Commission (0,5%) | - | 35 | 35 | 0.6 |
| Total | 5,000 | 560 | 5,560 | 100.0 |
| % | 90% | 10% | 100% |  |

- 3.02	The Bank financing of five million dollars (US$5 million) will come from the Fund for Special Operations (“FSO”).  The following table shows the terms and conditions of the loan:

| - Source of funds: | - Fund for Special Operations |
| --- | --- |
| - Amount: | - US$5 million (FSO) |
| - Terms: - Amortization: - Execution: - Disbursement: | - 40 years - 42 months - 48 months |
| - Interest rate: | - 1% for the first 10 years and 2% thereafter |
| - Inspection and supervision: | - 1% |
| - Credit fee: | - 0.5% on the undisbursed balance |

IV.	Execution

  - The Executing Agency will be the Office of the President through the Head of Presidential Secretariat, which will have overall responsibility for the implementation of the Project. For the purposes of project execution a Steering Committee (“SC”) and a Program Executing Unit (“PEU”) will be established, to carry out strategic and administrative guidance to the Project activities.

  - The SC will be responsible for strategic high-level leadership and overall Project guidance, coordination and oversight, as well as for the supervision and approval of annual operating plans (“AOP”). The SC will approve the Project’s semi-annual progress reports, mid-term review and final evaluation on the execution of the components. The Minister of Public Service will chair the SC by delegation of the Head of Presidential Secretariat, and its membership will include the Permanent Secretaries of the Office of the President, the Public Service Ministry (“PSM”), the Ministry of Finance (MOF) and of the Ministry of Local Government and Regional Development (“MLGRD”). The coordinator of the PEU will act as secretary of the SC. The SC will meet at least once a quarter and will send the semi-annual, mid-term and final progress reports to the MSB for its information; the SC will also consult the MSB from time to time, as needed.

  - The PEU will be structured within the Permanent Secretary’s Bureau of the Office of the President. A general coordinator, who shall be a highly qualified professional, will head the PEU. The PEU will be staffed with a procurement officer (for contracting firms/individual consultants and making purchases), a finance/accounting officer, a technical officer, and administrative assistants. The loan resources will cover the honoraria of the general coordinator and other officers. In order to ensure a better assimilation in the GOG of the project products prepared by the consultants and to promote project sustainability, the GOG will select, appoint and finance, with local counterpart resources, four technical coordinators (TC) to the satisfaction of the Bank (one coordinator per component and one for information technology). In order to support the PEU in the contracting of the individual consultants, GOG and COF/CGY may consider the feasibility of using a retainer firm to package some of these individual contracts.  For this purpose, the PEU would use the contingencies resources, if necessary. The technical coordinators will not be included in the PEU structure but in their corresponding ministries; nevertheless, the technical coordinators will coordinate their activities with the PEU during Project execution, and the local counterpart resources to finance these technical coordinators are included in the corresponding component’s budgets. The creation of the PEU will comprise the hiring of the general coordinator, the officers and the consultant for evaluation, and the appointment of the four technical coordinators.

  - The PEU will be responsible for: (i) coordinating and monitoring the Project execution; (ii) preparing and presenting the AOP of all subcomponents, and the semi-annual progress reports, midterm review and final evaluation to the SC for approval, in addition to other reports requested by the Bank during the Project; (iii) conducting the procurement and processing the contracts required; (iv) preparing and presenting disbursements requests and justification of the use of funds to the Bank’s satisfaction, and the semi-annual reports on the use of the revolving fund; (v) maintaining the financial and accounting records related to the use of financed resources, demonstrating at any time that the funds are used for the purpose intended by the loan; (vi) keeping adequate documentation to support the disbursements received; this information shall be made available for review by Bank personnel and/or external auditors; and (vii) preparing and presenting the financial statements of the Project to the Bank, duly certified by eligible external auditors, in conformity with Bank rules and procedures.

  - Notwithstanding that the Executing Agency is the Office of the President, each subcomponent has a participant entity responsible for the technical coordination of the activities. The four technical coordinators mentioned in paragraph 4.03 will be the link between the participant entities and the PEU, and will be responsible for the preparation of the terms of reference for each contract and for the approval of the consultants’ reports, in order to authorize the PEU to make the corresponding payments.

  - The AOP consists of the detailed budget for each subcomponent including the main characteristics of the contracts with each firm or individual consultant, the bidding procedure and time for execution. Also, the AOP includes the summary of the terms of reference with the objectives for each contract and the sequence of implementation. The draft of the AOP for the 3.5 years of Project execution has been prepared and agreed with the project team.

  - The semi-annual progress reports, midterm review and final evaluation will consist of the monitoring and evaluation of the execution of each subcomponent, including the activities completed, the costs incurred, the products obtained, and an assessment of the Project’s performance.

V.	Procurement of goods and services

- 5.01	Procurement of goods and consulting services will be conducted according to Bank standard procedures.  The procurement of goods exceeding the amount equivalent to US$100,000 will be carried out through international competitive bidding, open to all IDB member countries. For the hiring of consulting firms, with contracts in excess of US$100,000, it will be required that the PEU carry out international request for proposals.

- VI.	Execution and disbursement schedule

- 6.01	The disbursement of the loan’s resources will be made over a maximum period of 48 months. To disburse the Bank financing, a revolving fund of up to 5% of the amount of the loan will be established in a special bank account. The tentative schedule of disbursements of the Project disaggregated by sources of financing is as follows:

| Table III-1. Projected Annual Disbursements (In thousands of US$) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Source | Year 1 | Year 2 | Year 3 | Year 4 | Total |
| IDB (FSO) | 1,000 | 1,500 | 1,750 | 750 | 5,000 |
| GOG | 180 | 185 | 195 | - | 560 |
| Total | 1,180 | 1,685 | 1,945 | 750 | 5,560 |
| % Year | 21.2 | 30.3 | 35.0 | 13.5 | 100 |

- VII.	Monitoring and evaluation

- 7.01	The monitoring and evaluation process will include the submission to the Bank of AOP, semi-annual progress reports, a mid-term review and a final evaluation approved by the SC, as well as the presentation of the financial and revolving fund statements. The loan resources will finance the hiring of a consultant specialized in monitoring and evaluation. This consultant will be responsible for preparing the evaluation framework, based primarily on the indicators and goals defined in the Logical Framework, and for estimating the baseline for the first two indicators of the “purpose” for management efficiency. The PEU will hire this consultant during the creation of the PEU to fulfill the first condition of the Project.  On the basis of the evaluation framework, a mid-term review and a final evaluation of the Project will be carried out. The mid-term review shall be completed once 50% of the project financing has been disbursed, and will assess progress of project implementation, and the final evaluation should be completed within the last three months of the Project. The loan resources will also cover the cost of contracting an evaluation consultant to prepare the final evaluation.

- 7.02	The PEU will collect, store and retain all necessary information, indicators and parameters, including the AOP and other information compiled for the annual follow-up meetings, the mid-term review and final evaluation, to help the Bank prepare the Project Completion Report (PCR).

- 7.03	The PEU will prepare and submit to the Bank, within one hundred and twenty (120) days after the closing date of each fiscal year and within one hundred and twenty (120) days after the date of the last disbursement of the financing, the financial statements of the project, audited by a firm of independent auditors acceptable to the Bank, based on the terms of reference previously approved by the Bank (Document AF-400). The firm will be selected and contracted in accordance with the Bank’s bidding procedures for audit firms (Document AF-200), and will be paid with the Bank’s financing.