LEGIII/GY-768939-06

THE ANNEX

THE PROGRAM

Program for the Modernization of the Justice Administration System

I.	Objective

1.01	The objective of the Program is to enhance the investment climate and rights enforcement in Guyana through improved public sector governance. To achieve this objective, and in accordance with the three main pillars of the Justice Sector Reform Strategy (“JSRS”), the Program is intended to assist the Government of Guyana in taking initial steps towards: (a) strengthening the accountability and administrative efficiency of service delivery in the justice sector; (b) enhancing linkages and coordination within justice sector institutions; and (c) improving access to justice.

II.	Description

2.01	The Program will finance the implementation of the following subcomponents:

(a) Subcomponent 1: Enhancing institutional capacity

2.02	The purpose of this subcomponent is to improve the quality, efficiency and efficacy of service delivery in justice sector institutions in Guyana by strengthening governance and accountability, building institutional capacity, streamlining legal procedures and modernizing administrative systems. Specifically, this subcomponent will finance activities in the following areas:

1. Strengthening the Judicial Services Commission (“JSC”). Objective: Improve governance, recruitment, human resource management and accountability of judges, magistrates, and court staff. Specific tasks include: Consultancy services will be contracted by the Judiciary’s Project Execution Unit (“PEU”) in order to assist the Judicial Service Commission (“JSC”) in: (i) developing JSC governance policies, operational rules and regulations; (ii) developing a new code of conduct and ethics for judges and magistrates, as well as enforceable timeliness guidelines pertaining to orders and opinions as provided by the Constitution; and (iii) conducting workshops for judges to sensitize them to the new codes and guidelines. The Program will also finance the equipment and facility improvements needed to establish a JSC Secretariat. Consultancy services will also be provided to, in consultation with the Registrar’s Office, support the JSC in planning for and then assuming jurisdiction and oversight (including recruitment and discipline) of court administration staff.

2. Reducing Backlog and Raising Clearance Rates. Objective: Eliminate the backlog of civil and criminal cases in the High Court, Magistrates Courts and Appeals Courts, and reduce delays in the management and adjudication of cases. Specific tasks include: (i) design and implementation of new case flow management procedures and related training to be provided by experts in case management; (ii) building on the existing High Court civil cases backlog clearance program, consulting services will be provided to assist in streamlining the process and expanding it to criminal cases, as well as preliminary inquiries; and (iii) consulting services will also be hired to expand court-connected mediation to the Magistrates Courts.

3. Strengthening court administration. Objective: Strengthen the administration of the Supreme Court of Adjudicature in the management of cases and case-related information, human resources, and its budgeting and financial activities. Specific tasks include: necessary expertise and equipment will be contracted and procured in order to: (i) support to the Supreme Court Registry in the development and implementation of modern and transparent human resources policies and programs (including a reorganization, development of job descriptions and performance standards, and comprehensive training and continuing education for court staff); (ii) design and implement an information and management and communication system (including inter-court intranet and email communication system for both the Magistrates’ and High Courts); (iii) provide support to improve court financial management (with a focus on accounting and controls, financial reporting, budgeting); and (iv) design and installation of a modern Financial Management Information System (“FMIS”), and related training for court administration staff.

4. Enhancing skills and productivity of Judges and Magistrates. Objective: Improve the quality of judicial decisions and opinions and the overall productivity of judges and magistrates. Specific tasks include: (i) supply specialized training and continuing education throughout the execution of the Program for judges and magistrates with programs focused both on specialized areas of law (i.e., family) and on judicial skills (also, while the emphasis will be on in-country training, the Program will make resources available for study tours, primarily within the Caribbean and North America); and (ii) purchase legal materials, resources and tools such as legal texts (stocking of law libraries) and subscriptions to online legal resources. A consultant will be contracted to, in consultation with the Chief Justice, judges and magistrates, assess needs, conduct an inventory, and develop a plan for procurement of the most-needed texts, materials and resources to be procured within the available budget. The consultant will also provide orientation and training to judges in the use of online legal resources.

5. Rehabilitation of physical improvements to courtrooms and courthouses. Objective: Ensure that courthouses and courtrooms are basically equipped to facilitate hearings and trials of civil and criminal matters. Specific tasks include: (i) develop a needs assessment and procure furnishings and minor civil works for courthouses-in-need (especially several dilapidated courthouses in rural areas); (ii) procure equipment for court rooms (including court recording equipment and training of court reporters) and IT and related equipment for magistrates Court Offices; and (iii) procure goods, equipment and minor works for court houses relating to miscellaneous furnishings, basic equipment, soundproofing and air conditioning.

6. Improving criminal justice. Objective: Enhance the functional and operational capacity of the Department of Public Prosecution (“DPP”) and strengthen the effectiveness of public prosecutors. Specific tasks include: consulting services will be hired in order to: (i) help design and implement a functional and operational reorganization of DPP; (ii) develop and implement a plan for phasing out of Police prosecution of narcotics and indictable cases (short-term) and phasing out of Police prosecution of all criminal matters (long-term); and (iii) train prosecutors and Police (including training for prosecutors in specialized areas such as cyber-crime and money laundering) and DPP staff. Also, the Program will finance the design and installation of management information system software; and procurement of minor works and furnishings for confidential witness discussions; and procurement of goods, equipment, minor works for expansion of DPP offices outside of Georgetown.

7. Institutional strengthening of the Ministry of Legal Affairs (“MLA”). Objective: Strengthen the functional and operational capacity of the MLA in carrying out its legal mandates and improving its administrative efficiency. Specific tasks include: Consultancy services will be hired in order to: (i) review of the legislative making process, including the system for assignment of legislation to Ministries and development and implementation of a reform plan; (ii) review policies and procedures in relation to the conduct of Government litigation and develop policy guidelines and/or legislation; and (iii) assess functional and operational structure of MLA and implement a plan for strengthening legal sector policy and planning departments.

8. Drafting civil and criminal procedural laws. Objective: Modernize antiquated civil and criminal procedural laws and rules and draft new acts necessary for more efficient, effective and fair treatment of civil and criminal cases in the courts. Specific tasks include: (i) provide consulting support to MLA process of overseeing review of criminal and civil procedural provisions/rules in consultation with Judiciary and Bar; (ii) provide consulting support to MLA for legal drafting (this will include amendments to: Summary Jurisdiction (Petty Debt) Act; Summary Jurisdiction (Magistrates) Criminal Law (Procedure) Acts; Summary Jurisdiction (Offences) Act; Criminal Law (Offences) Act; Evidence Act, Arbitration Act, Legal Practitioners Act); and (iii) workshops will be conducted, with the participation of experts involved in drafting the law amendments, to sensitize judges/magistrates to the revised and new laws, and provide digests (with guidelines) on the revisions.

9. Improve other criminal and civil law procedures. Objective: Modernize and streamline criminal and civil procedures to achieve greater simplification, uniformity and predictability in matters of bail, sentencing, costs, appeals, and continuity of hearings and trials. Specific tasks include: (i) develop comprehensive guidelines for granting bail by judges and magistrates; (ii) reform of listing and notification procedures to ensure ‘continuous’ (day-to-day) hearings and trials in High Court and Magistrates Court; (iii) establish and implement plan for simplifying appeal procedures; (iv) establish sentencing guidelines (including community service orders) and a framework to facilitate consultation between judges and magistrates on sentencing issues; (v) develop guidelines on adjournments; (vi) develop guidelines and provide related training on assessment of costs; (vii) review current methods of enforcement and develop reform plans; and (viii) in consultation with main stakeholders, conduct a review of court fees and fines (which will then be included in the new High Court civil procedure rules).

(b) Subcomponent 2: Strengthening Linkages among Justice Institutions

2.03	The purpose of this subcomponent is to promote more efficient interactions among justice institutions through both “top down” and “bottom up” approaches. Top down interventions will be concerned with sector-wide policy, planning and resource allocation. The bottom up approach will enhance communication, coordination and cooperation among institutions at the operational/local level.

2.04	As part of its support to sector-wide policy leadership, planning and coordination (top down approach), the subcomponent will finance activities for the establishment of the Justice Sector Reform Steering Committee and its Technical Secretariat (“TS”). The Steering Committee will provide high-level policy guidance and coordination for implementation of the Justice Sector Reform Strategy (“JSRS”). It will bring together a small group of key policy makers from Government and the Judiciary (including, at a minimum, the Ministry of Finance (“MOF”), the Attorney’s General Chambers, the MLA, the Ministry of Home Affairs, the Chancellor of the Judiciary and the Chief Justice), and provide continuity with the group that led the development of the JSRS. The Steering Committee will provide an important high level forum for the various sector agencies to coordinate the overall reform, solve strategic problems as they arise, ensure that the overall Strategy is being followed, and all organizations are delivering what they need to do on time and within budget. It will meet quarterly to review progress and make any necessary policy decisions to guide implementation. The Committee’s purview is to be long term and sector-wide, beyond just the scope of this Program.

2.05	The Technical Secretariat will provide coordination and technical support to all justice sector institutions. Specifically, the Technical Secretariat will: (i) ensure that complex reforms in different institutions are effectively linked, sequenced, managed, resourced and led, and in particular that issues of joined-up justice are properly addressed; (ii) source additional technical assistance or other support as necessary to enable institutions to implement JSRS reforms; (iii) ensure timely and appropriate monitoring and evaluation of strategic performance, and make certain that this performance is communicated to stakeholders; (iv) provide a secretarial function for the JSRS Steering Committee, ensuring that the Committee has all necessary information available to support its decisions; and (v) coordinate donor agencies supporting the justice sector, including establishment of a justice sector donor group.

2.06	The objective in this area will be to create institutional and policy mechanisms for facilitating inter-institutional cooperation and coordination. Specific tasks include: (i) provide consulting support to work with the Secretariat; (ii) procure furnishings and equipment; (iii) develop terms of reference, rules of procedure, objectives, and comprehensive set of benchmarks and performance indicators; (iv) conduct mapping of end-to-end processes (organizational and functional) of each justice institution and for assessment of cost savings; (v) supply equipment and consulting support to establish integrated information systems to assimilate, analyze and report statistics and indicators on a cross sector basis; (vi) prepare a functional and operational plan for the DPP with particular focus on coordination with the Police; (vii) develop a monitoring and evaluation (M&E) framework; (viii) provide support for undertaking baseline indicators, goals and benchmarks; (ix) develop systematic M&E plans for the overall program and for individual justice sector institutions; and (x) conduct biannual user surveys (Bar, Private Sector, Civil Society).

2.07	Regarding support for coordination instances at the local level (bottom up approach) the objective is to foster ongoing participation of civil society in justice sector strategy and policy development. Specific tasks include, hiring consulting support, acquiring equipment and providing training necessary to: (i) establish Criminal Justice Committees at the local level, centered on each Magistrate Court (comprising representatives of stakeholders involved in the processing of criminal justice cases and focused on improving inter-agency cooperation, communication and co-ordination at the operational level); and (ii) establish Civil Justice Committees comprised of court users and other stakeholders (attorneys, private sector, NGOs) and workshops to facilitate semiannual consultations with the JSRS Steering Committee.

(c) Subcomponent 3: Improving Access to Justice

2.08	The purpose of this subcomponent is to improve access to justice in Guyana by enhancing citizen awareness of their rights and responsibilities and providing services to court users to facilitate legal advice and representation, as well as access to information and alternative dispute resolution mechanisms. To achieve these aims, activities to be financed under this subcomponent will include the following:

1. Expansion of legal aid services. Objective: Provide information, advice and representation to citizens, especially the poor and marginalized. Specific tasks include: consulting services, training activities and equipment purchases will be financed in order to: (i) provide expert support to develop an action plan for a nationally substainable legal aid scheme (including citizens’ legal advice offices); (ii) once the action plan has been agreed with the Government of Guyana, provide technical assistance and equipment to support the Georgetown Legal Aid Clinic as well as expansion of its services to New Amsterdam and Essequibo Coast; and (iii)  provide training and material resources for three-year implementation of national legal aid scheme.

2. Development of public legal awareness. Objective: Ensure all Guyanese citizens are aware of their legal rights and responsibilities and of the services available for resolution of their disputes. Specific tasks include: consulting services, training activities and purchase of media services will be financed to: (i) develop a national legal awareness strategy and action plan, and a communications strategy for the justice sector; (ii) implement legal awareness media campaigns, and support for related consultations in collaboration with NGOs; and (iii) implement local consultations/workshop series.

3. Support for informal justice. Objective: Provide alternatives to the formal justice system, especially in rural areas and for the poor and disadvantaged. Specific activities include: (i) develop a paralegal program including the use of voluntary social mediation workers from Village Councils, welfare officers and Justices of the Peace; and (ii) prepare a plan for introduction of community ADR (mediation) and program implementation, including training of local mediators and community NGOs.

4. Law revision and legislative framework. Objective: Enable improved access to justice-and to judicial orders and opinions-through revision of specific laws and updating of Guyana Law Reports and Laws of Guyana. Specific tasks include: Consulting support and equipment will be provided in order to: (i) reform the Legal Practitioners Act (including provisions for “no win no fee” contingency arrangements) and ADR Act; (ii) support and strengthening of the Legal Practitioners’ Committee, including training; and (iii) provide expert support to the MLA for updating Guyana’s Law Reports, and consultancy services to support for the Law Revision Commission (which is to be re-established further to the policy-based component of the Program).

III.	Total Cost of the Program and Financing Plan

3.01	The estimated cost of the Program is the equivalent of ten million two hundred-thirty two thousand dollars (US$10,232,000), in accordance with the following investment categories and sources of financing:

Cost and Financing

(in thousands of US$)

| ### Categories | Bank |  | Borrower | Total |
| --- | --- | --- | --- | --- |
| Investment Component | $9,900 |  | $0 | $9,900 |
| ## Implementation Responsibility > | Judiciary | MLA |  |  |
| ## Subcomponent 1: Enhancing Institutional Capacity | $3,383 | $1,347 |  | $4,730 |
| 1.1 Strengthening of the JSC | $91 |  |  |  |
| 1.2 Backlog and Delay Reduction | $506 |  |  |  |
| 1.3 Strengthening Court Administration | $1,031 |  |  |  |
| 1.4 Skills and Productivity Enhancement for Judges,Magistrates | $939 |  |  |  |
| 1.5 Amending civil and criminal procedural laws and drafting acts |  | $410 |  |  |
| 1.6 Physical improvements to courtrooms and courthouses | $675 |  |  |  |
| 1.7 Criminal Justice Improvements |  | $867 |  |  |
| 1.8 Criminal Procedures Improvements | $45 |  |  |  |
| 1.9 Civil Procedures Improvements | $66 |  |  |  |
| 1.10 Administrative Justice | $30 |  |  |  |
| 1.11 Institutional Strengthening of MLA |  | $70 |  |  |
| Subcomponent 2: Strengthening Linkages among Justice Institutions | $0 | $1,209 |  | $1,209 |
| - Sector-wide Policy Leadership, Planning a and Coordination |  | $1,000 |  |  |
| 2.2 Ensuring Participation of Users and Beneficiaries |  | $209 |  |  |
| Subcomponent 3: Improving Access to Justice | $0 | $2,077 |  | $2,077 |
| 3.1 Expansion of Legal Aid Services |  | $428 |  |  |
| 3.2 Development of public legal awareness |  | $351 |  |  |
| 3.3 Informal justice |  | $298 |  |  |
| 3.4 Law Revision and legislative framework |  | $1,000 |  |  |
| Project Coordination | $635 | $634 |  | $1,269 |
| PEU Staffing | $509 | $508 |  | $1017 |
| Other Project Administration Costs (Office/Equip/IT) | $126 | $126 |  | $252 |
| External Audit and Evaluation | $250 |  |  | $250 |
| Contingencies | $365 |  |  | $365 |
| Financing Costs | $100 |  | $232 | $332 |
| Interest |  |  |  |  |
| FIV (1%) | $100 |  |  | $100 |
| Credit Commission (0,5%) |  |  | $232 | $232 |
| TOTAL PROGRAM COSTS | $10,000 |  | $232 | $10,232 |

IV.	Execution

4.01	The overall responsibility for the implementation of the Program will rest on the Justice Sector Reform Steering Committee. A Technical Secretariat (“TS”) will also be established in the Ministry of Legal Affairs (“MLA”) for coordination and technical support to all justice sector agencies, including those directly benefited by the Program. The Technical Secretariat will function as a coordination instance and a source of technical guidance to all Program activities.

4.02	Two Project Executing Units (PEUs), one within the MLA and the other, within the High Court will be established to execute the activities of the Program places under their respective responsibilities. The MLA will be additionally responsible for the direct execution of activities planned for the DPP.

4.03	The Justice Sector Reform Steering Committee through its Technical Secretariat (“TS”) will be responsible for overall Program guidance and oversight, as well as for the supervision of annual operating plans and budgets. The TS will review the progress reports on the execution of the Program, and will interface with other institutional actors in order to facilitate the orderly implementation of the Program. The TS will be responsible for ensuring effective coordination and execution of Program activities.

4.04	Each PEU will be responsible for: (i) coordinating the Program execution; (ii) revising and presenting the annual operating plans (AOPs), the semiannual, midterm and final reports, and any other reports requested by the Bank during the execution of the Program; (iii) monitoring execution performance and providing related information to the Secretariat; (iv) conducting procurement and processing contracts required for the implementation of the different subcomponents; (v) preparing and presenting disbursement requests and justification of the use of funds to the Bank’s satisfaction, as well as the semiannual reports on the use of the revolving funds; (vi) preparing the annual progress reports on execution performance for submission to the MOF and the Bank; (vii) maintaining financial and accounting records related to the use of financed resources, demonstrating at any time that the funds are used for the purpose intended by this Program; (viii) keeping adequate documentation to support disbursements received (this information shall be made available for review by Bank personnel and/or external auditors); and (ix) preparing and presenting financial statements of the Program to the Bank.

4.05	Furthermore, each PEU will be headed by a Coordinator, who will be a highly qualified professional appointed by the head of the respective agency (either the High Court or the MLA) in consultation with the Bank. Each Coordinator will hold the responsibility to act as liaison with the Bank and to ensure the coordination and consistency of their Program’ activities. The PEUs will be staffed with a Program management officer, a procurement officer, a finance/accounting officer, an accounts/administration officer and a secretary/administrative assistant. Each Coordinator shall appoint the staff of the PEU in a manner consistent with Bank procedures. Program Financing will cover staff salaries.

4.06	The agreement referred to in Section 3.02(d) of the Special Conditions, will contain, among other provisions, the following: (i) transfer of resources from the MLA to the High Court will be made on a nonreimbursable basis; (ii) the Judiciary, through the High Court, will carry out the activities under its competency in accordance with the terms and conditions set forth in this Contract; and (iii) all other conditions in connection with procurement, auditing, maintenance; and reports. For the execution of the activities for strengthening the DPP, an inter-institutional agreement between the MLA and DPP will be signed. Under this agreement, the MLA’s PEU will be responsible for administrative matters and day-to-day execution of the activities related to the DPP’s institutional strengthening. The DPP will be responsible for the technical supervision.

4.07	The High Court and the Ministry of Legal Affairs will manage the Program’s finances and accounts, realizing the accounting corresponding to the activities under each of their responsibilities. To that end, each PEU must: (i) maintain an effective administrative, financial, and internal audit system; (ii) keep separate accounts for the proceeds from the Loan; (iii) keep detailed information for the preparation of the consolidated financial reports, in accordance with Bank procedures; (iv) keep supporting information on the use of Program funds in an accessible filing system; and (v) keep proper records of the disbursement requests. Regarding the Revolving Fund, each PEU will be responsible for: (i) preparing the biannual Revolving Fund statements; and (ii) requesting Revolving Fund replenishments.

4.08	The Technical Secretariat will be responsible for coordinating all monitoring and evaluation processes. This will include: (i) ensuring that the PEUs keep updated and available information on their performance and on the achievement of the Program’s objectives, as established by the “Logical Framework”(and providing them support to ensure that they have the appropriate data collection systems in place to track their progress in achieving the relevant performance indicators); (ii) providing technical support and training to PEU staff in the areas of Program monitoring, and performance reporting based on the “Logical Framework” methodology; and (iii) preparing and submitting to Justice Sector Reform Steering Committee and the Bank periodic reports on the status of the Program, including special studies as requested. The Program’s Operation Manual will include mechanisms to ensure that all performance information is channeled from each of the two Project Executing Units (PEUs) to the Technical Secretariat.

4.09	Regarding the Policy-Based Component, the TS will be responsible for: (i) monitoring the compliance of conditionality and performance benchmarks set out in the policy and verification matrix; and (ii) reporting on compliance progress to the MOF and the Bank.