LEG/SGO/GY-1317618-08

# THE ANNEX

THE PROGRAM

## Supporting the PRSP Process: Towards the Institutionalization of a

## Monitoring and Evaluation Framework

I.	Objective

  - The objective of the Program is to strengthen the implementation of pro-poor policies and contribute to overall government effectiveness by supporting the transition towards an institutionalized monitoring and evaluation framework across Guyana’s public sector. The Program expects to achieve its objective by providing a common approach and understanding to monitoring and evaluation as a management tool, strengthening and integrating information flows to support core public management decisions and enhancing institutional capacity in monitoring and evaluation functions.

II.	Description

  - The Program contemplates the following three Components:

- Component I: Action Plan for the Institutionalization of Monitoring and Evaluation Functions.

  - With Contribution resources, the Executing Agency will select and contract a consulting firm for the preparation of an Action Plan for the institutionalization of monitoring and evaluation functions. Contribution resources will also finance the selection and hiring of an individual consultant to assist in related preparatory diagnostic work.

  - This Component will provide (i) relevant technical assistance to complete the necessary assessments and proposals for the implementation of the Roadmap and (ii) a detailed operational plan outlining the relevant processes, resources, responsibilities and implementation benchmarks.

  - As a result of this Component, a common framework of action for future Monitoring and Evaluation (hereinafter “M&E”) activities will be provided under an integrated vision, facilitating future interventions.

- Component II: Enhanced Institutional Capacity for M&E Functions.

  - With Contribution resources, the Executing Agency will select and contract consulting services for: (i) the preparation of information maps to identify bottlenecks for the improvement of information flows; (ii) the preparation of a conceptual design of harmonized and automatic key processes; (iii) an assessment on performance information relevance, standards, clarity, economy, adequacy and measurability; (iv) the preparation of relevant guidelines, operational manuals and organization of training activities, including an M&E course and Regional M&E Training Modules; (v) the strengthening of M&E operational capacity at the Ministry of Health, Ministry of Education and Ministry of Finance, including capacity building activities for the Executing Agency’s staff.

  - Additionally, with Contribution resources, the Executing Agency will select and contract two Program Focal Points from the Executing Agency.

  - This Component will improve both horizontal and vertical information flows, strengthen the quality and timeliness of information generated at the regional level, define a framework of performance-based indicators, and facilitate the automatization of processes and reporting obligations in the Ministry of Health, Ministry of Education and in the Ministry of Finance. As a result of the implementation of these activities it is expected that on-going M&E efforts at the Ministry of Health and at the Ministry of Finance will be strengthened, while integrated under a shared M&E framework.

- Component III: Development of a Results-Based M&E Information Tool.

  - With Contribution resources, the Executing Agency will select and contract a consulting firm to prepare an assessment and design a result-based M&E information tool.

  - This Component will support the design of an M&E tool in the second half of the Program, benefiting from the outcomes of activities financed under the first two components, will facilitate and integrate information flows at the sector ministry levels while interfacing with existing data management tools at the central level.

- Component IV: Creating stakeholder awareness and consensus building.

  - With Contribution resources, the following activities will be organized: (i) workshops for the Action Plan; (ii) a seminar on international best practices on M&E for senior management; (iii) training modules on M&E; (iv) workshops on performance reports for relevant stakeholders; and (v) training modules for preparation of performance reports for line ministries.

  - The workshops and dialogue sessions will aim at (i) generating consensus over the medium term vision for M&E and (ii) facilitating the understanding of M&E as a constructive management tool.

III.	Total Cost of the Program

3.01	The estimated cost of the Program is the equivalent of US$660,000, in accordance with the following Budget:

Budget

(in US$)

| Program Components | BANK | COUNTERPART | TOTAL |
| --- | --- | --- | --- |
| Action Plan | 105,000 |  | 105,000 |
| Enhanced Institutional Capacity | 280,000 | 10,000 | 290,000 |
| Development of a Results-Based M&E tool | 100,000 |  | 100,000 |
| Awareness and consensus building | 30,000 | 35,000 | 65,000 |
| Program Coordinator | 55,000 |  | 55,000 |
| Audits and Evaluation | 15,000 |  | 15,000 |
| Contingencies | 15,000 | 15,000 | 30,000 |
| TOTAL | 600,000 | 60,000 | 660,000 |

IV.	Execution

  - The Program will be under technical responsibility of the Budget Director of the Executing Agency, who will act as Technical Director (hereinafter “TD”). The TD will be assisted by a Program Coordinator (hereinafter “PC”), who will be hired with Contribution resources to ensure a coordinated effort for the implementation of the administrative decisions approved by the TD. In addition, there will be Program Focal Points (hereinafter “PFP”) at the Ministry of Health and at the Executing Agency, financed also with Contribution Resources. The TC, PC and PFP will hold bi-weekly meetings to oversee Program implementation.

  - The PC will: (i) prepare for the TD’s approval the annual plans and work schedules for the Program; (ii) coordinate Program execution and support ministerial PFP in the execution of activities falling within the scope of the Ministry of Health and the Executing Agency; (iii) select and contract the consultants for the Program; (iv) prepare progress reports and propose the necessary measures to correct difficulties that may arise during execution; and (v) approve requests to purchase equipment and training materials for the Program.

  - PFP will (i) assist the PC in the preparation and update of annual work plans; (ii) coordinate implementation of activities falling within the scope of their relevant ministries; (iii) ensure coordination with the regions and among both ministries (Education and Health); (iv) participate in Program-related activities; and (v) provide feedback for overall Program implementation.

  - Administrative support for the execution will be provided by the existing Project Execution Unit (hereinafter “PEU”) of the Fiscal and Financial Management Program. As part of the general administrative activities, the PEU will be responsible for: (i) assisting the PC and PFP in monitoring execution performance, and collecting the information needed for the indicators specified in the logical framework; (ii) conducting the procurement and processing the contracts required for Program implementation; (iii) preparing and presenting disbursement requests and justification of the use of funds to the Bank’s satisfaction, and the semiannual reports on the use of the revolving fund; (iv) maintaining the financial and accounting records related to the use of Program resources; (v) keeping adequate documentation to support the disbursements received, which shall be made available for review by Bank personnel and/or external auditors; and (vi) preparing and presenting the financial statements of the Program to the Bank, duly certified by eligible external auditors.

  - The Program will assign some funds to provide per-diem assistance and encourage participation of the Executing Agency’s staff in capacity building activities related to Program implementation. Said payments will require Bank’s concurrence.