LEG/SGO/GY-903408-07

THE ANNEX

THE PROGRAM

Support for the Implementation of the Strategic Plan of the Audit Office

I.	Objective

1.01	The overall objective of the Program is to improve the structure and operation of the Audit Office of Guyana (AOG), by supporting the implementation of critical activities of its Strategic Development Plan that will contribute to consolidate its key role in Guyana’s oversight system. Specifically, the Program is designed to assist the AOG in further enhancing its technical and operational capacity in order to complete an adequate transition into an independent and improved national audit office, as mandated by the 2001 constitutional amendment, to improve public accountability.

II.	Description

2.01	Resources of the Program will be used to finance the following components:

Component 1. Enhancing professional audit practices and standards

2.02	This Component will support the implementation of critically important elements that the Audit Act defines as part of the core competences of the AOG, such as Value for Money Auditing (Performance Auditing) and Forensic Auditing. International auditing standards and national requirements are to be formally introduced and updated to cover these competences. This Component will finance: (i) consulting services for the design of the structure and operation of these specialized audit units; (ii) the preparation of audit manuals; (iii) the design of the core training activities in these areas; and (iv) provide technical support to start the operation of the units. In addition, some resources will help in the establishment of a Quality Review Unit to ensure adherence to all professional standards, practices and procedures.

2.03	According to the staffing plan contained in the AOG Strategic Plan, the Auditor General (AG) has committed to provide the necessary staff for the operations of the new units.

Component 2. Improving critical support systems to enhance operational effectiveness

2.04	This Component will be directed to improve the operation of support systems in the areas of Information Technology (IT) and records management. Some of the activities will be directed to enhance the contribution of these systems to the AOG capabilities to audit government information systems. In particular, the Program will support the design and implementation of a modern records management system for the AOG Registry.

2.05	The Program will also provide resources to support the reorganization of the AOG’s Finance and Accounts Division. Specialized consulting services will be contracted to set-up the new finance unit, and new instruments for reporting to the PAC will be provided. The provision of computers, equipment with mobile technology, and tools to improve communication connectivity will be financed under this component in order to support the records management and assure continuity of the IT modernization process.

Component 3. Institutionalizing best practices and skill transfer for sustainability

2.06	The activities under this Component will be directed to develop three sets of tools to ensure that all training is integrated into the AOG procedures, documentation and practices. These tools are defined as: (i) the enhancement of the “train the trainers” Program; (ii) the promotion of increased capacity building opportunities for the staff (training courses, participation in peer review Programs, distance learning activities, internships); and (iii) the development of an agenda for technical assistance activities supported by other Supreme Audit Institutions (SAI) or international audit organizations. The training areas that will be emphasized under these tools are: certified information system audit, fraud examination, value for money audit, quality control of audits, and specialized training for support divisions such as IT, human resource management and finance. In the case of forensic audit, the AOG will evaluate the possibility to establish a pilot certification program, that will be included in the training curriculum for this area.

Component 4. Creating stakeholder awareness of the oversight role of the AOG

2.07	In order to create stakeholder awareness in relation to the AOG’s duties, responsibilities, procedures, reporting mechanisms and its constructive oversight role, the Program will finance discrete dissemination activities through specialized workshops and publications. A critical activity under this Component will be directed to improve the coordination and communication mechanisms between the AOG and the Public Accounts Committee (PAC) and to inform other key stakeholders on the oversight responsibilities of Parliament through the PAC.

III.	Total Cost of the Program

  - The estimated cost of the Program is six hundred and sixty thousand dollars (US$660,000), in accordance with the following Budget:

Budget

(in US$)

|  | BANK | GOG | TOTAL |
| --- | --- | --- | --- |
| 1. Enhancing professional audit practices and standards | 175,000 | 0 | 175,000 |
| 2. Improving critical support systems | 163,500 | 27,500 | 191,000 |
| 3. Institutionalizing best practices | 124,000 | 0 | 124,000 |
| 4. Creating stakeholder awareness | 22,500 | 0 | 22,500 |
| 5. Administration | 45,000 | 32,500 | 77,500 |
| 6. Evaluation, audit and contingencies | 70,000 | 0 | 70,000 |
| TOTAL | 600,000 | 60,000 | 660,000 |

##### Execution

4.01	The Audit Office of Guyana (AOG) will be the Executing Agency of the Program, and will continue to maintain the Program Executing Unit (PEU) established under the operation ATN/SF-8184-GY.

4.02	As part of the general coordination activities, the PEU will be responsible for: (i) coordinating Program execution; (ii) revising and presenting the work plans, semiannual and final progress reports to the AOG for approval and later submission to the Bank, in addition to other reports requested by the Bank during the Program execution period; (iii) monitoring execution performance, and collecting the information needed for the indicators specified in the logical framework; (iv) conducting the procurement and processing the contracts required for Program implementation; (v) preparing and presenting disbursements requests and justification of the use of funds to the Bank’s satisfaction, and the semiannual reports on the use of the revolving fund; (vi) maintaining the financial and accounting records related to the use of Program resources, demonstrating at any time that the funds are used for the intended purpose; (vii) keeping adequate documentation to support the disbursements received; this information shall be made available for review by Bank personnel and/or external auditors; and (viii) preparing and presenting the financial statements of the Program to the Bank, duly certified by eligible external auditors.

4.03	The AOG will be assisted by a Technical Committee that will guarantee a coordinated effort for the implementation of any administrative decisions in connection with the Program execution. The Committee will consist of two Senior Audit Officers, the Human Resources Manager, the IT Manager and the Program Coordinator. Under this framework, the AOG will: (i) approve the plans and work schedules for the Program; (ii) select the employees who will work with the consultants for their assignment to the Program; (iii) analyze the progress reports submitted by the Coordinator and the consultants, proposing the necessary measures to correct difficulties that may arise during execution; and (iv) approve requests to purchase equipment and training materials for the Program. The AOG will delegate authority to the Technical Committee members for handling specific tasks that might be demanded during Program execution.

4.04	The PEU is currently operated by staff of the AOG, which was assigned to the Program on a full time basis. The AOG authorities have requested the Bank to finance top-up payments based on performance to the personnel responsible of the PEU. The quarterly performance benchmarks to allow these payments will be agreed between the bank and the AOG at the time of approval of the annual work plans. The payments will proceed upon satisfactory compliance of the quarterly benchmarks. Funding for the payments will come from the Bank’s contribution, as included in the category of Administration in the detailed budget for the Program, with concurrence of both the AOG and the Bank.