LEGIII/GY-893603-07

THE ANNEX

THE PROJECT

# Entrepreneurship Program to secure livelihoods of small farmers

# through improved production and marketing

I.	Objective

1.01	The goal of this Project is to contribute to the reduction of rural poverty in the coastal and near riverain regions of Guyana. Its purpose is to provide productive, marketing and capacity building services, materials and equipment to assist poor small farmer groups to increase their incomes by selling their produce through new market linkages, through the establishment of the Small Farmer Livelihood Program (“SFLP”) that will finance efficient, sustainable and market-driven projects.

  - It is a key principle of the Project to orient and support the small farmers to produce non-traditional crops for which unsatisfied market demand already has been identified, and to link the producers’ groups with these market opportunities. While there are some limited opportunities in the local market, it is likely that a large part of the production and market linkages will be oriented to export markets.

II.	Description

  - The Project will have two (2) Components: (1) a Non Reimbursable Financing Component; and (2) a Non-Reimbursable Technical Cooperation Component.

Component I. Non Reimbursable Financing Component

2.02	The Component will be will be used to establish a “responsive project fund” that will finance approximately 15 productive/commercial initiatives (projects) that will deliver technical assistance, training and productive or commercial inputs to selected small farmers groups, in response to their specific needs identified through participatory diagnostic exercises. This “responsive fund” will seek to facilitate farmers’ access to the inputs they require for improving their productive, value-added and commercial technologies and methodologies in non-traditional farming, as well as access to improved marketing linkages, and hence will ensure increases in their incomes and improvements in their livelihoods. The local counterpart will be contributed by Canadian International Development Agency (“CIDA”).

2.03	Project budgets will range from twenty five thousand dollars (US$25,000) to fifty thousand dollars (US$50,000), with an expected average of about US$44,000. The use of the funds in each project will vary according to the needs of each beneficiary group. Up to a maximum of five percent (5%) of project costs could also be used for a community-based field promoter to help organize project activities in the field, and/or for an accounts clerk to help organize the financial and accounting records of the beneficiary group.

Component II. Non-Reimbursable Technical Cooperation Component

2.04	The purpose of the Technical Cooperation Component is to provide direct technical assistance and training services in productive, commercial and capacity building issues to the beneficiary households, communities and productive networks. In general, this Component will support activities aimed at improving production methods and technologies, group organization, product quality, value-added and identifying and establishing new marketing linkages. The provision of this direct technical assistance and training will require two key inputs: (i) An operational project team (human resources) that will carry out all of the activities, from the identification of the communities, households, networks and projects, to the coordination and delivery of the services to be provided, accompaniment of project execution, and monitoring and evaluation of project results; and (ii) Financial resources for technical assistance services in specific areas of production, processing, packaging, marketing (in areas in which the Executing Agency may not have specific technical expertise), field travel expenses of the operational team, collection and dissemination of market information, training workshops, technical learning exchanges among farmers and processors, establishing alliances with key sectorial stakeholders, environmental analysis and monitoring, as well as audits and evaluations of the Project.

2.05	The Bank’s Technical Cooperation resources will cover the costs of the field-level technical assistance to beneficiary groups, market information, training workshops and materials, environmental consultancies, field travel of the operational project team, and project audits and evaluations. The Operating Regulations provide other details about how these funds will be used, managed, monitored and reported.

III.	Total Cost of the Project and Financing Plan

3.01	The estimated cost of the Project is the equivalent of one million five hundred ten thousand and five hundred ninety dollars (US$1,510,590) in accordance with the following investment categories and sources of financing:

Budget

(in US$ dollars)

|  |  |  | Bank |  | CIDA (->CHF) |  | TOTAL |
| --- | --- | --- | --- | --- | --- | --- | --- |
| DIRECT TECHNICAL ASSISTANCE |  |  |  |  |  |  |  |
| Short-term consultancies for technical assistance and extension services in production, processing, marketing, exporting, quality control, packaging, for producers, processors, ag entrepreneurs |  |  | $ 113,000 |  | $ - |  | $ 113,000 |
| Market studies and dissemination |  |  | $ 20,000 |  | $ - |  | $ 20,000 |
| Training workshops and meetings |  |  | $ 15,000 |  | $ - |  | $ 15,000 |
| Farm-to-farm beneficiary exchange visits |  |  | $ 15,000 |  | $ - |  | $ 15,000 |
| Travel, per diem, lodging for direct technical assistance, monitoring & evaluation |  |  | $ 32,000 |  | $ 32,000 |  | $ 64,000 |
| Environmental Consultant for sub-project analysis |  |  | $ 15,000 |  | $ - |  | $ 15,000 |
| TOTAL DIRECT TECHNICAL ASSISTANCE |  |  | $ 210,000 |  | $ 32,000 |  | $ 242,000 |
| OPERATIONAL UNIT & FIELD STAFF |  |  |  |  |  |  |  |
| CHF Technical Assistance |  |  |  |  |  |  |  |
| Project Director (4 years) |  |  | $ - |  | $ 98,962 |  | $ 98,962 |
| 3 Field Experts-Facilitators (4 years) |  |  | $ - |  | $ 216,952 |  | $ 216,952 |
| Other Short-Term Consultancies (inter-staff) |  |  | $ - |  | $ 30,144 |  | $ 30,144 |
| Sub-Total |  |  |  |  | $ 346,058 |  | $ 346,058 |
| CHF Operational Expenses |  |  |  |  |  |  |  |
| Admin-Financial Assistant (support staff) (4 years) |  |  | $ - |  | $ 52,469 |  | $ 52,469 |
| Operational Expenses/Rent/Equipment (4 years) |  |  | $ - |  | $ 137,221 |  | $ 137,221 |
| Indirect Cost CHF/Guyana |  |  | $ - |  | $ 34,497 |  | $ 34,497 |
| Sub-Total |  |  |  |  | $ 224,187 |  | $ 224,187 |
| TOTAL OPERATIONAL UNIT & FIELD STAFF |  |  | $ - |  | $ 570,245 |  | $ 570,245 |
|  |  |  |  |  |  |  | $ - |
| EVALUATIONS AND AUDITS |  |  |  |  |  |  | $ - |
| Mid-term Evaluation |  |  | $ 10,000 |  | $ - |  | $ 10,000 |
| Final Evaluation |  |  | $ 6,000 |  | $ - |  | $ 6,000 |
| Annual Audit of Responsive Fund |  |  |  |  |  |  | $ - |
| Final Audit of Technical Cooperation Comp. |  |  | $ 4,000 |  | $ - |  | $ 4,000 |
| TOTAL EVALUATIONS AND AUDIT |  |  | $ 20,000 |  | $ - |  | $ 20,000 |
| TOTAL TECHNICAL ASSISTANCE AND OPERATIONS |  |  | $ 230,000 |  | $ 602,245 |  | $ 832,245 |
| Non-reimbursable Financing for Responsive Project Fund |  |  | $ 600,000 |  | $ 65,000 |  | $ 665,000 |
|  |  |  | $ 200,000 |  |  |  |  |
| TOTAL PROJECT FINANCING |  |  | $ 830,000 |  | $ 667,245 |  | $ 1,497,245 |
| IaDB Admin Fee for Using Co financing Arrangement (IaDB-CIDA) |  | 2% |  |  | $13,345 |  | $13,345 |
| TOTAL -- CIDA Funding for Project Through IaDB (US$) |  |  | $ 830,000 |  | $680,590 |  | $1,510,590 |
| TOTAL -- CIDA Funding for Project Through IaDB (CAD$) (@1.15) |  |  | $954,500 |  | $782,678 |  | $1,737,178 |

#### Executing Agency and Mechanism

- 4.01	The Project’s Executing Agency will be Partners in Rural Development Limited.

  - For the execution of the Project, the Executing Agency will establish a Program Operational Unit (“POU”) in their main office in Georgetown, which will be responsible for coordinating, managing and controlling all activities and finances of the Project. Its role will be to make sure that the Project runs smoothly, to ensure that all the Project’s objectives are met and its activities are accomplished on time and within the established budget. The POU will be staffed by a Project Director, three field-level technical facilitators, and an administrative-financial assistant. The Executing Agency will designate a current staff member as Project Director and will hire the other staff members when the Project begins. All of the salaries and benefits of the POU staff will be covered by counterpart resources.

  - The selection criteria employed by the Executing Agency in the selection of projects will include the following: (i) Demonstrates clear and logical link between productive activities and identified market opportunities; (ii) Clearly defined indicators and tangible results in increasing small farmer income from non-traditional agriculture; (iii) All small farmers have equal access to participation in project activities, regardless of gender, ethnicity, age or religion; (iv) Includes aspects of sustainable management of natural resources and utilization of clean technologies; (v) Clarity of logic in relationship between project components; (vi) Feasible plan for sustainability of project impacts at household or cluster level; (vii) High probability of sustainability of income and technological improvements; (viii) Includes clear plans for data gathering for the purpose of monitoring and reporting results; (ix) Was designed using a participatory approach; (x) The planned duration is between 9 and 18 months, with an average of 12 months; and (xi) Required funding amount is between twenty five thousand dollars (US$25,000) and fifty thousand dollars (US$50,000).

V.	Monitoring and Evaluation

5.01	Monitoring: (a) during the execution of the Project and within sixty (60) days of the close of each calendar semester, the Executing Agency will present progress reports to the Bank. These reports will include progress in the following areas: (i) The accomplishment of the Project’s objectives (Logical Framework of the Project), with emphasis on increases in sales and income from agricultural activities; (ii) Execution of the Project’s annual work plan and budget; (iii) Formation and functioning of productive Inter-Community Groups (“ICGs”) and networks in each region; (iv) Potential market opportunities and linkages identified and established with private sector marketing, processing and/or industrial companies or providers; (v) Number, location, size and basic characteristics of projects financed; (vi) The training and technical assistance services provided to project beneficiaries; (vii) alliances around productive, value-added and marketing activities with key stakeholders in small-scale non-traditional farming identified and established; (viii) Information on the relationships and coordination with participating stakeholders institutions; (ix) Number, productive size and characteristics of the households that have benefited from the projects; (x) Results of the environmental assessments carried out for each project; (xi) Information on the ethnic representation of the Project staff and final beneficiary groups; and (xii) Problems encountered in the period and actions taken to resolve them. A final report will be presented within sixty (60) days of the end of the disbursement period. This final report should contain a summary of the results (outcomes) obtained compared with the Project’s original objectives, including impact on sales of non-traditional agricultural products and increases in agricultural incomes through the Project’s activities, and (b) the Bank will review the progress reports, and in the case that significant deficiencies are found in the implementation of the Project, the Bank will not authorize further commitments until the Executing Agency has taken the appropriate action to correct the situation.

5.02	Evaluations: (a) using Bank resources from the Technical Cooperation Component, the Bank, in coordination with CIDA, will contract consultants to carry out a mid-term and final evaluation of the Project. The mid-term evaluation will be carried out 24 months after the Project’s first disbursement or when 50% of the resources have been disbursed, whichever comes first. A final evaluation of the Project will be undertaken once 95% of the Project’s funds have been disbursed. Both of these evaluations will take into account the information obtained in the baseline surveys conducted of each household and community prior to project implementation, and (b) the mid-term evaluation will assess, at a minimum: (i) The Project’s response to the originally identified problems that it attempted to address; (ii) Progress in increasing agricultural incomes for project beneficiaries as well as the degree to which their market access has been improved for non-traditional crops; (iii) The level of fulfillment of the Project’s performance indicators from the Logical Framework, with emphasis on the number of projects financed, the number of beneficiaries and the establishment of new market linkages; and (iv) Lessons learned and recommendations to improve.