## Sheet1
PROCUREMENT PLAN FOR BANK EXECUTED OPERATIONS
Country: Brazil |  |  | Executing agency: IADB | [9 empty] | UDR: CBR
Project number: BR-T1371 |  |  | Sustainable Rural Development - Phase II MATOPIBA Kick-Off Project
Period covered by the plan: 6 months |  |  |  | Consulting services (US$): 340,000 |  |  |  |  | Non-consulting services (US$):
Component | Procurement Type | Service type | Description (4) | Estimated cost (US$) | Selection Method (2) | Type of contract | Source of financing and percentage |  |  |  | Estimated date of the procurement notice | Estimated contract start date | Comments
[7 empty] | IDB/MIF |  | Other Donor
[7 empty] | Amount | % | Amount | % |  |  |  | Direct Contracting
Select comp | Select Proc. Type | Goods Included in Firm Cons. RFP | Consultant 1: brief description |  | select method | Select Cont. Type |  |  |  |  | 2016-03-01 |  |  | International Competitive Bidding
Component 1,2,3 | A. Consulting services: | Firm Consultant (GN-2765) | Develop of two comprehensive reviews: (i) best practices and lessons learned from the phase I project “Low Carbon Agriculture and Avoided Deforestation to Reduce Poverty in Brazil” (BR-X1028) and (ii) an assessment on the MATOPIBA region to select the specific areas of intervention based on a study of microregions (geographic approach) and municipalities (Geopolitical approach). | 222000 | SC > $100K and <= $250K | Lump Sum | 222000 | 100 | 0 | 0 | 2017-09-04 | 2017-11-06 |  | National Competitive Bidding
Component 2 | A. Consulting services: | Individual Consultant (AM-650) | Analysis and recommendations of the most appropriate financial mechanisms for Rural SMEs in the in the MATOTIBA region through a comparative analysis of traditional credit lines, such as ABC, green finance lines (i.e. CRAs (Agribusiness Credit Rights)) and green bonds. | 38000 | SSS | PEC | 38000 | 100 | 0 | 0 | 2017-08-21 | 2017-09-25 |  | Shopping
Component 3 | A. Consulting services: | Individual Consultant (AM-650) | Develop a communications strategy to ensure that stakeholders are aware of the project and the appropriate channels are being used in the most effective way | 31000 | SSS | PEC | 31000 | 100 | 0 | 0 | 2017-09-25 | 2017-10-30 |  | Quality Based Selection
Component 4 | A. Consulting services: | Individual Consultant (AM-650) | Develop of a proposal for the design and implementation of Project's Phase II with a focus on strengthening the identification and engagement processes with stakeholders and defining the institutional arrangements to better manage the theory of change and monitor project results and its sustainability | 49000 | SSS | PEC | 49000 | 100 | 0 | 0 | 2017-10-16 | 2017-11-20 |  | Selection Based on the Consultants' Qualifications
Prepared by: Barbara Brakarz |  |  | TOTAL | 340000 |  |  | 340000 | 100 | 0 | 0
(1) Grouping together of similar procurement is recommended, such as publications, travel, etc. If there are a number of similar individual contracts to be executed at different times, they can be grouped together under a single heading, with an explanation in the comments column indicating the average individual amount and the period during which the contract would be executed. For example: an export promotion project that includes travel to participate in fairs would have an item called "airfare for fairs", an estimated total value od US$5,000, and an explanation in the Comments column: "This is for approximately four different airfares to participate in fairs in the region in years X and X1".
(2) Individual consultants: IICQ: International Individual Consultant Selection Based on Qualifications; SSS: Single Source Selection. Selection process to be done in accordance with AM-650.
(2) Consulting firms: Per GN-2765-1, Consulting Firm selection methods for Bank-executed Operations are: Single Source Selection (SSS); Simplified Competitive <= 100K (SC <=100K); Simplified Competitive >100K and <=250K (SC >100K and <=250K); Fully Competitive >250K and Framework Agreement Task Order (FWTO). All Consulting Firm selection processes under this policy must use the electronic module in Convergence.
(2) Goods: Per GN-2765-1, par. A.2.2.c: "The procurement of goods and related services, except when such goods and related services are necessary to achieve the objectives of the Bank-executed Operational Work and are included in the consulting services contract and represent less than ten percent (10%) of the consulting services contract value."