# Procurement plan

General information

Country: Ecuador.

Executing agency:  Inter-American Development Bank.

Technical cooperation project name: Improving the Business Climate for Forest-based Investments in Ecuador.

Technical cooperation project and loan contract numbers: EC-T1103.

Brief description of the project’s objectives and components: The objective of this operation is to undertake the Process to Improve the Business Climate for Forest Investment (PROMECIF) (see www.iadb.org/homeid/home-id.htm) for Ecuador by developing the following specific objectives: 1.) prepare a strategic action plan to improve the business climate for forest-based investments; 2.) identify and designing institutional and legal reforms to be implemented in the short term; and 3.) prepare a business plan to improve the performance, increase participants, and diversify and added value to the forest business clusters already exporting from Ecuador.

Estimated date of the final disbursement: 12 months after consulting services contract signed.

- A. Introduction

Procurement of contracts financed by the Inter-American Development Bank will be conducted in accordance with the Policies for Procurement of Works and Goods financed by the Inter-American Development Bank (current edition), and is open to all eligible bidders as defined in the policies. Consulting services will be selected and contracted in accordance with the Policies for the Selection and Contracting of Consultants financed by the Inter-American Development Bank (current edition).  Fifty percent (50%) of the financing of the technical cooperation is tied to the use of Swedish consulting services. Up to US$75,000 (seventy five thousand dollars) can be used to contract consultants from borrowing member countries of the IDB or from any IDB member country that has a reciprocity clause in its trust fund agreement, or pay for other eligible expenses.

- B. Procurement plan

The procurement plan for technical cooperation project Improving the Business Climate for Forest-based Investments in Ecuador covers the entire project execution period.  The plan, which is summarized in Appendix 1, indicates the procedure to be used for the procurement of services, and the method of selecting consultants, for each contract. It also estimated cost of each contract; and estimated dates for the publication of specific procurement notices and completion of the contracts included in this project.

- C. Project procurement

The procurements to be made for the proposed project are described in general below.

Procurement of consulting services: Contract a firm to undertake the Process to Improve the Business Climate for Forest Investment (PROMECIF).  The consulting firm to be selected will have to count with at least the following professionals to undertake the work: forest economist (to coordinate the team); forest investment expert with experience in investment analysis and forest business development; institutional development expert; forest and business lawyer; Business development services expert; and a professional website designer.  The study will generate the following outputs: initiation of the Process for Improvement of the Business Climate for Forest Investments (establishment and operation of the CC, the calculation of Ecuador’s Index for Forest Investment Attractiveness using the most recent data; and the definition of an strategic action plan to improve the business climate for forest based investments).  Institutional and legal measures to be implemented in the short term identified and the operational inputs necessary for their successful adoption designed.  Business plan for a selected forest-based exporting cluster designed to be implemented as part of the future financing packages.  Training and outreach to stakeholder and dissemination of results through the Internet. The documentation generated will have to be produced in Spanish, with executive summaries in English.  Contracted services are expected to start during the fourth quarter of 2007 and last for 12 months, mostly conducted in Ecuador.

A consulting firm for the project will be selected using the standard request for proposals (RFP) issued by the Bank, or an RFP satisfactory to the Bank in cases where the standard RFP is not applicable. An individual consultant will be selected bearing in mind the provisions of chapter V of the policy contained in document GN-2350-7.

Appendix I.

| Ref. No. | Description of the contract and estimated cost of procurement | Procurement method | Source of financing and percentage |  | Prequalification (Yes / No) | Estimated dates |  | Status (pending/in process/ awarded/ cancelled) | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | IDB % | Local/other % |  | Publication of specific procurement notice | Completion of contract |  |  |
| 1 | Consulting services Improving the Business Climate for Forest-based Investments in Ecuador. Estimated cost- (US$147,000 | FBS | 100 | 0 | No | Ago-07 | Nov/08 | Pending | US$75,000 (seventy five thousand dollars) is tied to the use of Swedish consulting services. The balance can be used to contract consultants from borrowing member countries of the IDB or from any IDB member country that has a reciprocity clause in its trust fund agreement, or pay for other eligible expenses. |

FBS: Selection under a fixed budget.